# Engineering Pulse — Mobile ADS Q3 W33 - 17-21 Aug

Planned sprint ADS Q3 W33 - 17-21 Aug • planning snapshot + end-of-sprint outcome snapshot

This version uses the planning snapshot as the promise set and the outcome snapshot as the result set. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 4/12 visible items. The team absorbed noise well — 0/2 added items were closed — but predictability on committed work was only 40.0% (4/10), and bugs made up 25.0% of completed items. The main drag was execution system quality, not readiness: 4/6 carryovers had been marked Ready at planning time.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 40.0% (4/10) | Planned items marked Done ÷ all planned committed items |
| Committed carryover | 60.0% (6/10) | Planned committed carryovers ÷ all planned committed items |
| Finish predictability | 50.0% (4/8) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 100.0% (2/2) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 16.7% (2/12) | Added items ÷ all visible items |
| Added work closure | 0/2 | All added items marked Done |
| Reactive load (bug share) | 25.0% (1/4) | Completed bugs ÷ all completed work |
| Planning quality | 70.0% (7/10) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 0 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

The sprint did not fail; it traded predictability for responsiveness. 0/2 added items were closed, but that responsiveness came with 25.0% bug share and diluted committed completion.

The miss pattern is concentrated: 3 partial-completion carryovers, 0 dependency-driven misses, and 3 committed items that never really started.

Most misses were not caused by poor readiness. 4 of the 6 carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 2 | 0 | 0 | 0 | 2 | 50.0% |
| Task | 1 | 0 | 0 | 0 | 1 | 25.0% |
| Bug | 1 | 0 | 0 | 0 | 1 | 25.0% |

# Committed work: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Committed items | 10 | Explicit promise set |
| Committed done | 4 | Closed as promised |
| Committed carry over | 6 | Unfinished promise |
| Committed items marked Ready | 7 | Planning-quality input |
| Carryovers marked Ready | 4 | Ready did not guarantee finish |
| Carryovers not started | 3 | Execution focus gap |
| Carryovers started but unfinished | 3 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Status | Why it carried |
| --- | --- | --- | --- |
| ADS-4419 — Story — [Elev][Părinte] - Redesign - Noutati & Activitati | stefan musat | In Progress | Partial completion |
| ADS-5808 — Bug — [MOB][Wellbeing] - Parintele nu poate vizualiza testele de autocunoastere pe mob | Antoci Razvan | To Do | Not started |
| ADS-8297 — Story — [Elev][Parinte] - Redesign - Materii | stefan musat | In Progress | Partial completion |
| ADS-8298 — Story — [Elev][Parinte] - Redesign - Gradinite | stefan musat | To Do | Not started |
| ADS-8378 — Story — [Elev][Parinte] Materie detalii | Stefan Agrigoroaei | In Progress | Partial completion |
| ADS-8477 — Improvement — [Mobile][Teme] - Filtru materii | Stefan Agrigoroaei | To Do | Not started |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 3 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 0 | Capacity protection or dependency timing created slip |
| Not started | 3 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 3 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| None |  |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did committed items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show carryovers split by progress continuation, dependency, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 10 | 10 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 12 | 12 issues in the Friday review snapshot |
| Normalized sprint fact base | 12 | 12 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.