# Engineering Pulse — Org Adservio ADS Q2 W22 - 01-05 Iunie

Aggregated sprint ADS Q2 W22 - 01-05 Iunie • deduplicated roll-up across included teams

This org roll-up aggregates deduplicated frozen issue facts across 4 team snapshots. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 45/103 visible items. The org roll-up absorbed noise reasonably well — 14/24 added items were closed — but finish predictability was only 40.9% (27/66), and bugs made up 48.9% of completed items. Planning-baseline carryover includes 39 finish misses and 8 expected progress continuations.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 39.2% (31/79) | Planned items marked Done ÷ all planned committed items |
| Planning-baseline carryover | 60.8% (48/79) | All planned items not Done, including expected Progress continuations |
| Finish-intent carryover | 59.1% (39/66) | Finish-intent planned items not Done ÷ all finish-intent planned items |
| Finish predictability | 40.9% (27/66) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 80.0% (8/10) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 23.3% (24/103) | Outcome-only items ÷ all visible items |
| Added work closure | 14/24 | All added items marked Done |
| Reactive load (bug share) | 48.9% (22/45) | Completed bugs ÷ all completed work |
| Planning quality | 49.4% (39/79) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 5 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

Across included teams, the sprint did not fail; it traded predictability for responsiveness. 14/24 added items were closed, but that responsiveness came with 48.9% bug share and diluted finish predictability.

The miss pattern is concentrated: 12 partial-completion carryovers, 5 dependency-driven misses, and 25 planning-baseline items that never really started.

Most misses were not caused by poor readiness. 19 of the 48 planning-baseline carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 4 | 2 | 1 | 0 | 7 | 15.6% |
| Task | 7 | 2 | 1 | 0 | 10 | 22.2% |
| Bug | 13 | 9 | 0 | 0 | 22 | 48.9% |

# Planning baseline: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Planning-baseline items | 79 | Items present in the frozen planning snapshot |
| Planning-baseline done | 31 | Closed by sprint review |
| Planning-baseline carryover | 48 | All planned items still open, including Progress continuation |
| Finish-intent carryover | 39 | Planned-to-finish items that did not finish |
| Progress continuation | 8 | Progress-intent planned items still open as expected |
| Planning-baseline items marked Ready | 39 | Planning-quality input |
| Carryovers marked Ready | 19 | Ready did not guarantee closure |
| Carryovers not started | 25 | Execution focus gap |
| Carryovers started but unfinished | 17 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Intent | Status | Why it carried |
| --- | --- | --- | --- | --- |
| ADS-1757 — Story — [Financiar] - Plati partiale | Edgar Alexa | Finish | In Progress | Dependency delay |
| ADS-2564 — Story — [School managment/Teachers] - Modules to be tested until the end of the school year | Cosmin Olaru | Progress | To Do | Dependency delay |
| ADS-406 — Bug — [Files] Missing description in ‘’Istoric’ when sharing documents | Antoci Razvan | Finish | To Do | Not started |
| ADS-4341 — Bug — [Condica de prezenta] - Nu apare butonul ,, semneaza condica pentru toata ziua | Vlad Lihaceanu | Finish | To Do | Not started |
| ADS-4439 — Bug — [Teste si chestionare] - Numarul de destinatari care se afiseaza nu corespunde cu numarul real de destinatari | Marian Andrei | Finish | To Do | Not started |
| ADS-4857 — Bug — [Mesagerie] - Restricționarea mesajelor de grup, conform configurărilor setate | Petronel Pavel | Progress | In Progress | Partial completion |
| ADS-5722 — Bug — [BE/FE] Modal adauga note | Andrei Dragan | Finish | To Do |  |
| ADS-5808 — Bug — [FE][Wellbeing] - Parintele nu poate vizualiza testele de autocunoastere pe mob | Antoci Razvan | Finish | To Do | Not started |
| ADS-5919 — Bug — [Fotografii] - Distribuirea nu este afișată exclusiv pe clasele sau grupele configurate în modulul Clase | Petronel Pavel | Finish | To Do | Not started |
| ADS-6494 — Story — Log levels & Log formats | Cojan Paul-Catalin | Finish | In Progress | Not started |
| ADS-6495 — Story — Service Internal API | Ionut Ciolan | Finish | Done | Partial completion |
| ADS-6499 — Story — Implementat CRUD Etnii in Laravel | Ionut Ciolan | Finish | Done | Not started |
| ADS-6501 — Story — Input validation errors | Ionut Ciolan | Finish | Done | Partial completion |
| ADS-6545 — Story — Implementare v1 layer comunicare native-web *post message bridge | Ivan Ioana | Finish | To Do | Not started |
| ADS-6562 — Story — Remove any mentions of Laravel in production mode | Ionut Ciolan | Finish | Done | Partial completion |
| ADS-6698 — Bug — [FE/BE] Restrictie vizualizare fise scolare | Marian Andrei | Finish | To Do | Not started |
| ADS-6712 — Task — [Note/absențe] - Recuperare informații | Marian Andrei | Finish | To Do | Not started |
| ADS-7009 — Task — Dezactivare actiuni noteaza/absenta (si bulk) daca media anuala si/sau media semestriala este incheiata | Ivan Ioana | Finish | To Do | Not started |
| ADS-7141 — Story — [Mob] - Redesign dashboard profesor | Stefan Agrigoroaei | Finish | In Progress | Bug / rework pressure |
| ADS-7284 — Story — Refactorizare "Anuleaza recurenta" | Edgar Alexa | Progress | In Progress | Partial completion |
| ADS-7330 — Task — [BE] - Valoare implicita incorecta pentru tipul de calcul al mediei la adaugarea unei materii noi | Andrei Dragan | Finish | To Do |  |
| ADS-7375 — Story — [BE/FE] - Disciplinele in EN pentru programele de studiu din EN | Virlan Francisc-Gabriel | Finish | Code Review | Partial completion |
| ADS-7388 — Bug — docgen2-api: gradebook view/download endpoints return HTTP 500 - 15 hits/Friday | Ivan Ioana | Finish |  | Missing from outcome snapshot |
| ADS-7389 — Bug — AdservioAPI.php: svcAuth self-call failures turn web API endpoints into HTTP 500 - 20 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7390 — Bug — rooms-api: room search endpoint returns HTTP 500 - 3 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7405 — Story — [BE] - Local Cache | Alex Murarescu | Finish | In Progress | Dependency delay |
| ADS-7423 — Task — [Stiri] - Updates after release/feedback | Alex Murarescu | Finish | In Progress | Partial completion |
| ADS-7427 — Story — [Admitere v2][Taxe] - 3. Admin Vizualizare/Validare plată | Dragoș Ivan | Finish | In Progress | Dependency delay |
| ADS-7428 — Story — [Admitere v2][Taxe] - 4. Candidate - Necesita modificări | George Murgoci | Finish | In Progress | Partial completion |
| ADS-7430 — Story — [Admitere v2][Taxe] - 5. Export platile candidatului | George Murgoci | Finish | To Do | Not started |
| ADS-7448 — Bug — [BE] Grades.php: deleting a grade can deadlock on cat_note and return HTTP 500 - 8 hits/24h | Andrei Dragan | Finish | To Do | Not started |
| ADS-7451 — Bug — [BE] - Condica - Activitati duplicate | Ionut Ciolan | Finish | In Progress | Partial completion |
| ADS-7454 — Story — [MOB] - Afisare medii in functie de perioada de studiu | stefan musat | Progress | In Progress | Priority Change |
| ADS-7460 — Bug — Absences time interval export_xls returns HTTP 500 for inverted date range (6 errors/24h) | Marian Andrei | Finish | To Do | Not started |
| ADS-7484 — Bug — Session.php: session_start() fails reading session data during teacher class-book requests - 26 errors/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7495 — Story — [FE/BE][Adeverinte absolvire] - Creare Probe evaluare | Ionut Ciolan | Progress | In Progress | Partial completion |
| ADS-7496 — Story — [FE/BE][Adeverinte absolvire] - Probe&medie pe situatie scolara | andrei.alexandru | Progress | In Progress | Partial completion |
| ADS-7519 — Task — [BE] "Afișează noutăți Adservio" toggle is non-functional | Alex Murarescu | Finish | In Progress | Dependency delay |
| ADS-7575 — Bug — M_export.php / Export.php: student export references missing second-semester average column and returns HTTP 500 on /ro/secretary/export/elevi - 16 hits/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-760 — Bug — [Classes][LCY][WEB][FE/MOB] - Classroom - Unable to delete a document attached to a message | Antoci Razvan | Finish | To Do | Not started |
| ADS-7618 — Bug — [BE/FE] Chestionare - Descarcarea raspunsurilor individuale descarca mereu primul parinte din lista, iar status completare este gresit | Marian Andrei | Finish | In Progress | Not started |
| ADS-7654 — Bug — Grades.php / AverageCalculator: POST /api/v2/grades accepts grade but skips average recomputation - 2 errors/24h | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7666 — Bug — accommodations-api: shared HTTP 500 burst on POST /api/v2/accommodations/dorms/list and related endpoints - 16 hits/20m | Ionut Ciolan | Stretch / Optional | To Do | Bug / rework pressure |
| ADS-7688 — Bug — [BE] [Studenti] [Muzica]- Studentul nu este unificat pe baza CNP-ului la import | andrei.alexandru | Finish | To Do | Not started |
| ADS-7709 — Improvement — [MOB]: Nu se deschide modalul de adauga absenta / nota din catalog-secretariat | Stefan Agrigoroaei | Progress | To Do | Not started |
| ADS-7724 — Task — [FR] Setare calcul medie - Standard Romania | Andrei Dragan | Progress | To Do | Not started |
| ADS-7740 — Story — [TDD][Generare Adeverințe] - Creare document tehnic | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7743 — Bug — [FE/BE] - Bugs Admitere v3 | George Murgoci | Finish | In Progress | Partial completion |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 12 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 5 | Capacity protection or dependency timing created slip |
| Not started | 25 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 17 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| ADS-6360 — [Catalog PDF] - Număr indicatori incorect – Semestre | Ready for testing | Finish |
| ADS-7132 — [FE/BE] - Gestiunea restantierilor | Ready to merge | Progress |
| ADS-7729 — Îmbunătățirea procesului pentru import Excel studenți V2 | Ready to merge | Finish |
| ADS-7786 — [Docgen] -Catalogul pe semestre nu afiseaza datele legate de situatia scolara | Code Review |  |
| ADS-7795 — [FE] - Examenul de specialitate nu e trecut complet cand e cu virgula in catalogul PDF | Code Review |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did finish-intent items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show finish-intent carryovers split by dependency, partial completion, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Included teams in this org pulse: Mobile, Team 1, Team 2, University.

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 83 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 106 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 103 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 79 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 102 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 78 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 24 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 1 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 4 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Committed completion | 39.2% (31/79) | planned committed items marked Done ÷ all planned committed items | 31/79 | Open denominator JQL |
| Planning-baseline carryover | 60.8% (48/79) | planned baseline items not Done at review ÷ all planned baseline items | 48/79 | Open denominator JQL |
| Finish-intent carryover | 59.1% (39/66) | finish-intent planned items not Done at review ÷ all finish-intent planned items | 39/66 | Open denominator JQL |
| Finish predictability | 40.9% (27/66) | finish-intent committed items marked Done ÷ all finish-intent committed items | 27/66 | Open denominator JQL |
| Progress predictability | 80.0% (8/10) | progress-intent items that carried as intended ÷ all progress-intent committed items | 8/10 | Open denominator JQL |
| Added-during-sprint load | 23.3% (24/103) | visible items absent from planning and present in review ÷ all visible sprint items | 24/103 | Open denominator JQL |
| Added work closure | 14/24 | added visible items marked Done ÷ all added visible items | 14/24 | Open denominator JQL |
| Planning quality | 49.4% (39/79) | committed items marked Ready in planning snapshot ÷ all committed items | 39/79 | Open denominator JQL |
| Carryovers marked Ready | 39.6% (19/48) | carryovers that were marked Ready in planning snapshot ÷ all carryovers | 19/48 | Open denominator JQL |
| Reactive load | 48.9% (22/45) | completed bugs ÷ all completed work | 22/45 | Open denominator JQL |
| Workflow-truth mismatches | 5 | Done rows with non-final workflow status | 5/45 | Open denominator JQL |

Planning-baseline carryover includes both finish-intent misses and expected Progress continuations. Use Finish-intent carryover when you want only planned-to-finish items that did not finish.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.