# Engineering Pulse — Org Adservio ADS Q2 W23 - 08-12 June

Aggregated sprint ADS Q2 W23 - 08-12 June • deduplicated roll-up across included teams

This org roll-up aggregates deduplicated frozen issue facts across 4 team snapshots. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 58/114 visible items. The org roll-up absorbed noise reasonably well — 30/48 added items were closed — but finish predictability was only 42.4% (25/59), and bugs made up 51.7% of completed items. Planning-baseline carryover includes 34 finish misses and 4 expected progress continuations.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 42.4% (28/66) | Planned items marked Done ÷ all planned committed items |
| Planning-baseline carryover | 57.6% (38/66) | All planned items not Done, including expected Progress continuations |
| Finish-intent carryover | 57.6% (34/59) | Finish-intent planned items not Done ÷ all finish-intent planned items |
| Finish predictability | 42.4% (25/59) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 57.1% (4/7) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 42.1% (48/114) | Outcome-only items ÷ all visible items |
| Added work closure | 30/48 | All added items marked Done |
| Reactive load (bug share) | 51.7% (30/58) | Completed bugs ÷ all completed work |
| Planning quality | 34.8% (23/66) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 6 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

Across included teams, the sprint did not fail; it traded predictability for responsiveness. 30/48 added items were closed, but that responsiveness came with 51.7% bug share and diluted finish predictability.

The miss pattern is concentrated: 6 partial-completion carryovers, 3 dependency-driven misses, and 20 planning-baseline items that never really started.

Most misses were not caused by poor readiness. 12 of the 38 planning-baseline carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 9 | 0 | 0 | 0 | 9 | 15.5% |
| Task | 4 | 10 | 0 | 0 | 14 | 24.1% |
| Bug | 13 | 17 | 0 | 0 | 30 | 51.7% |

# Planning baseline: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Planning-baseline items | 66 | Items present in the frozen planning snapshot |
| Planning-baseline done | 28 | Closed by sprint review |
| Planning-baseline carryover | 38 | All planned items still open, including Progress continuation |
| Finish-intent carryover | 34 | Planned-to-finish items that did not finish |
| Progress continuation | 4 | Progress-intent planned items still open as expected |
| Planning-baseline items marked Ready | 23 | Planning-quality input |
| Carryovers marked Ready | 12 | Ready did not guarantee closure |
| Carryovers not started | 20 | Execution focus gap |
| Carryovers started but unfinished | 10 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Intent | Status | Why it carried |
| --- | --- | --- | --- | --- |
| ADS-1757 — Story — [Financiar] - Plati partiale | Paul Bostan | Finish | Testing | Dependency delay |
| ADS-406 — Bug — [Files] Missing description in ‘’Istoric’ when sharing documents | Petronel Pavel | Finish | In Progress | Not started |
| ADS-4341 — Bug — [Condica de prezenta] - Nu apare butonul ,, semneaza condica pentru toata ziua | Vlad Lihaceanu | Finish | To Do | Not started |
| ADS-4439 — Bug — [Teste si chestionare] - Numarul de destinatari care se afiseaza nu corespunde cu numarul real de destinatari | Marian Andrei | Finish | To Do | Not started |
| ADS-4763 — Story — [Statistici] - Exporturi Excel | Marian Andrei | Finish | To Do | Not started |
| ADS-4857 — Bug — [Mesagerie] - Restricționarea mesajelor de grup, conform configurărilor setate | Petronel Pavel | Finish | To Do | Partial completion |
| ADS-5722 — Bug — [BE/FE] Modal adauga note | Andrei Dragan | Finish | To Do | Not started |
| ADS-5808 — Bug — [FE][Wellbeing] - Parintele nu poate vizualiza testele de autocunoastere pe mob | Antoci Razvan | Finish | To Do | Not started |
| ADS-5919 — Bug — [Fotografii] - Distribuirea nu este afișată exclusiv pe clasele sau grupele configurate în modulul Clase | Petronel Pavel | Finish | To Do | Not started |
| ADS-6358 — Story — [FE/Mobile] - Setari Sistem de notare | stefan musat | Finish | Done |  |
| ADS-6494 — Story — Log levels & Log formats | Cojan Paul-Catalin | Finish | Code Review | Dependency delay |
| ADS-6545 — Story — Implementare v1 layer comunicare native-web *post message bridge | Ivan Ioana | Finish | To Do | Not started |
| ADS-6698 — Bug — [FE/BE] Restrictie vizualizare fise scolare | Marian Andrei | Finish | To Do | Not started |
| ADS-6712 — Task — [Note/absențe] - Recuperare informații | Marian Andrei | Finish | To Do | Not started |
| ADS-6990 — Bug — [MOB] - Mesaj gresit la stergerea unei note mai vechi de 24 ore | stefan musat | Finish | To Do |  |
| ADS-7389 — Bug — AdservioAPI.php: svcAuth self-call failures turn web API endpoints into HTTP 500 - 20 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7390 — Bug — rooms-api: room search endpoint returns HTTP 500 - 3 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7430 — Story — [Admitere v2][Taxe] - 5. Export platile candidatului&extinderea cu alte informatii ale candidatilor | George Murgoci | Finish | To Do | Not started |
| ADS-7448 — Bug — [BE] Grades.php: deleting a grade can deadlock on cat_note and return HTTP 500 - 8 hits/24h | Andrei Dragan | Finish | To Do | Not started |
| ADS-7454 — Story — [MOB] - Afisare medii in functie de perioada de studiu | stefan musat | Finish | Done | Priority Change |
| ADS-7484 — Bug — Session.php: session_start() fails reading session data during teacher class-book requests - 26 errors/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7487 — Story — [Admitere v2] - Adaugare candidat in billing&eliberare chitanta | Edgar Alexa | Progress | In Progress | Partial completion |
| ADS-7495 — Story — [FE/BE][Adeverinte absolvire] - Creare Probe evaluare | Ionut Ciolan | Progress | In Progress | Partial completion |
| ADS-7496 — Story — [FE/BE][Adeverinte absolvire] - Probe&medie pe situatie scolara | Ionut Ciolan | Progress | In Progress | Partial completion |
| ADS-7519 — Task — [BE] "Afișează noutăți Adservio" toggle is non-functional | Alex Murarescu | Finish | In Progress | Dependency delay |
| ADS-7534 — Story — [FE/BE][Adeverinte absolvire] - Flow generare adeverinte | Cristina Condrea | Progress | In Progress | Partial completion |
| ADS-7575 — Bug — M_export.php / Export.php: student export references missing second-semester average column and returns HTTP 500 on /ro/secretary/export/elevi - 16 hits/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7618 — Bug — [BE/FE] Chestionare - Descarcarea raspunsurilor individuale descarca mereu primul parinte din lista, iar status completare este gresit | Marian Andrei | Finish | In Progress | Not started |
| ADS-7653 — Bug — Clase_profesori.php / M_cmc.php: teacher-class assignment insert fails FK constraint in cat_cadre2materii2clase - 2 errors/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7654 — Bug — Grades.php / AverageCalculator: POST /api/v2/grades accepts grade but skips average recomputation - 2 errors/24h | Andrei Dragan | Finish | To Do | Not started |
| ADS-7666 — Bug — accommodations-api: shared HTTP 500 burst on POST /api/v2/accommodations/dorms/list and related endpoints - 16 hits/20m | Ionut Ciolan | Finish | To Do | Bug / rework pressure |
| ADS-7688 — Bug — [BE] [Studenti] [Muzica]- Studentul nu este unificat pe baza CNP-ului la import | andrei.alexandru | Finish | To Do | Priority Change |
| ADS-7708 — Bug — [BE] - Personal universitar: Numele nu se actualizeaza corect dupa editare | andrei.alexandru | Finish | In Progress | Priority Change |
| ADS-7709 — Improvement — [MOB]: Nu se deschide modalul de adauga absenta / nota din catalog-secretariat | Stefan Agrigoroaei | Finish | To Do | Priority Change |
| ADS-7720 — Bug — [BE-JAVA][Asachi] - Nu mai apare optiune de 'Grupe asociate' pe studenti | andrei.alexandru | Finish | To Do | Priority Change |
| ADS-7796 — Task — [FR] istoric note sterse de catre profesorul ID 2329864 | Petronel Pavel | Finish | Ready for testing | Partial completion |
| ADS-7803 — Task — [SPIKE][FE] - Titulatura | Ivan Ioana | Finish | To Do | Not started |
| ADS-7812 — Bug — [MOB] - Dupa stergerea note nu se face refresh | Stefan Agrigoroaei | Finish | To Do |  |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 6 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 3 | Capacity protection or dependency timing created slip |
| Not started | 20 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 10 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| ADS-7009 — Dezactivare actiuni noteaza(si bulk) daca media anuala si/sau media semestriala este incheiata | Code Review | Finish |
| ADS-7141 — [Mob] - Redesign dashboard profesor | In Progress | Finish |
| ADS-7375 — [BE/FE] - Disciplinele in EN pentru programele de studiu din EN | Ready to merge | Finish |
| ADS-7807 — [MOB] - Notificări modul admitere | Ready for testing | Finish |
| ADS-7844 — [MOB] bifa pentru situatie incheiata sa fie vizibila pe mobile in conturile elevilor/parintilor | Ready for testing |  |
| ADS-7882 — [FE] - Eroare 400 la semnare condica | Code Review |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did finish-intent items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show finish-intent carryovers split by dependency, partial completion, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Included teams in this org pulse: Mobile, Team 1, Team 2, University.

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 71 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 124 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 114 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 66 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 114 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 66 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 48 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 0 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 10 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Committed completion | 42.4% (28/66) | planned committed items marked Done ÷ all planned committed items | 28/66 | Open denominator JQL |
| Planning-baseline carryover | 57.6% (38/66) | planned baseline items not Done at review ÷ all planned baseline items | 38/66 | Open denominator JQL |
| Finish-intent carryover | 57.6% (34/59) | finish-intent planned items not Done at review ÷ all finish-intent planned items | 34/59 | Open denominator JQL |
| Finish predictability | 42.4% (25/59) | finish-intent committed items marked Done ÷ all finish-intent committed items | 25/59 | Open denominator JQL |
| Progress predictability | 57.1% (4/7) | progress-intent items that carried as intended ÷ all progress-intent committed items | 4/7 | Open denominator JQL |
| Added-during-sprint load | 42.1% (48/114) | visible items absent from planning and present in review ÷ all visible sprint items | 48/114 | Open denominator JQL |
| Added work closure | 30/48 | added visible items marked Done ÷ all added visible items | 30/48 | Open denominator JQL |
| Planning quality | 34.8% (23/66) | committed items marked Ready in planning snapshot ÷ all committed items | 23/66 | Open denominator JQL |
| Carryovers marked Ready | 31.6% (12/38) | carryovers that were marked Ready in planning snapshot ÷ all carryovers | 12/38 | Open denominator JQL |
| Reactive load | 51.7% (30/58) | completed bugs ÷ all completed work | 30/58 | Open denominator JQL |
| Workflow-truth mismatches | 6 | Done rows with non-final workflow status | 6/58 | Open denominator JQL |

Planning-baseline carryover includes both finish-intent misses and expected Progress continuations. Use Finish-intent carryover when you want only planned-to-finish items that did not finish.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.