# Engineering Pulse — Org Adservio ADS Q2 W25 - 22-26 Jun

Aggregated sprint ADS Q2 W25 - 22-26 Jun • deduplicated roll-up across included teams

This org roll-up aggregates deduplicated frozen issue facts across 4 team snapshots. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 48/112 visible items. The org roll-up absorbed noise reasonably well — 38/57 added items were closed — but predictability on committed work was only 37.4% (34/91), and bugs made up 56.2% of completed items. The main drag was execution system quality, not readiness: 13/57 carryovers had been marked Ready at planning time.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 37.4% (34/91) | Planned items marked Done ÷ all planned committed items |
| Committed carryover | 62.6% (57/91) | Planned committed carryovers ÷ all planned committed items |
| Finish predictability | 40.0% (32/80) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 75.0% (6/8) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 50.9% (57/112) | Added items ÷ all visible items |
| Added work closure | 38/57 | All added items marked Done |
| Reactive load (bug share) | 56.2% (27/48) | Completed bugs ÷ all completed work |
| Planning quality | 20.9% (19/91) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 4 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

Across included teams, the sprint did not fail; it traded predictability for responsiveness. 38/57 added items were closed, but that responsiveness came with 56.2% bug share and diluted committed completion.

The miss pattern is concentrated: 15 partial-completion carryovers, 2 dependency-driven misses, and 24 committed items that never really started.

Most misses were not caused by poor readiness. 13 of the 57 carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 4 | 4 | 0 | 0 | 8 | 16.7% |
| Task | 5 | 4 | 0 | 0 | 9 | 18.8% |
| Bug | 0 | 27 | 0 | 0 | 27 | 56.2% |

# Committed work: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Committed items | 91 | Explicit promise set |
| Committed done | 34 | Closed as promised |
| Committed carry over | 57 | Unfinished promise |
| Committed items marked Ready | 19 | Planning-quality input |
| Carryovers marked Ready | 13 | Ready did not guarantee finish |
| Carryovers not started | 24 | Execution focus gap |
| Carryovers started but unfinished | 17 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Status | Why it carried |
| --- | --- | --- | --- |
| ADS-406 — Bug — [Files] Missing description in ‘’Istoric’ when sharing documents | Petronel Pavel | To Do | Not started |
| ADS-4341 — Bug — [Condica de prezenta] - Nu apare butonul ,, semneaza condica pentru toata ziua | Luiza Horlescu | To Do | Not started |
| ADS-4439 — Bug — [Teste si chestionare] - Numarul de destinatari care se afiseaza nu corespunde cu numarul real de destinatari | Marian Andrei | To Do | Not started |
| ADS-4857 — Bug — [Mesagerie] - Restricționarea mesajelor de grup, conform configurărilor setate | Petronel Pavel | To Do | Not started |
| ADS-5722 — Bug — [BE/FE] Modal adauga note | Andrei Dragan | In Progress | Not started |
| ADS-5737 — Bug — [MOB][Photo] - Nu functioneaza filtrele de ani si de albume | Stefan Agrigoroaei | To Do | Not started |
| ADS-5784 — Story — [FE/BE] Refactor pagina de permisiuni | Petronel Pavel | To Do |  |
| ADS-5808 — Bug — [MOB][Wellbeing] - Parintele nu poate vizualiza testele de autocunoastere pe mob | Antoci Razvan | To Do | Not started |
| ADS-5919 — Bug — [Fotografii] - Distribuirea nu este afișată exclusiv pe clasele sau grupele configurate în modulul Clase | Petronel Pavel | To Do | Not started |
| ADS-6201 — Story — Log formatting - node.js, subscriptions | Dragoș Ivan | To Do | Partial completion |
| ADS-6494 — Story — Log levels & Log formats | Cojan Paul-Catalin | Done |  |
| ADS-6638 — Story — [Preferinte][Notificari] Refactor pagina de gestionare notificări | Petronel Pavel | In Progress | Partial completion |
| ADS-6698 — Bug — [FE/BE] Restrictie vizualizare fise scolare | Marian Andrei | To Do | Not started |
| ADS-6712 — Task — [Note/absențe] - Recuperare informații | Marian Andrei | To Do | Not started |
| ADS-6980 — Story — Tracing & Error Logging | Dragoș Ivan | To Do | Partial completion |
| ADS-6990 — Bug — [MOB] - Mesaj gresit la stergerea unei note mai vechi de 24 ore | stefan musat | To Do |  |
| ADS-7141 — Story — [Mob] - Redesign dashboard profesor | Stefan Agrigoroaei | Done | Bug / rework pressure |
| ADS-7266 — Task — [Portofoliu][Profesor] - Actualizare sectiuni | Petronel Pavel | In Progress | Partial completion |
| ADS-7305 — Task — [REQ] - Remote Session Termination for Users | Andrei Dragan | To Do |  |
| ADS-7389 — Bug — AdservioAPI.php: svcAuth self-call failures turn web API endpoints into HTTP 500 - 20 hits/Friday | Ionut Ciolan | To Do | Not started |
| ADS-7390 — Bug — rooms-api: room search endpoint returns HTTP 500 - 3 hits/Friday | Ionut Ciolan | To Do | Not started |
| ADS-7419 — Bug — [SUBSCRIPTIONS] - Bug-uri | Edgar Alexa | To Do | Not started |
| ADS-7430 — Story — [Admitere v2][Taxe] - 5. Export platile candidatului&extinderea cu alte informatii ale candidatilor | George Murgoci | To Do | Not started |
| ADS-7474 — Task — [FE] - Optimizare viteză de încărcare pagini | Dragoș Ivan | In Progress | Partial completion |
| ADS-7484 — Bug — Session.php: session_start() fails reading session data during teacher class-book requests - 26 errors/24h | Marian Andrei | To Do | Not started |
| ADS-7495 — Story — [FE/BE][Adeverinte absolvire] - Creare Probe evaluare | Ionut Ciolan | Code Review | Partial completion |
| ADS-7496 — Story — [FE/BE][Adeverinte absolvire] - Probe&medie pe situatie scolara | Ionut Ciolan | Code Review | Partial completion |
| ADS-7534 — Story — [FE/BE][Adeverinte absolvire] - Flow generare adeverinte | Cristina Condrea | In Progress | Partial completion |
| ADS-7575 — Bug — M_export.php / Export.php: student export references missing second-semester average column and returns HTTP 500 on /ro/secretary/export/elevi - 16 hits/24h | Marian Andrei | In Progress | Partial completion |
| ADS-7642 — Story — DSS Romania + Creeaza institutii updates | Cosmin Olaru | In Progress |  |
| ADS-7653 — Bug — Clase_profesori.php / M_cmc.php: teacher-class assignment insert fails FK constraint in cat_cadre2materii2clase - 2 errors/24h | Marian Andrei | To Do | Not started |
| ADS-7666 — Bug — accommodations-api: shared HTTP 500 burst on POST /api/v2/accommodations/dorms/list and related endpoints - 16 hits/20m | Ionut Ciolan | To Do | Bug / rework pressure |
| ADS-7732 — Bug — TUIASI M_fisiere.php: file list query expects fsScimCeacSyncFsID missing from on-prem schema and breaks document listings - 12 errors/24h | Marian Andrei | To Do | Not started |
| ADS-7746 — Bug — Fill.php / FormResultAnswerTable.php: questionnaire save fails when fraAnswer contains unsupported 4-byte emoji - 43 errors/72h | Marian Andrei | To Do | Dependency delay |
| ADS-7803 — Task — [SPIKE][FE] - Titulatura | Ivan Ioana | To Do | Not started |
| ADS-7807 — Story — [MOB] - Notificări modul admitere | Stefan Agrigoroaei | Ready for testing |  |
| ADS-7831 — Story — [Spike] - Mobile app cold start | stefan musat | To Do |  |
| ADS-7852 — Task — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata | Cosmin Olaru | Testing |  |
| ADS-7880 — Bug — TUIASI uni-api: catalog import and adjacent grades endpoints return HTTP 500 - 23 hits/72h | andrei.alexandru | In Progress |  |
| ADS-7890 — Story — [BE PHP][Cazari] - Stingerea obligatiilor din E-taxe | Ionut Ciolan | In Progress | Dependency delay |
| ADS-7896 — Story — Migrare documente S3 | Cojan Paul-Catalin | Merged | Partial completion |
| ADS-7904 — Bug — [BE] - Elev cu situatie scolara neincheiata apare in topul elevilor cu media 9,50,premianta | Andrei Dragan | In Progress | Partial completion |
| ADS-7907 — Task — [BE] Refactoring SQL_CALC_FOUND_ROWS | Marian Andrei | Ready for testing | Partial completion |
| ADS-7908 — Bug — [Prod][AWS][legacy-web] Auth recaptcha helper dereferences null verification response | Daniel Onisoru | To Do | Not started |
| ADS-7910 — Bug — [Prod][TUIASI][uni-api] DB pool exhaustion breaks academic-years, faculty, and grade-save flows | andrei.alexandru | In Progress |  |
| ADS-7952 — Story — [Persoana] - Implementare mecanism Atribute | andrei.alexandru | In Progress | Partial completion |
| ADS-7962 — Story — [MOB] Translate app in French | stefan musat | Testing |  |
| ADS-7976 — Story — [MOB] BFF - newsfeed | stefan musat | To Do | Partial completion |
| ADS-7981 — Bug — Notificările nu se trimit pe Admitere | George Murgoci | In Progress | Partial completion |
| ADS-7989 — Bug — [BE] - Job zilnic - publicare rezultate chestionare | Marian Andrei | To Do | Not started |
| ADS-8000 — Task — [UNI][Denumire disciplina] Refactor atribut Denumire disciplina - loc | Virlan Francisc-Gabriel | To Do | Not started |
| ADS-8007 — Improvement — Adaugare disciplina in modulul Portofoliu la "Rezultate la olimpiada" | Petronel Pavel | To Do |  |
| ADS-8008 — Task — [BE] Cleanup news legacy | Marian Andrei | Ready for testing |  |
| ADS-8046 — Bug — [Prod][AWS][legacy-web] POST /api/v2/clase/locks returns HTTP 500 when class-lock scope fields are empty - 11 errors/72h | Petronel Pavel | To Do | Not started |
| ADS-8060 — Bug — [BE] - Indicatori gresiti ID 1885 | Andrei Dragan | To Do | Not started |
| ADS-8061 — Bug — [Prod][AWS][legacy-web] School-transfer edit recalculates status for NULL student ID - 64 errors/72h | Andrei Dragan | To Do | Not started |
| ADS-8068 — Story — [MOB] - Încheiere situatie | Stefan Agrigoroaei | To Do |  |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 15 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 2 | Capacity protection or dependency timing created slip |
| Not started | 24 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 17 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| ADS-7574 — [UPG/ASachi] - Calculul mediilor la nivel de grupa/serie | Testing | Progress |
| ADS-7748 — Fisiere.php: POST /api/v2/fisiere/upload reuses non-unique thumb_/resized_ temp paths and races same-name image uploads - 9 warnings+errors/72h | Code Review | Finish |
| ADS-8010 — [BE] -Pe disciplina s-au modificat procentele | Ready to merge |  |
| ADS-8019 — [BE-JAVA] -Nu mai sunt afisate notele la laborator si seminar pe anumite discipline | Ready to merge |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did committed items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show carryovers split by progress continuation, dependency, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Included teams in this org pulse: Mobile, Team 1, Team 2, University.

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 88 | 88 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 116 | 116 issues in the Friday review snapshot |
| Normalized sprint fact base | 112 | 112 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.