# Engineering Pulse — Org Adservio ADS Q2 W26 - 29 Jun-03 Jul

Aggregated sprint ADS Q2 W26 - 29 Jun-03 Jul • deduplicated roll-up across included teams

This org roll-up aggregates deduplicated frozen issue facts across 4 team snapshots. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 54/106 visible items. The org roll-up absorbed noise reasonably well — 40/76 added items were closed — but predictability on committed work was only 47.1% (40/85), and bugs made up 50.0% of completed items. The main drag was execution system quality, not readiness: 8/45 carryovers had been marked Ready at planning time.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 47.1% (40/85) | Planned items marked Done ÷ all planned committed items |
| Committed carryover | 52.9% (45/85) | Planned committed carryovers ÷ all planned committed items |
| Finish predictability | 50.0% (32/64) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 58.8% (10/17) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 71.7% (76/106) | Added items ÷ all visible items |
| Added work closure | 40/76 | All added items marked Done |
| Reactive load (bug share) | 50.0% (27/54) | Completed bugs ÷ all completed work |
| Planning quality | 27.1% (23/85) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 18 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

Across included teams, the sprint did not fail; it traded predictability for responsiveness. 40/76 added items were closed, but that responsiveness came with 50.0% bug share and diluted committed completion.

The miss pattern is concentrated: 9 partial-completion carryovers, 4 dependency-driven misses, and 15 committed items that never really started.

Most misses were not caused by poor readiness. 8 of the 45 carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 7 | 3 | 0 | 0 | 10 | 18.5% |
| Task | 6 | 5 | 0 | 0 | 11 | 20.4% |
| Bug | 0 | 27 | 0 | 0 | 27 | 50.0% |

# Committed work: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Committed items | 85 | Explicit promise set |
| Committed done | 40 | Closed as promised |
| Committed carry over | 45 | Unfinished promise |
| Committed items marked Ready | 23 | Planning-quality input |
| Carryovers marked Ready | 8 | Ready did not guarantee finish |
| Carryovers not started | 15 | Execution focus gap |
| Carryovers started but unfinished | 12 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Status | Why it carried |
| --- | --- | --- | --- |
| ADS-4439 — Bug — [Teste si chestionare] - Numarul de destinatari care se afiseaza nu corespunde cu numarul real de destinatari | Marian Andrei | To Do | Not started |
| ADS-5784 — Story — [FE/BE] Refactor pagina de permisiuni | Petronel Pavel | In Progress | Late start / sequencing |
| ADS-5808 — Bug — [MOB][Wellbeing] - Parintele nu poate vizualiza testele de autocunoastere pe mob | Antoci Razvan | To Do | Not started |
| ADS-6183 — Bug — [MOB] - Utilizatorii de Android nu pot realiza poză direct la încărcarea scutirilor | stefan musat | Done |  |
| ADS-6201 — Story — Log formatting - node.js, subscriptions | Dragoș Ivan | To Do | Not started |
| ADS-6675 — Story — [Financiar] - Managementul penalitatilor | Edgar Alexa | In Progress | Partial completion |
| ADS-6698 — Bug — [FE/BE] Restrictie vizualizare fise scolare | Marian Andrei | To Do | Not started |
| ADS-6712 — Task — [Note/absențe] - Recuperare informații | Marian Andrei | To Do | Not started |
| ADS-6889 — Improvement — [Library] - Adăugat ESLint și bump la versiunile de Nest și MikroORM | Alex Murarescu | To Do | Not started |
| ADS-6990 — Bug — [MOB] - Mesaj gresit la stergerea unei note mai vechi de 24 ore | valentin.pal | Done |  |
| ADS-7219 — Bug — [MOB] - Fixes post release 06/04/2026 | Stefan Agrigoroaei | To Do | Priority Change |
| ADS-7305 — Task — [REQ] - Remote Session Termination for Users | Andrei Dragan | To Do | Not started |
| ADS-7389 — Bug — AdservioAPI.php: svcAuth self-call failures turn web API endpoints into HTTP 500 - 20 hits/Friday | Ionut Ciolan | To Do | Not started |
| ADS-7390 — Bug — rooms-api: room search endpoint returns HTTP 500 - 3 hits/Friday | Ionut Ciolan | To Do | Not started |
| ADS-7419 — Bug — [SUBSCRIPTIONS] - Bug-uri | Edgar Alexa | Ready for testing | Partial completion |
| ADS-7484 — Bug — Session.php: session_start() fails reading session data during teacher class-book requests - 26 errors/24h | Marian Andrei | To Do | Not started |
| ADS-7495 — Story — [FE/BE][Adeverinte absolvire] - Creare Probe evaluare | Ionut Ciolan | Code Review | Dependency delay |
| ADS-7496 — Story — [FE/BE][Adeverinte absolvire] - Probe&medie pe situatie scolara | Ionut Ciolan | Code Review | Dependency delay |
| ADS-7534 — Story — [FE/BE][Adeverinte absolvire] - Flow generare adeverinte | Cristina Condrea | In Progress | Partial completion |
| ADS-7653 — Bug — Clase_profesori.php / M_cmc.php: teacher-class assignment insert fails FK constraint in cat_cadre2materii2clase - 2 errors/24h | Marian Andrei | To Do | Not started |
| ADS-7666 — Bug — accommodations-api: shared HTTP 500 burst on POST /api/v2/accommodations/dorms/list and related endpoints - 16 hits/20m | Ionut Ciolan | To Do | Bug / rework pressure |
| ADS-7807 — Story — [MOB] - Notificări modul admitere | Stefan Agrigoroaei | Ready for testing |  |
| ADS-7831 — Story — [Spike] - Mobile app cold start | stefan musat | To Do |  |
| ADS-7849 — Story — Stergere date S3 | Cojan Paul-Catalin | To Do | Not started |
| ADS-7852 — Task — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata | Cosmin Olaru | Testing | Partial completion |
| ADS-7890 — Story — [BE PHP][Cazari] - Stingerea obligatiilor din E-taxe | Ionut Ciolan | Ready for testing | Dependency delay |
| ADS-7908 — Bug — [Prod][AWS][legacy-web] Auth recaptcha helper dereferences null verification response | Daniel Onisoru | To Do | Not started |
| ADS-7910 — Bug — [Prod][TUIASI][uni-api] DB pool exhaustion breaks academic-years, faculty, and grade-save flows | andrei.alexandru | Done |  |
| ADS-7952 — Story — [Persoana][Burse] - US1- Implementare mecanism Atribute | andrei.alexandru | In Progress | Partial completion |
| ADS-7958 — Story — [FE/BE] - Reconstituire scolaritate - transfer, an repetare | andrei.alexandru | To Do | Not started |
| ADS-7962 — Story — [MOB] Translate app in French | stefan musat | Done |  |
| ADS-7976 — Story — [MOB] BFF - newsfeed | stefan musat | Testing | Partial completion |
| ADS-7988 — Bug — [Prod][AWS][legacy-web] School update/logo storage uses invalid S3 endpoint or wrong region - 32,341 errors/72h | valentin.pal | Ready to merge |  |
| ADS-8004 — Improvement — [FE] - Elevii transferati apar in statistici ca "medii neconfirmate" | Marian Andrei | To Do |  |
| ADS-8047 — Bug — [BE-JAVA] - Student promovat ii apare in situatie scolara Absent | andrei.alexandru | Done |  |
| ADS-8049 — Bug — [MOB] - Primele doua ecrane de autentificare raman in limba romana dupa selectarea limbii engleze | valentin.pal | Done |  |
| ADS-8056 — Task — [BE] -Inchiderea cataloagelor istorice pentru facultatea CMMI | andrei.alexandru | In Progress | Partial completion |
| ADS-8061 — Bug — [Prod][AWS][legacy-web] School-transfer edit recalculates status for NULL student ID - 64 errors/72h | Andrei Dragan | To Do | Not started |
| ADS-8062 — Bug — [Prod][AWS][legacy-web] Certificate template fetch returns 500 when forms schema lookup gets 403 - 26 errors/72h | Petronel Pavel | To Do | Dependency delay |
| ADS-8071 — Story — Teste automate flow Subscripții | Edgar Alexa | In Progress | Partial completion |
| ADS-8073 — Task — [FE/BE] - Aducerea titularilor din planul curent in tab-ul restantieri pe disciplina | andrei.alexandru | In Progress | Partial completion |
| ADS-8118 — Bug — [BE] - Lipsa nota si catalog deschis pe restantieri | andrei.alexandru | To Do |  |
| ADS-8139 — Story — [MOB]Fix notification navigation | stefan musat | In Progress | Late start / sequencing |
| ADS-8140 — Story — [MOB] - Maarif Retake Exam | Stefan Agrigoroaei | To Do |  |
| ADS-8141 — Task — [FE][Situatie scolara] - Lipsa mesaj de eroare la modificarea mediei de absolvire |  | To Do |  |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 9 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 4 | Capacity protection or dependency timing created slip |
| Not started | 15 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 12 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| ADS-2001 — [BE][Setari ] - Desi profesoara a fost stearsa de la cadre didactice ea apare in continuare la roluri si permisiuni si nu se poate sterge de acolo- la stergere apare eroar 400 | To Do | Finish |
| ADS-4338 — [MOB][Dashboard][Parinte/elev] - Afișarea categoriei unității de învățamânt | Testing | Finish |
| ADS-5722 — [BE/FE] Modal adauga note | In Progress | Finish |
| ADS-6438 — [BE][UNI] - Sincronizare ID-uri Ani universitari/scolari - UNI/preuni - master | Ready to merge | Finish |
| ADS-6638 — [Preferinte][Notificari] Refactor pagina de gestionare notificări | Testing | Progress |
| ADS-6980 — Tracing & Error Logging | In Progress | Stretch / Optional |
| ADS-7319 — [Preferinte][Admin] - Stiri | Testing |  |
| ADS-7474 — [FE] - Optimizare viteză de încărcare pagini | To Do | Progress |
| ADS-7571 — Utilizatori.php: candidate profile_get() dereferences missing candidate row in GET /api/v2/utilizatori/profile - 48 warnings/24h | In Progress |  |
| ADS-7575 — M_export.php / Export.php: student export references missing second-semester average column and returns HTTP 500 on /ro/secretary/export/elevi - 16 hits/24h | Ready for testing | Finish |
| ADS-7854 — MY_Audit.php: audit hook emits non-numeric arithmetic warnings on TUIASI web traffic - 72 warnings/72h | In Progress | Finish |
| ADS-7907 — [BE] Refactoring SQL_CALC_FOUND_ROWS | Ready for testing | Progress |
| ADS-8000 — [UNI][Denumire disciplina] Refactor atribut Denumire disciplina - loc | Ready to merge | Finish |
| ADS-8010 — [BE] -Pe disciplina s-au modificat procentele | Ready to merge | Finish |
| ADS-8068 — [MOB] - Încheiere situatie | Testing | Finish |
| ADS-8072 — Admitere - Structură proiect, documentație, teste automate back-end | In Progress |  |
| ADS-8078 — Stergere elevi de test | In Progress |  |
| ADS-8098 — [MOB] - Filter school years | Testing |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did committed items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show carryovers split by progress continuation, dependency, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Included teams in this org pulse: Mobile, Team 1, Team 2, University.

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 88 | 88 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 119 | 119 issues in the Friday review snapshot |
| Normalized sprint fact base | 106 | 106 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.