# Engineering Pulse — Org Adservio ADS Q3 W27 - 06-10 Jul

Aggregated sprint ADS Q3 W27 - 06-10 Jul • deduplicated roll-up across included teams

This org roll-up aggregates deduplicated frozen issue facts across 4 team snapshots. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 47/119 visible items. The org roll-up absorbed noise reasonably well — 19/44 added items were closed — but finish predictability was only 40.4% (23/57), and bugs made up 59.6% of completed items. Planning-baseline carryover includes 34 finish misses and 11 expected progress continuations.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 37.3% (28/75) | Planned items marked Done ÷ all planned committed items |
| Planning-baseline carryover | 62.7% (47/75) | All planned items not Done, including expected Progress continuations |
| Finish-intent carryover | 59.6% (34/57) | Finish-intent planned items not Done ÷ all finish-intent planned items |
| Finish predictability | 40.4% (23/57) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 78.6% (11/14) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 37.0% (44/119) | Outcome-only items ÷ all visible items |
| Added work closure | 19/44 | All added items marked Done |
| Reactive load (bug share) | 59.6% (28/47) | Completed bugs ÷ all completed work |
| Planning quality | 28.0% (21/75) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 0 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

Across included teams, the sprint did not fail; it traded predictability for responsiveness. 19/44 added items were closed, but that responsiveness came with 59.6% bug share and diluted finish predictability.

The miss pattern is concentrated: 11 partial-completion carryovers, 5 dependency-driven misses, and 20 planning-baseline items that never really started.

Most misses were not caused by poor readiness. 11 of the 47 planning-baseline carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 8 | 0 | 1 | 0 | 9 | 19.1% |
| Task | 4 | 2 | 1 | 0 | 7 | 14.9% |
| Bug | 12 | 16 | 0 | 0 | 28 | 59.6% |

# Planning baseline: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Planning-baseline items | 75 | Items present in the frozen planning snapshot |
| Planning-baseline done | 28 | Closed by sprint review |
| Planning-baseline carryover | 47 | All planned items still open, including Progress continuation |
| Finish-intent carryover | 34 | Planned-to-finish items that did not finish |
| Progress continuation | 11 | Progress-intent planned items still open as expected |
| Planning-baseline items marked Ready | 21 | Planning-quality input |
| Carryovers marked Ready | 11 | Ready did not guarantee closure |
| Carryovers not started | 20 | Execution focus gap |
| Carryovers started but unfinished | 15 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Intent | Status | Why it carried |
| --- | --- | --- | --- | --- |
| ADS-2001 — Bug — [BE][Setari ] - Desi profesoara a fost stearsa de la cadre didactice ea apare in continuare la roluri si permisiuni si nu se poate sterge de acolo- la stergere apare eroar 400 | Ivan Ioana | Finish | To Do |  |
| ADS-4328 — Story — Headers in Mobile App | Dragoș Ivan | Stretch / Optional | To Do | Not started |
| ADS-4439 — Bug — [Teste si chestionare] - Numarul de destinatari care se afiseaza nu corespunde cu numarul real de destinatari | Marian Andrei | Finish | To Do | Not started |
| ADS-5808 — Bug — [MOB][Wellbeing] - Parintele nu poate vizualiza testele de autocunoastere pe mob | Antoci Razvan | Finish | To Do | Not started |
| ADS-5931 — Story — Seedere de date - cod in proiect | Andrei Dragan |  | To Do | Not started |
| ADS-6159 — Story — Notification Center for Mobile | Dragoș Ivan | Progress | To Do | Partial completion |
| ADS-6201 — Story — Log formatting - node.js, subscriptions | Dragoș Ivan | Stretch / Optional | To Do | Not started |
| ADS-6438 — Task — [BE][UNI] - Sincronizare ID-uri Ani universitari/scolari - UNI/preuni - master | andrei.alexandru | Finish | Ready to merge |  |
| ADS-6545 — Story — [SDK] Implementare v1 layer comunicare native-web *post message bridge | Ivan Ioana | Finish | Ready to merge | Not started |
| ADS-6675 — Story — [Financiar] - Managementul penalitatilor | Edgar Alexa | Finish | In Progress | Partial completion |
| ADS-6698 — Bug — [FE/BE] Restrictie vizualizare fise scolare | Marian Andrei | Finish | To Do | Not started |
| ADS-7305 — Task — [REQ] - Remote Session Termination for Users | Andrei Dragan | Progress | To Do | Not started |
| ADS-7389 — Bug — AdservioAPI.php: svcAuth self-call failures turn web API endpoints into HTTP 500 - 20 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7390 — Bug — rooms-api: room search endpoint returns HTTP 500 - 3 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7474 — Task — [FE] - Optimizare viteză de încărcare pagini | Dragoș Ivan | Progress | To Do | Partial completion |
| ADS-7484 — Bug — Session.php: session_start() fails reading session data during teacher class-book requests - 26 errors/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7495 — Story — [FE/BE][Adeverinte absolvire] - Creare Probe evaluare | Ionut Ciolan | Finish | Code Review | Dependency delay |
| ADS-7496 — Story — [FE/BE][Adeverinte absolvire] - Probe&medie pe situatie scolara | Ionut Ciolan | Finish | Code Review | Dependency delay |
| ADS-7534 — Story — [FE/BE][Adeverinte absolvire] - Flow generare adeverinte | Cristina Condrea | Progress | Testing | Partial completion |
| ADS-7535 — Story — [FE] - Download Adeverinta de absolvire | stefan.achim | Progress | In Progress | Dependency delay |
| ADS-7653 — Bug — Clase_profesori.php / M_cmc.php: teacher-class assignment insert fails FK constraint in cat_cadre2materii2clase - 2 errors/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7666 — Bug — accommodations-api: shared HTTP 500 burst on POST /api/v2/accommodations/dorms/list and related endpoints - 16 hits/20m | Ionut Ciolan | Finish | In Progress | Bug / rework pressure |
| ADS-7721 — Bug — Repartizari.php / M_elevi.php: grade-system visibility toggle inserts partial student config row and fails when no override exists - 3 errors/24h | Marian Andrei | Finish | To Do |  |
| ADS-7831 — Story — [Spike] - Mobile app cold start | stefan musat | Stretch / Optional | To Do |  |
| ADS-7849 — Story — Stergere date S3 | Cojan Paul-Catalin | Progress | In Progress | Partial completion |
| ADS-7852 — Task — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata | Andrei Dragan | Finish | Code Review | Partial completion |
| ADS-7890 — Story — [BE PHP][Cazari] - Stingerea obligatiilor din E-taxe | Ionut Ciolan | Finish | Ready for testing | Dependency delay |
| ADS-7907 — Task — [BE] Refactoring SQL_CALC_FOUND_ROWS | Marian Andrei | Finish | Ready for testing | Partial completion |
| ADS-7908 — Bug — [Prod][AWS][legacy-web] Auth recaptcha helper dereferences null verification response | Daniel Onisoru | Finish | To Do | Not started |
| ADS-7952 — Story — [Burse] - US1 - Implementare mecanism Atribute | andrei.alexandru | Progress | Code Review | Partial completion |
| ADS-7958 — Story — [FE/BE] - Reconstituire scolaritate - transfer, an repetare | stefan.achim | Progress | In Progress | Partial completion |
| ADS-8004 — Improvement — [FE] - Elevii transferati apar in statistici ca "medii neconfirmate" | Marian Andrei | Finish | To Do |  |
| ADS-8061 — Bug — [Prod][AWS][legacy-web] School-transfer edit recalculates status for NULL student ID - 64 errors/72h | Andrei Dragan | Finish | To Do | Not started |
| ADS-8062 — Bug — [Prod][AWS][legacy-web] Certificate template fetch returns 500 when forms schema lookup gets 403 - 26 errors/72h | Petronel Pavel | Finish | To Do | Dependency delay |
| ADS-8067 — Improvement — [Incadrare] Refactoring React & API | Andrei Dragan | Progress | To Do | Late start / sequencing |
| ADS-8068 — Story — [MOB] - Încheiere situatie | Stefan Agrigoroaei | Finish | To Do |  |
| ADS-8071 — Story — Teste automate flow Subscripții | Edgar Alexa | Progress | In Progress | Partial completion |
| ADS-8073 — Task — [FE/BE] - Aducerea titularilor din planul curent in tab-ul restantieri pe disciplina | andrei.alexandru | Progress | Code Review | Partial completion |
| ADS-8104 — Story — [BE-PHP] - Gestiunea cazarilor de vara | Ionut Ciolan | Finish | Testing |  |
| ADS-8105 — Story — Impartirea pe module | Ivan Ioana | Progress | In Progress |  |
| ADS-8108 — Bug — [Prod][AWS][legacy-web] Teacher exam-prep save writes unsupported peeTipPregatire value - 2 errors/72h | Marian Andrei | Finish | To Do | Not started |
| ADS-8111 — Bug — [FE/BE] - In centralizator note nu apare numele unei discipline | andrei.alexandru | Finish | In Progress | Not started |
| ADS-8118 — Bug — [BE] - Lipsa nota si catalog deschis pe restantieri | andrei.alexandru | Finish | To Do | Not started |
| ADS-8141 — Task — [FE][Situatie scolara] - Lipsa mesaj de eroare la modificarea mediei de absolvire | stefan.achim | Finish | To Do | Not started |
| ADS-8147 — Bug — [BE] - Nu apar studentii pe sesiunea 2 | andrei.alexandru | Finish | To Do | Not started |
| ADS-8151 — Bug — [Prod][AWS][legacy-web] POST /ro/secretary/export/elevi returns HTTP 500 from M_export num_rows on bool - 4 errors/72h | Marian Andrei | Finish | To Do |  |
| ADS-8153 — Bug — [Prod][TUIASI][accommodations-api] Student balance export returns HTTP 500 when mPDF hits pcre.backtrack_limit | andrei.alexandru | Finish | To Do | Not started |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 11 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 5 | Capacity protection or dependency timing created slip |
| Not started | 20 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 15 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| None |  |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did finish-intent items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show finish-intent carryovers split by dependency, partial completion, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Included teams in this org pulse: Mobile, Team 1, Team 2, University.

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 77 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 141 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 119 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 75 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 119 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 75 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 44 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 0 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 22 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Committed completion | 37.3% (28/75) | planned committed items marked Done ÷ all planned committed items | 28/75 | Open denominator JQL |
| Planning-baseline carryover | 62.7% (47/75) | planned baseline items not Done at review ÷ all planned baseline items | 47/75 | Open denominator JQL |
| Finish-intent carryover | 59.6% (34/57) | finish-intent planned items not Done at review ÷ all finish-intent planned items | 34/57 | Open denominator JQL |
| Finish predictability | 40.4% (23/57) | finish-intent committed items marked Done ÷ all finish-intent committed items | 23/57 | Open denominator JQL |
| Progress predictability | 78.6% (11/14) | progress-intent items that carried as intended ÷ all progress-intent committed items | 11/14 | Open denominator JQL |
| Added-during-sprint load | 37.0% (44/119) | visible items absent from planning and present in review ÷ all visible sprint items | 44/119 | Open denominator JQL |
| Added work closure | 19/44 | added visible items marked Done ÷ all added visible items | 19/44 | Open denominator JQL |
| Planning quality | 28.0% (21/75) | committed items marked Ready in planning snapshot ÷ all committed items | 21/75 | Open denominator JQL |
| Carryovers marked Ready | 23.4% (11/47) | carryovers that were marked Ready in planning snapshot ÷ all carryovers | 11/47 | Open denominator JQL |
| Reactive load | 59.6% (28/47) | completed bugs ÷ all completed work | 28/47 | Open denominator JQL |
| Workflow-truth mismatches | 0 | Done rows with non-final workflow status | 0/47 | Open denominator JQL |

Planning-baseline carryover includes both finish-intent misses and expected Progress continuations. Use Finish-intent carryover when you want only planned-to-finish items that did not finish.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.