# Engineering Pulse — Org Adservio ADS Q3 W29 - 20-24 Jul

Aggregated sprint ADS Q3 W29 - 20-24 Jul • deduplicated roll-up across included teams

This org roll-up aggregates deduplicated frozen issue facts across 4 team snapshots. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 32/70 visible items. The org roll-up absorbed noise reasonably well — 6/10 added items were closed — but finish predictability was only 48.8% (21/43), and bugs made up 37.5% of completed items. Planning-baseline carryover includes 22 finish misses and 10 expected progress continuations.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 43.3% (26/60) | Planned items marked Done ÷ all planned committed items |
| Planning-baseline carryover | 56.7% (34/60) | All planned items not Done, including expected Progress continuations |
| Finish-intent carryover | 51.2% (22/43) | Finish-intent planned items not Done ÷ all finish-intent planned items |
| Finish predictability | 48.8% (21/43) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 66.7% (10/15) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 14.3% (10/70) | Outcome-only items ÷ all visible items |
| Added work closure | 6/10 | All added items marked Done |
| Reactive load (bug share) | 37.5% (12/32) | Completed bugs ÷ all completed work |
| Planning quality | 35.0% (21/60) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 0 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

Across included teams, the sprint did not fail; it traded predictability for responsiveness. 6/10 added items were closed, but that responsiveness came with 37.5% bug share and diluted finish predictability.

The miss pattern is concentrated: 16 partial-completion carryovers, 1 dependency-driven misses, and 10 planning-baseline items that never really started.

Most misses were not caused by poor readiness. 10 of the 34 planning-baseline carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 10 | 0 | 0 | 0 | 10 | 31.2% |
| Task | 5 | 2 | 0 | 0 | 7 | 21.9% |
| Bug | 10 | 2 | 0 | 0 | 12 | 37.5% |

# Planning baseline: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Planning-baseline items | 60 | Items present in the frozen planning snapshot |
| Planning-baseline done | 26 | Closed by sprint review |
| Planning-baseline carryover | 34 | All planned items still open, including Progress continuation |
| Finish-intent carryover | 22 | Planned-to-finish items that did not finish |
| Progress continuation | 10 | Progress-intent planned items still open as expected |
| Planning-baseline items marked Ready | 21 | Planning-quality input |
| Carryovers marked Ready | 10 | Ready did not guarantee closure |
| Carryovers not started | 10 | Execution focus gap |
| Carryovers started but unfinished | 13 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Intent | Status | Why it carried |
| --- | --- | --- | --- | --- |
| ADS-2590 — Bug — [Students] - Trebuie inlocuit articolul de la model import automat-date de completare si sa se deschida articolul din manualul de utilizare daca de da click pe linkul respectiv | Marian Andrei | Finish | In Progress | Partial completion |
| ADS-3527 — Bug — [Photos]- Primul videoclip dintr-un album video nu este redat corect în aplicația mobilă | stefan musat | Finish | Ready for testing | Partial completion |
| ADS-3896 — Bug — [Classes][Homework] -Problema la Trimiterea Temelor Corectate din aplicatia de mobil | Ivan Ioana | Finish | To Do | Not started |
| ADS-4007 — Bug — [BE][Subscriptions] - Comportament ciudat featureflags in cazul in care sunt dezactivate subscriptiile | Dragoș Ivan | Finish | To Do | Not started |
| ADS-4328 — Story — Headers in Mobile App | Dragoș Ivan | Stretch / Optional | To Do | Not started |
| ADS-5651 — Bug — [FE/BE/MOB] - Coprofesorul vede toți elevii clasei, deși are asociați doar unii | stefan musat | Finish | Done |  |
| ADS-5784 — Story — [FE/BE] Refactor pagina de permisiuni | Petronel Pavel | Progress | Merged |  |
| ADS-5808 — Bug — [MOB][Wellbeing] - Parintele nu poate vizualiza testele de autocunoastere pe mob | Antoci Razvan | Finish | To Do | Not started |
| ADS-6142 — Story — [Registre Matricole] -US1.1 Creare volume si asociere studenti incadrati | Cojan Paul-Catalin | Progress | In Progress | Partial completion |
| ADS-6159 — Story — Notification Center for Mobile | Dragoș Ivan | Progress | In Progress | Partial completion |
| ADS-6201 — Story — Log formatting - node.js, subscriptions | Dragoș Ivan | Stretch / Optional | To Do | Not started |
| ADS-6438 — Task — [BE][UNI] - Sincronizare ID-uri Ani universitari/scolari - UNI/preuni - master | andrei.alexandru | Finish | Ready to merge | Partial completion |
| ADS-6675 — Story — [Financiar] - Managementul penalitatilor | George Murgoci | Finish | Ready for testing | Partial completion |
| ADS-6694 — Story — [MOB] - Test parenting |  | Progress | In Progress | Partial completion |
| ADS-7474 — Task — [FE] - Optimizare viteză de încărcare pagini | Dragoș Ivan | Progress | To Do | Partial completion |
| ADS-7534 — Story — [FE/BE][Adeverinte absolvire] - Flow generare adeverinte | Ionut Ciolan | Finish | Ready for testing | Partial completion |
| ADS-7535 — Story — [FE] - Download Adeverinta de absolvire | Ionut Ciolan | Finish | Ready for testing | Dependency delay |
| ADS-7666 — Bug — accommodations-api: shared HTTP 500 burst on POST /api/v2/accommodations/dorms/list and related endpoints - 16 hits/20m | andrei.alexandru | Finish | To Do | Bug / rework pressure |
| ADS-7816 — Story — [SIIIR] - Import clase | Marian Andrei | Progress | In Progress | Partial completion |
| ADS-7849 — Story — Stergere date S3 | Cojan Paul-Catalin | Progress | In Progress | Bug / rework pressure |
| ADS-7906 — Story — [FE/BE] - Config -posibilitatea setarii mediei ca fiind confirmata | andrei.alexandru | Progress | To Do | Not started |
| ADS-7907 — Task — [BE] Refactoring SQL_CALC_FOUND_ROWS | Marian Andrei | Finish | In Progress | Partial completion |
| ADS-8023 — Story — [BE/FE][Adeverinte] Permisiuni &feature flags | Ionut Ciolan | Finish | To Do | Not started |
| ADS-8058 — Story — [BE/FE][UNI] - Generare serii si ani universitari bulk | andrei.alexandru | Finish | In Progress | Partial completion |
| ADS-8067 — Story — [Incadrare] Refactoring React & API | Andrei Dragan | Progress | In Progress | Late start / sequencing |
| ADS-8068 — Story — [MOB] - Încheiere situatie | Stefan Agrigoroaei | Finish | In Progress | Partial completion |
| ADS-8071 — Story — Teste automate flow Subscripții | Edgar Alexa | Progress | In Progress | Partial completion |
| ADS-8105 — Story — Impartirea pe module | Ivan Ioana | Finish | In Progress | Partial completion |
| ADS-8111 — Bug — [FE/BE] - In centralizator note nu apare numele unei discipline | andrei.alexandru | Finish | To Do | Bug / rework pressure |
| ADS-8147 — Bug — [BE] - Nu apar studentii pe sesiunea 2 | andrei.alexandru | Finish | To Do | Not started |
| ADS-8209 — Bug — [Prod][AWS][legacy-web] GET /api/v2/fisiere/view returns HTTP 500 when M_fisiere.php calls query() on null | Marian Andrei | Finish | To Do | Not started |
| ADS-8223 — Bug — [Prod][AWS][ingress] POST /api/v2/fisiere/upload maps backend 400 to HTTP 500 - 10/72h | Cojan Paul-Catalin | Finish | To Do | Not started |
| ADS-8237 — Bug — [MOB] - Problema la switch account de pe notif admission | Stefan Agrigoroaei | Finish | Testing |  |
| ADS-8273 — Story — [MOB][Elev][Parinte] - Detalii elev | Stefan Agrigoroaei | Finish | To Do | Partial completion |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 16 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 1 | Capacity protection or dependency timing created slip |
| Not started | 10 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 13 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| None |  |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did finish-intent items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show finish-intent carryovers split by dependency, partial completion, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Included teams in this org pulse: Mobile, Team 1, Team 2, University.

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 60 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 70 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 70 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 60 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 70 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 60 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 10 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 0 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 0 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Committed completion | 43.3% (26/60) | planned committed items marked Done ÷ all planned committed items | 26/60 | Open denominator JQL |
| Planning-baseline carryover | 56.7% (34/60) | planned baseline items not Done at review ÷ all planned baseline items | 34/60 | Open denominator JQL |
| Finish-intent carryover | 51.2% (22/43) | finish-intent planned items not Done at review ÷ all finish-intent planned items | 22/43 | Open denominator JQL |
| Finish predictability | 48.8% (21/43) | finish-intent committed items marked Done ÷ all finish-intent committed items | 21/43 | Open denominator JQL |
| Progress predictability | 66.7% (10/15) | progress-intent items that carried as intended ÷ all progress-intent committed items | 10/15 | Open denominator JQL |
| Added-during-sprint load | 14.3% (10/70) | visible items absent from planning and present in review ÷ all visible sprint items | 10/70 | Open denominator JQL |
| Added work closure | 6/10 | added visible items marked Done ÷ all added visible items | 6/10 | Open denominator JQL |
| Planning quality | 35.0% (21/60) | committed items marked Ready in planning snapshot ÷ all committed items | 21/60 | Open denominator JQL |
| Carryovers marked Ready | 29.4% (10/34) | carryovers that were marked Ready in planning snapshot ÷ all carryovers | 10/34 | Open denominator JQL |
| Reactive load | 37.5% (12/32) | completed bugs ÷ all completed work | 12/32 | Open denominator JQL |
| Workflow-truth mismatches | 0 | Done rows with non-final workflow status | 0/32 | Open denominator JQL |

Planning-baseline carryover includes both finish-intent misses and expected Progress continuations. Use Finish-intent carryover when you want only planned-to-finish items that did not finish.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.