Engineering Pulse — Org Adservio ADS Q3 W34 - 24-28 Aug
Aggregated sprint ADS Q3 W34 - 24-28 Aug • deduplicated roll-up across included teams
This org roll-up aggregates deduplicated frozen issue facts across 4 team snapshots. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.
Executive summary
Yellow. The sprint closed 21/71 visible items. The org roll-up absorbed noise reasonably well — 7/18 added items were closed — but predictability on committed work was only 30.4% (17/56), and bugs made up 52.4% of completed items. The main drag was execution system quality, not readiness: 19/39 carryovers had been marked Ready at planning time.
Top-line metrics
	Metric
	Value
	How to read it

	Committed completion
	30.4% (17/56)
	Planned items marked Done ÷ all planned committed items

	Committed carryover
	69.6% (39/56)
	Planned committed carryovers ÷ all planned committed items

	Finish predictability
	41.0% (16/39)
	Finish-intent planned items done ÷ all finish-intent planned items

	Progress predictability
	92.3% (12/13)
	Progress items that behaved as intended by carrying

	Added-during-sprint load
	25.4% (18/71)
	Added items ÷ all visible items

	Added work closure
	7/18
	All added items marked Done

	Reactive load (bug share)
	52.4% (11/21)
	Completed bugs ÷ all completed work

	Planning quality
	44.6% (25/56)
	Committed items marked Ready ÷ all committed items

	Workflow-truth mismatches
	0
	Items marked Done in review while workflow status remained non-final


Engineering readout
Across included teams, the sprint did not fail; it traded predictability for responsiveness. 7/18 added items were closed, but that responsiveness came with 52.4% bug share and diluted committed completion.
The miss pattern is concentrated: 17 partial-completion carryovers, 7 dependency-driven misses, and 9 committed items that never really started.
Most misses were not caused by poor readiness. 19 of the 39 carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.
Delivered work mix
	Type
	Planned
	Added
	Stretch
	Unclear
	Total done
	Done %

	Story
	2
	1
	0
	0
	3
	14.3%

	Task
	3
	1
	0
	0
	4
	19.0%

	Bug
	8
	3
	0
	0
	11
	52.4%


Committed work: plan vs execution
	Signal
	Value
	Why it matters

	Committed items
	56
	Explicit promise set

	Committed done
	17
	Closed as promised

	Committed carry over
	39
	Unfinished promise

	Committed items marked Ready
	25
	Planning-quality input

	Carryovers marked Ready
	19
	Ready did not guarantee finish

	Carryovers not started
	9
	Execution focus gap

	Carryovers started but unfinished
	20
	Work moved, but did not close


Carryover pattern
	Jira item
	Owner
	Status
	Why it carried

	ADS-2590 — Bug — [Students] - Trebuie inlocuit articolul de la model import automat-date de completare si sa se deschida articolul din manualul de utilizare daca de da click pe linkul respectiv
	Marian Andrei
	To Do
	Not started

	ADS-4419 — Story — [Elev][Părinte] - Redesign - Noutati & Activitati
	stefan musat
	In Progress
	Partial completion

	ADS-5654 — Story — [UPA,UPG, Asachi] Taxe școlarizare
	George Murgoci
	In Progress
	Partial completion

	ADS-6438 — Task — [BE][UNI] - Sincronizare ID-uri Ani universitari/scolari - UNI/preuni - master
	andrei.alexandru
	Ready to merge
	Partial completion

	ADS-7251 — Story — Mutarea subscriptii de pe recurenta An scolar pe recurenta an calendaristic
	Edgar Alexa
	Ready to merge
	Dependency delay

	ADS-7279 — Task — [Billing] - Implementare Stripe + Apple pay + Google pay
	Edgar Alexa
	In Progress
	Late start / sequencing

	ADS-7354 — Story — [Abonamente] - Gestionare recurență pachete anuale
	Edgar Alexa
	To Do
	Not started

	ADS-7816 — Story — [SIIIR] - Import clase
	Marian Andrei
	In Progress
	Partial completion

	ADS-7818 — Story — [SIIIR] - Import elevi
	Vlad Lihaceanu
	In Progress
	Partial completion

	ADS-7849 — Story — Stergere date S3
	Cojan Paul-Catalin
	To Do
	Priority Change

	ADS-7852 — Task — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata
	Andrei Dragan
	Ready to merge
	Dependency delay

	ADS-8067 — Story — [Incadrare] Refactoring React & API
	Andrei Dragan
	Testing
	Under Estimated

	ADS-8159 — Story — [Burse] - US2 - Configurare bugete, Panou
	Iuliana Gugeanu
	In Progress
	Dependency delay

	ADS-8160 — Story — [Burse] - US3 - Configurare burse
	Iuliana Gugeanu
	In Progress
	Dependency delay

	ADS-8161 — Story — [Burse] - US4 - Alocare burse
	Ionut Ciolan
	In Progress
	Dependency delay

	ADS-8162 — Story — [Burse] - US5 - Plati
	Ionut Ciolan
	In Progress
	Partial completion

	ADS-8166 — Story — [Burse] - US7 - View Student/actiuni student
	Ionut Ciolan
	In Progress
	Dependency delay

	ADS-8176 — Story — [State de functii] - Functionalitati si flux
	andrei.alexandru
	Testing
	Partial completion

	ADS-8179 — Story — [Registre Matricole] - US2 Incarcare atribute studenti pentru popularea registrelor matricole
	Virlan Francisc-Gabriel
	In Progress
	Under Estimated

	ADS-8209 — Bug — [Prod][AWS][legacy-web] GET /api/v2/fisiere/view returns HTTP 500 when M_fisiere.php calls query() on null
	Marian Andrei
	To Do
	Not started

	ADS-8223 — Bug — [Prod][AWS][ingress] POST /api/v2/fisiere/upload maps backend 400 to HTTP 500 - 10/72h
	Cojan Paul-Catalin
	To Do
	Not started

	ADS-8297 — Story — [Elev][Parinte] - Redesign - Materii
	stefan musat
	In Progress
	Partial completion

	ADS-8298 — Story — [Elev][Parinte] - Redesign - Gradinite
	stefan musat
	To Do
	Not started

	ADS-8326 — Bug — [BE-PHP][Cazari] - La decazare soldurie apar incorect fata de fisa studentilor
	Ionut Ciolan
	Testing
	Partial completion

	ADS-8339 — Story — Tools
	Alex Murarescu
	In Progress
	Partial completion

	ADS-8366 — Bug — [Prod][AWS][legacy-web] Tenantless API requests hit null school DB handle across timetable, grades, and portfolio
	Ionut Ciolan
	To Do
	Not started

	ADS-8378 — Story — [Elev][Parinte] Materie detalii
	Stefan Agrigoroaei
	In Progress
	Partial completion

	ADS-8383 — Story — [BE] - Local Cache Billing
	George Murgoci
	In Progress
	Dependency delay

	ADS-8404 — Improvement — [Elev][Parinte] - Redesign - Rapoarte
	Cojan Paul-Catalin
	To Do
	Not started

	ADS-8462 — Task — [Localizare] Elemente netraduse în interfața English, grupate per rol
	
	In Progress
	Partial completion

	ADS-8501 — Task — S3: Ștergere variabile OSS vechi și verificat că totul merge bine
	Cojan Paul-Catalin
	To Do
	Priority Change

	ADS-8506 — Bug — [Prod][AWS][legacy-web] Student export binds an empty DATE value and silently returns no rows - 10 errors/72h
	
	To Do
	Not started

	ADS-8510 — Bug — [FE] diferenta numar elevi in raportul "promovabilitae elevi"
	Andrei Dragan
	To Do
	Priority Change

	ADS-8533 — Task — Logout methods helper
	Stefan Agrigoroaei
	Ready for testing
	Partial completion

	ADS-8534 — Bug — Asachi - Nu afiseaza an de studiu pentru studentii din anul 1 (2025-2026)din situatie scolara
	andrei.alexandru
	Ready to merge
	Partial completion

	ADS-8535 — Bug — [Prod][AWS][University] Add discipline sends string for localized disciplineName - 12 HTTP 400s/72h
	andrei.alexandru
	To Do
	Not started

	ADS-8541 — Bug — Class management day diary
	Stefan Agrigoroaei
	Ready for testing
	Partial completion

	ADS-8546 — Task — Prod][uni-api] Guardrail student search export
	andrei.alexandru
	Ready for testing
	Partial completion

	ADS-8558 — Story — [Elev][Părinte] - Materii - Observații si conduita
	Stefan Agrigoroaei
	In Progress
	Partial completion


Miss pattern summary
	Pattern
	Count
	What it suggests

	Partial completion
	17
	Breakdown / sizing / stage-gating was not tight enough

	Dependency delay
	7
	Capacity protection or dependency timing created slip

	Not started
	9
	A committed item remained outside execution focus

	In Progress / Code Review carryovers
	20
	Most misses were moving, but not closing


Workflow-truth mismatches
Items marked Done in the sprint-review field while Jira workflow status was still non-final.
	Jira item
	Status
	Intent

	None
	
	


Executive follow-up questions
	Question
	Why this matters
	What evidence to ask for

	Why did committed items carry over despite planning readiness?
	This tests execution quality rather than just scope quality.
	Show carryovers split by progress continuation, dependency, and not-started.

	Are Progress items being managed intentionally?
	Progress items are allowed to continue, but the continuation should be visible and controlled.
	Show the original slice and the specific landing expectation for each item.

	Is added work a healthy responsiveness level or chronic interruption?
	High responsiveness can hide systemic instability and diluted predictability.
	Show which added items were urgent/reactive versus discretionary scope change.

	Can we trust Done in review when workflow is still non-final?
	Workflow-truth gaps reduce trust and make completion easy to game.
	Show the exact mismatches and the completion rule to enforce next sprint.


Included teams in this org pulse: Mobile, Team 1, Team 2, University.
Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.
Snapshot and fact-base list links
	Snapshot
	Issue count
	Link

	Planning snapshot raw list
	62
	62 issues in the planning snapshot

	Sprint review / outcome snapshot raw list
	79
	79 issues in the Friday review snapshot

	Normalized sprint fact base
	71
	71 issues used for metrics and drill-down


Planning and outcome are separate frozen moments.
Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.
Evidence artifacts
	Artifact
	Link

	Issue audit register
	Open issue-level audit CSV

	Metric lineage
	Open metric lineage CSV

	JQL traceability register
	Open JQL traceability CSV

	Sprint metrics JSON
	Open sprint metrics JSON


These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.




