# Engineering Pulse — Org Adservio ADS Q3 W37 - 14-18 Sep

Aggregated sprint ADS Q3 W37 - 14-18 Sep • deduplicated roll-up across included teams

This org roll-up aggregates deduplicated frozen issue facts across 4 team snapshots. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 34/79 visible items. The org roll-up absorbed noise reasonably well — 26/35 added items were closed — but predictability on committed work was only 30.9% (17/55), and bugs made up 58.8% of completed items. The main drag was execution system quality, not readiness: 16/38 carryovers had been marked Ready at planning time.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 30.9% (17/55) | Planned items marked Done ÷ all planned committed items |
| Committed carryover | 69.1% (38/55) | Planned committed carryovers ÷ all planned committed items |
| Finish predictability | 39.0% (16/41) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 91.7% (11/12) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 44.3% (35/79) | Added items ÷ all visible items |
| Added work closure | 26/35 | All added items marked Done |
| Reactive load (bug share) | 58.8% (20/34) | Completed bugs ÷ all completed work |
| Planning quality | 43.6% (24/55) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 0 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

Across included teams, the sprint did not fail; it traded predictability for responsiveness. 26/35 added items were closed, but that responsiveness came with 58.8% bug share and diluted committed completion.

The miss pattern is concentrated: 26 partial-completion carryovers, 1 dependency-driven misses, and 11 committed items that never really started.

Most misses were not caused by poor readiness. 16 of the 38 carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 1 | 1 | 0 | 0 | 2 | 5.9% |
| Task | 4 | 6 | 0 | 0 | 10 | 29.4% |
| Bug | 2 | 18 | 0 | 0 | 20 | 58.8% |

# Committed work: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Committed items | 55 | Explicit promise set |
| Committed done | 17 | Closed as promised |
| Committed carry over | 38 | Unfinished promise |
| Committed items marked Ready | 24 | Planning-quality input |
| Carryovers marked Ready | 16 | Ready did not guarantee finish |
| Carryovers not started | 11 | Execution focus gap |
| Carryovers started but unfinished | 24 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Status | Why it carried |
| --- | --- | --- | --- |
| ADS-2590 — Bug — [Students] - Trebuie inlocuit articolul de la model import automat-date de completare si sa se deschida articolul din manualul de utilizare daca de da click pe linkul respectiv | Marian Andrei | To Do | Not started |
| ADS-5654 — Story — [UPA,UPG, Asachi] Taxe școlarizare | George Murgoci | Ready for testing | Dependency delay |
| ADS-6159 — Story — Notification Center for Mobile | Dragoș Ivan | In Progress | Partial completion |
| ADS-7272 — Bug — M_user_api.php / M_user.php: subscriptions features lookup fails hard when subscriptions-api-svc is slow or down - 20 errors/48h | Cojan Paul-Catalin | To Do | Not started |
| ADS-7279 — Task — [Billing] - Implementare Stripe + Apple pay + Google pay | Edgar Alexa | Testing | Partial completion |
| ADS-7354 — Story — [Abonamente] - Gestionare recurență pachete anuale | Edgar Alexa | In Progress | Partial completion |
| ADS-7421 — Task — [BE] Cleanup Noutati | Cojan Paul-Catalin | To Do | Not started |
| ADS-7559 — Story — [UPG] - Adeverinte de student | Ionut Ciolan | Code Review | Partial completion |
| ADS-7803 — Task — [FE/BE/MOB/UNI] - Titulatura | Ivan Ioana | In Progress | Partial completion |
| ADS-7817 — Story — [SIIIR] - Import cadre didactice | Marian Andrei | In Progress | Partial completion |
| ADS-7852 — Task — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata | Andrei Dragan | Ready for testing | Partial completion |
| ADS-8162 — Story — [Burse] - US5 - Plati | Iuliana Gugeanu | In Progress | Partial completion |
| ADS-8164 — Story — [Burse] - US6 - Rapoarte | Magda Gradinaru | To Do | Not started |
| ADS-8177 — Story — [State de functii] - Rapoarte 20 sept | stefan.achim | Code Review | Partial completion |
| ADS-8179 — Story — [Registre Matricole] - US2 Incarcare atribute studenti pentru popularea registrelor matricole | Virlan Francisc-Gabriel | Code Review | Partial completion |
| ADS-8259 — Story — [Abonamente][RC] - Rambursare clienti | Dragoș Ivan | To Do | Not started |
| ADS-8343 — Story — Integration | Alex Murarescu | Code Review | Partial completion |
| ADS-8404 — Improvement — [Elev][Parinte] - Redesign - Rapoarte | Cojan Paul-Catalin | Code Review | Partial completion |
| ADS-8501 — Task — S3: Ștergere variabile OSS vechi și verificat că totul merge bine | Cojan Paul-Catalin | In Progress | Partial completion |
| ADS-8569 — Task — [BE] transfer date comasare scoli | Ionut Ciolan | Code Review | Partial completion |
| ADS-8570 — Task — [FE] inactivare conturi in urma comasarii | Ionut Ciolan | Code Review | Partial completion |
| ADS-8580 — Task — Recuperare date sterse elev ID 775987 | Daniel Onisoru | In Progress | Partial completion |
| ADS-8598 — Task — [BE] aflare cine l-a sters pe elev ID 2372338 | Daniel Onisoru | In Progress | Partial completion |
| ADS-8599 — Story — [Asachi][BE/FE] Ajustari echivalari note | andrei.alexandru | In Progress | Partial completion |
| ADS-8624 — Bug — [2FA] Dezactivarea autentificării prin cod e-mail eșuează cu error.e_99 | Cojan Paul-Catalin | Code Review | Partial completion |
| ADS-8671 — Story — [AI - MCP] Teacher summaries | Alex Murarescu | In Progress | Partial completion |
| ADS-8679 — Story — [BE/FE] Refactor student | Daniel Nechita | In Progress | Partial completion |
| ADS-8713 — Bug — [FE] cod de inregistrare invalid la accesarea linkului din email | Marian Andrei | To Do | Not started |
| ADS-8721 — Bug — [FE] Butonul de semnare a condicii de prezenta nu e afisat pentru rolul de contabil | Petronel Pavel | To Do | Not started |
| ADS-8723 — Improvement — Posibilitate generare orar atunci cand exista 2 profesori principali | Ionut Ciolan | Testing | Partial completion |
| ADS-8733 — Bug — [Prod][Billing] Custom Invoice workload exposes premature PostgreSQL client release and slow pending-charge aggregation | Edgar Alexa | To Do | Not started |
| ADS-8751 — Bug — [FE] Import note bulk are success dar nu importa notele | stefan.achim | In Progress | Partial completion |
| ADS-8756 — Bug — [Asachi][BE] Stituatii din RC | Andreea Moldovanu | To Do | Not started |
| ADS-8758 — Task — de mutat elevii de clasa aVIII de pe scoala ID 6179 pe ID 6254 | Ionut Ciolan | Code Review | Partial completion |
| ADS-8760 — Task — [FE]: Schimbari pe Suprascrieri si transferuri | Ivan Ioana | To Do | Not started |
| ADS-8761 — Story — Notification center | stefan musat | To Do | Partial completion |
| ADS-8763 — Task — [Asachi][BE] Import studenti pentru anul universitar 2026-2027 | andrei.alexandru | In Progress | Partial completion |
| ADS-8766 — Bug — [Prod][AWS][legacy-web] Bulk class creation returns 500 when generated class name exceeds storage limit - 35 failures/72h | Petronel Pavel | To Do | Not started |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 26 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 1 | Capacity protection or dependency timing created slip |
| Not started | 11 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 24 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| None |  |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did committed items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show carryovers split by progress continuation, dependency, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Included teams in this org pulse: Mobile, Team 1, Team 2, University.

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 61 | 61 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 85 | 85 issues in the Friday review snapshot |
| Normalized sprint fact base | 79 | 79 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.