# Engineering Pulse — Team 1 ADS Q2 W22 - 01-05 Iunie

Planned sprint ADS Q2 W22 - 01-05 Iunie • planning snapshot + end-of-sprint outcome snapshot

This version uses the planning snapshot as the promise set and the outcome snapshot as the result set. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 31/64 visible items. The team absorbed noise well — 11/15 added items were closed — but finish predictability was only 42.2% (19/45), and bugs made up 54.8% of completed items. Planning-baseline carryover includes 26 finish misses and 3 expected progress continuations.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 40.8% (20/49) | Planned items marked Done ÷ all planned committed items |
| Planning-baseline carryover | 59.2% (29/49) | All planned items not Done, including expected Progress continuations |
| Finish-intent carryover | 57.8% (26/45) | Finish-intent planned items not Done ÷ all finish-intent planned items |
| Finish predictability | 42.2% (19/45) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 100.0% (3/3) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 23.4% (15/64) | Outcome-only items ÷ all visible items |
| Added work closure | 11/15 | All added items marked Done |
| Reactive load (bug share) | 54.8% (17/31) | Completed bugs ÷ all completed work |
| Planning quality | 51.0% (25/49) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 3 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

The sprint did not fail; it traded predictability for responsiveness. 11/15 added items were closed, but that responsiveness came with 54.8% bug share and diluted finish predictability.

The miss pattern is concentrated: 5 partial-completion carryovers, 1 dependency-driven misses, and 20 planning-baseline items that never really started.

Most misses were not caused by poor readiness. 10 of the 29 planning-baseline carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 1 | 1 | 0 | 0 | 2 | 6.5% |
| Task | 3 | 2 | 1 | 0 | 6 | 19.4% |
| Bug | 10 | 7 | 0 | 0 | 17 | 54.8% |

# Planning baseline: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Planning-baseline items | 49 | Items present in the frozen planning snapshot |
| Planning-baseline done | 20 | Closed by sprint review |
| Planning-baseline carryover | 29 | All planned items still open, including Progress continuation |
| Finish-intent carryover | 26 | Planned-to-finish items that did not finish |
| Progress continuation | 3 | Progress-intent planned items still open as expected |
| Planning-baseline items marked Ready | 25 | Planning-quality input |
| Carryovers marked Ready | 10 | Ready did not guarantee closure |
| Carryovers not started | 20 | Execution focus gap |
| Carryovers started but unfinished | 3 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Intent | Status | Why it carried |
| --- | --- | --- | --- | --- |
| ADS-2564 — Story — [School managment/Teachers] - Modules to be tested until the end of the school year | Cosmin Olaru | Progress | To Do | Dependency delay |
| ADS-406 — Bug — [Files] Missing description in ‘’Istoric’ when sharing documents | Antoci Razvan | Finish | To Do | Not started |
| ADS-4341 — Bug — [Condica de prezenta] - Nu apare butonul ,, semneaza condica pentru toata ziua | Vlad Lihaceanu | Finish | To Do | Not started |
| ADS-4439 — Bug — [Teste si chestionare] - Numarul de destinatari care se afiseaza nu corespunde cu numarul real de destinatari | Marian Andrei | Finish | To Do | Not started |
| ADS-4857 — Bug — [Mesagerie] - Restricționarea mesajelor de grup, conform configurărilor setate | Petronel Pavel | Progress | In Progress | Partial completion |
| ADS-5722 — Bug — [BE/FE] Modal adauga note | Andrei Dragan | Finish | To Do |  |
| ADS-5808 — Bug — [FE][Wellbeing] - Parintele nu poate vizualiza testele de autocunoastere pe mob | Antoci Razvan | Finish | To Do | Not started |
| ADS-5919 — Bug — [Fotografii] - Distribuirea nu este afișată exclusiv pe clasele sau grupele configurate în modulul Clase | Petronel Pavel | Finish | To Do | Not started |
| ADS-6495 — Story — Service Internal API | Ionut Ciolan | Finish | Done | Partial completion |
| ADS-6499 — Story — Implementat CRUD Etnii in Laravel | Ionut Ciolan | Finish | Done | Not started |
| ADS-6501 — Story — Input validation errors | Ionut Ciolan | Finish | Done | Partial completion |
| ADS-6545 — Story — Implementare v1 layer comunicare native-web *post message bridge | Ivan Ioana | Finish | To Do | Not started |
| ADS-6562 — Story — Remove any mentions of Laravel in production mode | Ionut Ciolan | Finish | Done | Partial completion |
| ADS-6698 — Bug — [FE/BE] Restrictie vizualizare fise scolare | Marian Andrei | Finish | To Do | Not started |
| ADS-6712 — Task — [Note/absențe] - Recuperare informații | Marian Andrei | Finish | To Do | Not started |
| ADS-7009 — Task — Dezactivare actiuni noteaza/absenta (si bulk) daca media anuala si/sau media semestriala este incheiata | Ivan Ioana | Finish | To Do | Not started |
| ADS-7330 — Task — [BE] - Valoare implicita incorecta pentru tipul de calcul al mediei la adaugarea unei materii noi | Andrei Dragan | Finish | To Do |  |
| ADS-7388 — Bug — docgen2-api: gradebook view/download endpoints return HTTP 500 - 15 hits/Friday | Ivan Ioana | Finish |  | Missing from outcome snapshot |
| ADS-7389 — Bug — AdservioAPI.php: svcAuth self-call failures turn web API endpoints into HTTP 500 - 20 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7390 — Bug — rooms-api: room search endpoint returns HTTP 500 - 3 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7448 — Bug — [BE] Grades.php: deleting a grade can deadlock on cat_note and return HTTP 500 - 8 hits/24h | Andrei Dragan | Finish | To Do | Not started |
| ADS-7451 — Bug — [BE] - Condica - Activitati duplicate | Ionut Ciolan | Finish | In Progress | Partial completion |
| ADS-7460 — Bug — Absences time interval export_xls returns HTTP 500 for inverted date range (6 errors/24h) | Marian Andrei | Finish | To Do | Not started |
| ADS-7484 — Bug — Session.php: session_start() fails reading session data during teacher class-book requests - 26 errors/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7575 — Bug — M_export.php / Export.php: student export references missing second-semester average column and returns HTTP 500 on /ro/secretary/export/elevi - 16 hits/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-760 — Bug — [Classes][LCY][WEB][FE/MOB] - Classroom - Unable to delete a document attached to a message | Antoci Razvan | Finish | To Do | Not started |
| ADS-7618 — Bug — [BE/FE] Chestionare - Descarcarea raspunsurilor individuale descarca mereu primul parinte din lista, iar status completare este gresit | Marian Andrei | Finish | In Progress | Not started |
| ADS-7654 — Bug — Grades.php / AverageCalculator: POST /api/v2/grades accepts grade but skips average recomputation - 2 errors/24h | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7724 — Task — [FR] Setare calcul medie - Standard Romania | Andrei Dragan | Progress | To Do | Not started |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 5 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 1 | Capacity protection or dependency timing created slip |
| Not started | 20 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 3 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| ADS-6360 — [Catalog PDF] - Număr indicatori incorect – Semestre | Ready for testing | Finish |
| ADS-7786 — [Docgen] -Catalogul pe semestre nu afiseaza datele legate de situatia scolara | Code Review |  |
| ADS-7795 — [FE] - Examenul de specialitate nu e trecut complet cand e cu virgula in catalogul PDF | Code Review |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did finish-intent items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show finish-intent carryovers split by dependency, partial completion, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 52 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 66 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 64 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 49 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 63 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 48 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 15 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 1 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 3 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Committed completion | 40.8% (20/49) | planned committed items marked Done ÷ all planned committed items | 20/49 | Open denominator JQL |
| Planning-baseline carryover | 59.2% (29/49) | planned baseline items not Done at review ÷ all planned baseline items | 29/49 | Open denominator JQL |
| Finish-intent carryover | 57.8% (26/45) | finish-intent planned items not Done at review ÷ all finish-intent planned items | 26/45 | Open denominator JQL |
| Finish predictability | 42.2% (19/45) | finish-intent committed items marked Done ÷ all finish-intent committed items | 19/45 | Open denominator JQL |
| Progress predictability | 100.0% (3/3) | progress-intent items that carried as intended ÷ all progress-intent committed items | 3/3 | Open denominator JQL |
| Added-during-sprint load | 23.4% (15/64) | visible items absent from planning and present in review ÷ all visible sprint items | 15/64 | Open denominator JQL |
| Added work closure | 11/15 | added visible items marked Done ÷ all added visible items | 11/15 | Open denominator JQL |
| Planning quality | 51.0% (25/49) | committed items marked Ready in planning snapshot ÷ all committed items | 25/49 | Open denominator JQL |
| Carryovers marked Ready | 34.5% (10/29) | carryovers that were marked Ready in planning snapshot ÷ all carryovers | 10/29 | Open denominator JQL |
| Reactive load | 54.8% (17/31) | completed bugs ÷ all completed work | 17/31 | Open denominator JQL |
| Workflow-truth mismatches | 3 | Done rows with non-final workflow status | 3/31 | Open denominator JQL |

Planning-baseline carryover includes both finish-intent misses and expected Progress continuations. Use Finish-intent carryover when you want only planned-to-finish items that did not finish.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.