# Engineering Pulse — Team 1 ADS Q2 W24 - 15-19 Jun

Planned sprint ADS Q2 W24 - 15-19 Jun • planning snapshot + end-of-sprint outcome snapshot

This version uses the planning snapshot as the promise set and the outcome snapshot as the result set. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 27/54 visible items. The team absorbed noise well — 17/21 added items were closed — but finish predictability was only 30.3% (10/33), and bugs made up 48.1% of completed items. Planning-baseline carryover includes 23 finish misses and 0 expected progress continuations.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 30.3% (10/33) | Planned items marked Done ÷ all planned committed items |
| Planning-baseline carryover | 69.7% (23/33) | All planned items not Done, including expected Progress continuations |
| Finish-intent carryover | 69.7% (23/33) | Finish-intent planned items not Done ÷ all finish-intent planned items |
| Finish predictability | 30.3% (10/33) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 0.0% (0/0) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 38.9% (21/54) | Outcome-only items ÷ all visible items |
| Added work closure | 17/21 | All added items marked Done |
| Reactive load (bug share) | 48.1% (13/27) | Completed bugs ÷ all completed work |
| Planning quality | 39.4% (13/33) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 1 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

The sprint did not fail; it traded predictability for responsiveness. 17/21 added items were closed, but that responsiveness came with 48.1% bug share and diluted finish predictability.

The miss pattern is concentrated: 4 partial-completion carryovers, 0 dependency-driven misses, and 18 planning-baseline items that never really started.

Most misses were not caused by poor readiness. 6 of the 23 planning-baseline carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 0 | 0 | 0 | 0 | 0 | 0.0% |
| Task | 3 | 5 | 0 | 0 | 8 | 29.6% |
| Bug | 5 | 8 | 0 | 0 | 13 | 48.1% |

# Planning baseline: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Planning-baseline items | 33 | Items present in the frozen planning snapshot |
| Planning-baseline done | 10 | Closed by sprint review |
| Planning-baseline carryover | 23 | All planned items still open, including Progress continuation |
| Finish-intent carryover | 23 | Planned-to-finish items that did not finish |
| Progress continuation | 0 | Progress-intent planned items still open as expected |
| Planning-baseline items marked Ready | 13 | Planning-quality input |
| Carryovers marked Ready | 6 | Ready did not guarantee closure |
| Carryovers not started | 18 | Execution focus gap |
| Carryovers started but unfinished | 4 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Intent | Status | Why it carried |
| --- | --- | --- | --- | --- |
| ADS-406 — Bug — [Files] Missing description in ‘’Istoric’ when sharing documents | Petronel Pavel | Finish | To Do | Not started |
| ADS-4341 — Bug — [Condica de prezenta] - Nu apare butonul ,, semneaza condica pentru toata ziua | Luiza Horlescu | Finish | To Do | Not started |
| ADS-4439 — Bug — [Teste si chestionare] - Numarul de destinatari care se afiseaza nu corespunde cu numarul real de destinatari | Marian Andrei | Finish | To Do | Not started |
| ADS-4763 — Story — [Statistici] - Exporturi Excel | Marian Andrei | Finish | To Do | Not started |
| ADS-4857 — Bug — [Mesagerie] - Restricționarea mesajelor de grup, conform configurărilor setate | Petronel Pavel | Finish | To Do | Not started |
| ADS-5722 — Bug — [BE/FE] Modal adauga note | Andrei Dragan | Finish | To Do | Not started |
| ADS-5808 — Bug — [FE][Wellbeing] - Parintele nu poate vizualiza testele de autocunoastere pe mob | Antoci Razvan | Finish |  | Missing from outcome snapshot |
| ADS-5919 — Bug — [Fotografii] - Distribuirea nu este afișată exclusiv pe clasele sau grupele configurate în modulul Clase | Petronel Pavel | Finish | To Do | Not started |
| ADS-6545 — Story — Implementare v1 layer comunicare native-web *post message bridge | Ivan Ioana | Finish | To Do | Not started |
| ADS-6698 — Bug — [FE/BE] Restrictie vizualizare fise scolare | Marian Andrei | Finish | To Do | Not started |
| ADS-6712 — Task — [Note/absențe] - Recuperare informații | Marian Andrei | Finish | To Do | Not started |
| ADS-6781 — Story — [Documente] Sortare materii foaia matricola | Andrei Dragan | Finish | In Progress | Partial completion |
| ADS-7389 — Bug — AdservioAPI.php: svcAuth self-call failures turn web API endpoints into HTTP 500 - 20 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7390 — Bug — rooms-api: room search endpoint returns HTTP 500 - 3 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7448 — Bug — [BE] Grades.php: deleting a grade can deadlock on cat_note and return HTTP 500 - 8 hits/24h | Andrei Dragan | Finish | To Do | Not started |
| ADS-7484 — Bug — Session.php: session_start() fails reading session data during teacher class-book requests - 26 errors/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7575 — Bug — M_export.php / Export.php: student export references missing second-semester average column and returns HTTP 500 on /ro/secretary/export/elevi - 16 hits/24h | Marian Andrei | Finish | In Progress | Partial completion |
| ADS-7653 — Bug — Clase_profesori.php / M_cmc.php: teacher-class assignment insert fails FK constraint in cat_cadre2materii2clase - 2 errors/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7654 — Bug — Grades.php / AverageCalculator: POST /api/v2/grades accepts grade but skips average recomputation - 2 errors/24h | Andrei Dragan | Finish | To Do | Not started |
| ADS-7732 — Bug — TUIASI M_fisiere.php: file list query expects fsScimCeacSyncFsID missing from on-prem schema and breaks document listings - 12 errors/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7803 — Task — [SPIKE][FE] - Titulatura | Ivan Ioana | Finish | To Do | Not started |
| ADS-7852 — Task — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata | Andrei Dragan | Finish | In Progress | Partial completion |
| ADS-7897 — Task — [BE] Analizat Slow queries | Marian Andrei | Finish | In Progress | Partial completion |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 4 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 0 | Capacity protection or dependency timing created slip |
| Not started | 18 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 4 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| ADS-7963 — [FE] - Notare cu calificative, insa in catalog PDF apare mediile in note | Code Review |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did finish-intent items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show finish-intent carryovers split by dependency, partial completion, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 35 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 56 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 54 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 33 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 53 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 32 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 21 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 1 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 3 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Committed completion | 30.3% (10/33) | planned committed items marked Done ÷ all planned committed items | 10/33 | Open denominator JQL |
| Planning-baseline carryover | 69.7% (23/33) | planned baseline items not Done at review ÷ all planned baseline items | 23/33 | Open denominator JQL |
| Finish-intent carryover | 69.7% (23/33) | finish-intent planned items not Done at review ÷ all finish-intent planned items | 23/33 | Open denominator JQL |
| Finish predictability | 30.3% (10/33) | finish-intent committed items marked Done ÷ all finish-intent committed items | 10/33 | Open denominator JQL |
| Progress predictability | 0.0% (0/0) | progress-intent items that carried as intended ÷ all progress-intent committed items | 0/0 | Open denominator JQL |
| Added-during-sprint load | 38.9% (21/54) | visible items absent from planning and present in review ÷ all visible sprint items | 21/54 | Open denominator JQL |
| Added work closure | 17/21 | added visible items marked Done ÷ all added visible items | 17/21 | Open denominator JQL |
| Planning quality | 39.4% (13/33) | committed items marked Ready in planning snapshot ÷ all committed items | 13/33 | Open denominator JQL |
| Carryovers marked Ready | 26.1% (6/23) | carryovers that were marked Ready in planning snapshot ÷ all carryovers | 6/23 | Open denominator JQL |
| Reactive load | 48.1% (13/27) | completed bugs ÷ all completed work | 13/27 | Open denominator JQL |
| Workflow-truth mismatches | 1 | Done rows with non-final workflow status | 1/27 | Open denominator JQL |

Planning-baseline carryover includes both finish-intent misses and expected Progress continuations. Use Finish-intent carryover when you want only planned-to-finish items that did not finish.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.