# Engineering Pulse — Team 1 ADS Q2 W26 - 29 Jun-03 Jul

Planned sprint ADS Q2 W26 - 29 Jun-03 Jul • planning snapshot + end-of-sprint outcome snapshot

This version uses the planning snapshot as the promise set and the outcome snapshot as the result set. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 27/43 visible items. The team absorbed noise well — 22/34 added items were closed — but predictability on committed work was only 61.1% (22/36), and bugs made up 55.6% of completed items. The main drag was execution system quality, not readiness: 4/14 carryovers had been marked Ready at planning time.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 61.1% (22/36) | Planned items marked Done ÷ all planned committed items |
| Committed carryover | 38.9% (14/36) | Planned committed carryovers ÷ all planned committed items |
| Finish predictability | 63.0% (17/27) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 44.4% (4/9) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 79.1% (34/43) | Added items ÷ all visible items |
| Added work closure | 22/34 | All added items marked Done |
| Reactive load (bug share) | 55.6% (15/27) | Completed bugs ÷ all completed work |
| Planning quality | 33.3% (12/36) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 7 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

The sprint did not fail; it traded predictability for responsiveness. 22/34 added items were closed, but that responsiveness came with 55.6% bug share and diluted committed completion.

The miss pattern is concentrated: 1 partial-completion carryovers, 1 dependency-driven misses, and 10 committed items that never really started.

Most misses were not caused by poor readiness. 4 of the 14 carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 2 | 1 | 0 | 0 | 3 | 11.1% |
| Task | 3 | 1 | 0 | 0 | 4 | 14.8% |
| Bug | 0 | 15 | 0 | 0 | 15 | 55.6% |

# Committed work: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Committed items | 36 | Explicit promise set |
| Committed done | 22 | Closed as promised |
| Committed carry over | 14 | Unfinished promise |
| Committed items marked Ready | 12 | Planning-quality input |
| Carryovers marked Ready | 4 | Ready did not guarantee finish |
| Carryovers not started | 10 | Execution focus gap |
| Carryovers started but unfinished | 2 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Status | Why it carried |
| --- | --- | --- | --- |
| ADS-4439 — Bug — [Teste si chestionare] - Numarul de destinatari care se afiseaza nu corespunde cu numarul real de destinatari | Marian Andrei | To Do | Not started |
| ADS-5784 — Story — [FE/BE] Refactor pagina de permisiuni | Petronel Pavel | In Progress | Late start / sequencing |
| ADS-6698 — Bug — [FE/BE] Restrictie vizualizare fise scolare | Marian Andrei | To Do | Not started |
| ADS-6712 — Task — [Note/absențe] - Recuperare informații | Marian Andrei | To Do | Not started |
| ADS-7305 — Task — [REQ] - Remote Session Termination for Users | Andrei Dragan | To Do | Not started |
| ADS-7389 — Bug — AdservioAPI.php: svcAuth self-call failures turn web API endpoints into HTTP 500 - 20 hits/Friday | Ionut Ciolan | To Do | Not started |
| ADS-7390 — Bug — rooms-api: room search endpoint returns HTTP 500 - 3 hits/Friday | Ionut Ciolan | To Do | Not started |
| ADS-7484 — Bug — Session.php: session_start() fails reading session data during teacher class-book requests - 26 errors/24h | Marian Andrei | To Do | Not started |
| ADS-7653 — Bug — Clase_profesori.php / M_cmc.php: teacher-class assignment insert fails FK constraint in cat_cadre2materii2clase - 2 errors/24h | Marian Andrei | To Do | Not started |
| ADS-7852 — Task — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata | Cosmin Olaru | Testing | Partial completion |
| ADS-7908 — Bug — [Prod][AWS][legacy-web] Auth recaptcha helper dereferences null verification response | Daniel Onisoru | To Do | Not started |
| ADS-8004 — Improvement — [FE] - Elevii transferati apar in statistici ca "medii neconfirmate" | Marian Andrei | To Do |  |
| ADS-8061 — Bug — [Prod][AWS][legacy-web] School-transfer edit recalculates status for NULL student ID - 64 errors/72h | Andrei Dragan | To Do | Not started |
| ADS-8062 — Bug — [Prod][AWS][legacy-web] Certificate template fetch returns 500 when forms schema lookup gets 403 - 26 errors/72h | Petronel Pavel | To Do | Dependency delay |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 1 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 1 | Capacity protection or dependency timing created slip |
| Not started | 10 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 2 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| ADS-2001 — [BE][Setari ] - Desi profesoara a fost stearsa de la cadre didactice ea apare in continuare la roluri si permisiuni si nu se poate sterge de acolo- la stergere apare eroar 400 | To Do | Finish |
| ADS-5722 — [BE/FE] Modal adauga note | In Progress | Finish |
| ADS-6638 — [Preferinte][Notificari] Refactor pagina de gestionare notificări | Testing | Progress |
| ADS-7571 — Utilizatori.php: candidate profile_get() dereferences missing candidate row in GET /api/v2/utilizatori/profile - 48 warnings/24h | In Progress |  |
| ADS-7575 — M_export.php / Export.php: student export references missing second-semester average column and returns HTTP 500 on /ro/secretary/export/elevi - 16 hits/24h | Ready for testing | Finish |
| ADS-7907 — [BE] Refactoring SQL_CALC_FOUND_ROWS | Ready for testing | Progress |
| ADS-8078 — Stergere elevi de test | In Progress |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did committed items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show carryovers split by progress continuation, dependency, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 40 | 40 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 52 | 52 issues in the Friday review snapshot |
| Normalized sprint fact base | 43 | 43 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.