# Engineering Pulse — Team 1 ADS Q3 W27 - 06-10 Jul

Planned sprint ADS Q3 W27 - 06-10 Jul • planning snapshot + end-of-sprint outcome snapshot

This version uses the planning snapshot as the promise set and the outcome snapshot as the result set. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 24/57 visible items. The team absorbed noise well — 17/29 added items were closed — but finish predictability was only 21.7% (5/23), and bugs made up 83.3% of completed items. Planning-baseline carryover includes 18 finish misses and 3 expected progress continuations.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 25.0% (7/28) | Planned items marked Done ÷ all planned committed items |
| Planning-baseline carryover | 75.0% (21/28) | All planned items not Done, including expected Progress continuations |
| Finish-intent carryover | 78.3% (18/23) | Finish-intent planned items not Done ÷ all finish-intent planned items |
| Finish predictability | 21.7% (5/23) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 60.0% (3/5) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 50.9% (29/57) | Outcome-only items ÷ all visible items |
| Added work closure | 17/29 | All added items marked Done |
| Reactive load (bug share) | 83.3% (20/24) | Completed bugs ÷ all completed work |
| Planning quality | 21.4% (6/28) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 0 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

The sprint did not fail; it traded predictability for responsiveness. 17/29 added items were closed, but that responsiveness came with 83.3% bug share and diluted finish predictability.

The miss pattern is concentrated: 2 partial-completion carryovers, 1 dependency-driven misses, and 12 planning-baseline items that never really started.

Most misses were not caused by poor readiness. 5 of the 21 planning-baseline carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 2 | 0 | 0 | 0 | 2 | 8.3% |
| Task | 0 | 2 | 0 | 0 | 2 | 8.3% |
| Bug | 5 | 15 | 0 | 0 | 20 | 83.3% |

# Planning baseline: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Planning-baseline items | 28 | Items present in the frozen planning snapshot |
| Planning-baseline done | 7 | Closed by sprint review |
| Planning-baseline carryover | 21 | All planned items still open, including Progress continuation |
| Finish-intent carryover | 18 | Planned-to-finish items that did not finish |
| Progress continuation | 3 | Progress-intent planned items still open as expected |
| Planning-baseline items marked Ready | 6 | Planning-quality input |
| Carryovers marked Ready | 5 | Ready did not guarantee closure |
| Carryovers not started | 12 | Execution focus gap |
| Carryovers started but unfinished | 2 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Intent | Status | Why it carried |
| --- | --- | --- | --- | --- |
| ADS-2001 — Bug — [BE][Setari ] - Desi profesoara a fost stearsa de la cadre didactice ea apare in continuare la roluri si permisiuni si nu se poate sterge de acolo- la stergere apare eroar 400 | Ivan Ioana | Finish | To Do |  |
| ADS-4439 — Bug — [Teste si chestionare] - Numarul de destinatari care se afiseaza nu corespunde cu numarul real de destinatari | Marian Andrei | Finish | To Do | Not started |
| ADS-5931 — Story — Seedere de date - cod in proiect | Andrei Dragan |  | To Do | Not started |
| ADS-6545 — Story — [SDK] Implementare v1 layer comunicare native-web *post message bridge | Ivan Ioana | Finish | Ready to merge | Not started |
| ADS-6698 — Bug — [FE/BE] Restrictie vizualizare fise scolare | Marian Andrei | Finish | To Do | Not started |
| ADS-7305 — Task — [REQ] - Remote Session Termination for Users | Andrei Dragan | Progress | To Do | Not started |
| ADS-7389 — Bug — AdservioAPI.php: svcAuth self-call failures turn web API endpoints into HTTP 500 - 20 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7390 — Bug — rooms-api: room search endpoint returns HTTP 500 - 3 hits/Friday | Ionut Ciolan | Finish | To Do | Not started |
| ADS-7484 — Bug — Session.php: session_start() fails reading session data during teacher class-book requests - 26 errors/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7653 — Bug — Clase_profesori.php / M_cmc.php: teacher-class assignment insert fails FK constraint in cat_cadre2materii2clase - 2 errors/24h | Marian Andrei | Finish | To Do | Not started |
| ADS-7721 — Bug — Repartizari.php / M_elevi.php: grade-system visibility toggle inserts partial student config row and fails when no override exists - 3 errors/24h | Marian Andrei | Finish | To Do |  |
| ADS-7852 — Task — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata | Andrei Dragan | Finish | Code Review | Partial completion |
| ADS-7907 — Task — [BE] Refactoring SQL_CALC_FOUND_ROWS | Marian Andrei | Finish | Ready for testing | Partial completion |
| ADS-7908 — Bug — [Prod][AWS][legacy-web] Auth recaptcha helper dereferences null verification response | Daniel Onisoru | Finish | To Do | Not started |
| ADS-8004 — Improvement — [FE] - Elevii transferati apar in statistici ca "medii neconfirmate" | Marian Andrei | Finish | To Do |  |
| ADS-8061 — Bug — [Prod][AWS][legacy-web] School-transfer edit recalculates status for NULL student ID - 64 errors/72h | Andrei Dragan | Finish | To Do | Not started |
| ADS-8062 — Bug — [Prod][AWS][legacy-web] Certificate template fetch returns 500 when forms schema lookup gets 403 - 26 errors/72h | Petronel Pavel | Finish | To Do | Dependency delay |
| ADS-8067 — Improvement — [Incadrare] Refactoring React & API | Andrei Dragan | Progress | To Do | Late start / sequencing |
| ADS-8105 — Story — Impartirea pe module | Ivan Ioana | Progress | In Progress |  |
| ADS-8108 — Bug — [Prod][AWS][legacy-web] Teacher exam-prep save writes unsupported peeTipPregatire value - 2 errors/72h | Marian Andrei | Finish | To Do | Not started |
| ADS-8151 — Bug — [Prod][AWS][legacy-web] POST /ro/secretary/export/elevi returns HTTP 500 from M_export num_rows on bool - 4 errors/72h | Marian Andrei | Finish | To Do |  |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 2 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 1 | Capacity protection or dependency timing created slip |
| Not started | 12 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 2 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| None |  |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did finish-intent items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show finish-intent carryovers split by dependency, partial completion, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 30 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 79 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 57 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 28 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 57 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 28 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 29 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 0 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 22 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Committed completion | 25.0% (7/28) | planned committed items marked Done ÷ all planned committed items | 7/28 | Open denominator JQL |
| Planning-baseline carryover | 75.0% (21/28) | planned baseline items not Done at review ÷ all planned baseline items | 21/28 | Open denominator JQL |
| Finish-intent carryover | 78.3% (18/23) | finish-intent planned items not Done at review ÷ all finish-intent planned items | 18/23 | Open denominator JQL |
| Finish predictability | 21.7% (5/23) | finish-intent committed items marked Done ÷ all finish-intent committed items | 5/23 | Open denominator JQL |
| Progress predictability | 60.0% (3/5) | progress-intent items that carried as intended ÷ all progress-intent committed items | 3/5 | Open denominator JQL |
| Added-during-sprint load | 50.9% (29/57) | visible items absent from planning and present in review ÷ all visible sprint items | 29/57 | Open denominator JQL |
| Added work closure | 17/29 | added visible items marked Done ÷ all added visible items | 17/29 | Open denominator JQL |
| Planning quality | 21.4% (6/28) | committed items marked Ready in planning snapshot ÷ all committed items | 6/28 | Open denominator JQL |
| Carryovers marked Ready | 23.8% (5/21) | carryovers that were marked Ready in planning snapshot ÷ all carryovers | 5/21 | Open denominator JQL |
| Reactive load | 83.3% (20/24) | completed bugs ÷ all completed work | 20/24 | Open denominator JQL |
| Workflow-truth mismatches | 0 | Done rows with non-final workflow status | 0/24 | Open denominator JQL |

Planning-baseline carryover includes both finish-intent misses and expected Progress continuations. Use Finish-intent carryover when you want only planned-to-finish items that did not finish.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.