# Engineering Pulse — Team 1 ADS Q3 W36 - 07-11 Sep

Planned sprint ADS Q3 W36 - 07-11 Sep • planning snapshot + end-of-sprint outcome snapshot

This version uses the planning snapshot as the promise set and the outcome snapshot as the result set. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 15/37 visible items. The team absorbed noise well — 10/13 added items were closed — but predictability on committed work was only 25.9% (7/27), and bugs made up 73.3% of completed items. The main drag was execution system quality, not readiness: 6/20 carryovers had been marked Ready at planning time.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 25.9% (7/27) | Planned items marked Done ÷ all planned committed items |
| Committed carryover | 74.1% (20/27) | Planned committed carryovers ÷ all planned committed items |
| Finish predictability | 30.4% (7/23) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 100.0% (3/3) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 35.1% (13/37) | Added items ÷ all visible items |
| Added work closure | 10/13 | All added items marked Done |
| Reactive load (bug share) | 73.3% (11/15) | Completed bugs ÷ all completed work |
| Planning quality | 37.0% (10/27) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 2 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

The sprint did not fail; it traded predictability for responsiveness. 10/13 added items were closed, but that responsiveness came with 73.3% bug share and diluted committed completion.

The miss pattern is concentrated: 4 partial-completion carryovers, 0 dependency-driven misses, and 15 committed items that never really started.

Most misses were not caused by poor readiness. 6 of the 20 carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 0 | 0 | 0 | 0 | 0 | 0.0% |
| Task | 0 | 2 | 0 | 0 | 2 | 13.3% |
| Bug | 5 | 6 | 0 | 0 | 11 | 73.3% |

# Committed work: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Committed items | 27 | Explicit promise set |
| Committed done | 7 | Closed as promised |
| Committed carry over | 20 | Unfinished promise |
| Committed items marked Ready | 10 | Planning-quality input |
| Carryovers marked Ready | 6 | Ready did not guarantee finish |
| Carryovers not started | 15 | Execution focus gap |
| Carryovers started but unfinished | 4 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Status | Why it carried |
| --- | --- | --- | --- |
| ADS-2590 — Bug — [Students] - Trebuie inlocuit articolul de la model import automat-date de completare si sa se deschida articolul din manualul de utilizare daca de da click pe linkul respectiv | Marian Andrei | To Do | Not started |
| ADS-7818 — Story — [SIIIR] - Import elevi | Marian Andrei | In Progress | Partial completion |
| ADS-7852 — Task — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata | Andrei Dragan | To Do | Not started |
| ADS-8209 — Bug — [Prod][AWS][legacy-web] GET /api/v2/fisiere/view returns HTTP 500 when M_fisiere.php calls query() on null | Cojan Paul-Catalin | To Do | Not started |
| ADS-8366 — Bug — [Prod][AWS][legacy-web] Tenantless API requests hit null school DB handle across timetable, grades, and portfolio | Ionut Ciolan | To Do | Not started |
| ADS-8486 — Task — [Catalog] - Import note din VIVA (verificare format și date necesare) | Andrei Dragan | In Progress | Partial completion |
| ADS-8506 — Bug — [Prod][AWS][legacy-web] Student export binds an empty DATE value and silently returns no rows - 10 errors/72h | Marian Andrei | To Do | Not started |
| ADS-8510 — Bug — [FE] diferenta numar elevi in raportul "promovabilitae elevi" | Andrei Dragan | To Do | Not started |
| ADS-8569 — Task — [BE] transfer date comasare scoli | Ionut Ciolan | To Do | Not started |
| ADS-8570 — Task — [FE] inactivare conturi in urma comasarii | Ionut Ciolan | To Do | Not started |
| ADS-8580 — Task — Recuperare date sterse elev ID 775987 | Daniel Onisoru | In Progress | Partial completion |
| ADS-8598 — Task — [BE] aflare cine l-a sters pe elev ID 2372338 | Daniel Onisoru | In Progress | Partial completion |
| ADS-8624 — Bug — [2FA] Dezactivarea autentificării prin cod e-mail eșuează cu error.e_99 | Andrei Dragan | To Do | Not started |
| ADS-8656 — Task — [BE]: [Incadrare] Sync catalog si alte dependente prin event-uri | Andrei Dragan | To Do | Not started |
| ADS-8684 — Bug — [Prod][AWS][Web] Invalid SIIIR encryption key breaks saved-account authentication |  | To Do | Not started |
| ADS-8687 — Bug — [Prod][AWS][Web] Student averages API dereferences missing class metadata - 14 failures/72h |  | To Do | Not started |
| ADS-8688 — Bug — [Prod][AWS][legacy-web] Class-teacher save returns 500 for missing or invalid subject |  | To Do | Not started |
| ADS-8695 — Task — [BE]: Adaugare nota tip corigenta pe Maarif | Andrei Dragan |  | Missing from outcome snapshot |
| ADS-8713 — Bug — [FE] cod de inregistrare invalid la accesarea linkului din email | Marian Andrei | To Do | Not started |
| ADS-8723 — Improvement — Posibilitate generare orar atunci cand exista 2 profesori principali | Ionut Ciolan | To Do | Not started |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 4 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 0 | Capacity protection or dependency timing created slip |
| Not started | 15 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 4 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| ADS-8638 — [BE] eroare 403 cand un cadru didactic acceseaza o pagina pe anul scolar trecut | In Progress | Finish |
| ADS-8674 — stergere cont profesor Goiceanu Laura Mara | In Progress | Finish |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did committed items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show carryovers split by progress continuation, dependency, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 27 | 27 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 38 | 38 issues in the Friday review snapshot |
| Normalized sprint fact base | 37 | 37 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.