# Engineering Pulse — Team 1 ADS Q3 W38 - 21-25 Sep

Planned sprint ADS Q3 W38 - 21-25 Sep • planning snapshot + end-of-sprint outcome snapshot

This version uses the planning snapshot as the promise set and the outcome snapshot as the result set. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 17/33 visible items. The team absorbed noise well — 11/20 added items were closed — but predictability on committed work was only 50.0% (10/20), and bugs made up 29.4% of completed items. The main drag was execution system quality, not readiness: 4/10 carryovers had been marked Ready at planning time.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 50.0% (10/20) | Planned items marked Done ÷ all planned committed items |
| Committed carryover | 50.0% (10/20) | Planned committed carryovers ÷ all planned committed items |
| Finish predictability | 56.2% (9/16) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 75.0% (3/4) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 60.6% (20/33) | Added items ÷ all visible items |
| Added work closure | 11/20 | All added items marked Done |
| Reactive load (bug share) | 29.4% (5/17) | Completed bugs ÷ all completed work |
| Planning quality | 35.0% (7/20) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 0 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

The sprint did not fail; it traded predictability for responsiveness. 11/20 added items were closed, but that responsiveness came with 29.4% bug share and diluted committed completion.

The miss pattern is concentrated: 9 partial-completion carryovers, 0 dependency-driven misses, and 1 committed items that never really started.

Most misses were not caused by poor readiness. 4 of the 10 carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 0 | 0 | 0 | 0 | 0 | 0.0% |
| Task | 4 | 6 | 0 | 0 | 10 | 58.8% |
| Bug | 1 | 4 | 0 | 0 | 5 | 29.4% |

# Committed work: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Committed items | 20 | Explicit promise set |
| Committed done | 10 | Closed as promised |
| Committed carry over | 10 | Unfinished promise |
| Committed items marked Ready | 7 | Planning-quality input |
| Carryovers marked Ready | 4 | Ready did not guarantee finish |
| Carryovers not started | 1 | Execution focus gap |
| Carryovers started but unfinished | 7 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Status | Why it carried |
| --- | --- | --- | --- |
| ADS-3757 — Story — [Site] - Actualizare website Adservio | Petronel Pavel | In Progress | Partial completion |
| ADS-7803 — Task — [FE/BE/MOB/UNI] - Titulatura | Ivan Ioana | In Progress | Partial completion |
| ADS-7817 — Story — [SIIIR] - Import cadre didactice | Marian Andrei | In Progress | Partial completion |
| ADS-8567 — Story — NOMENCLATOR - Refactor structura clasa | Marian Andrei | In Progress | Partial completion |
| ADS-8580 — Task — Recuperare date sterse elev ID 775987 | Daniel Onisoru | In Progress | Partial completion |
| ADS-8598 — Task — [BE] aflare cine l-a sters pe elev ID 2372338 | Daniel Onisoru | In Progress | Partial completion |
| ADS-8723 — Improvement — Posibilitate generare orar atunci cand exista 2 profesori principali | Ionut Ciolan | Testing | Partial completion |
| ADS-8760 — Task — [FE]: Schimbari pe Suprascrieri si transferuri | Ivan Ioana | To Do | Partial completion |
| ADS-8785 — Bug — [Prod][AWS][Auth] Password recovery silently skips missing parent profile - 28 requests/72h | Daniel Onisoru | To Do | Partial completion |
| ADS-8841 — Bug — [FE] Clase lipsa din statisticile de promovabilitate pentru anul scolar 2025-2026 | Ivan Ioana | To Do | Not started |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 9 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 0 | Capacity protection or dependency timing created slip |
| Not started | 1 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 7 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| None |  |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did committed items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show carryovers split by progress continuation, dependency, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 26 | 26 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 39 | 39 issues in the Friday review snapshot |
| Normalized sprint fact base | 33 | 33 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.