# Engineering Pulse — Team 2 ADS Q2 W22 - 01-05 Iunie

Planned sprint ADS Q2 W22 - 01-05 Iunie • planning snapshot + end-of-sprint outcome snapshot

This version uses the planning snapshot as the promise set and the outcome snapshot as the result set. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 4/16 visible items. The team absorbed noise well — 0/2 added items were closed — but finish predictability was only 25.0% (3/12), and bugs made up 50.0% of completed items. Planning-baseline carryover includes 9 finish misses and 1 expected progress continuations.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 28.6% (4/14) | Planned items marked Done ÷ all planned committed items |
| Planning-baseline carryover | 71.4% (10/14) | All planned items not Done, including expected Progress continuations |
| Finish-intent carryover | 75.0% (9/12) | Finish-intent planned items not Done ÷ all finish-intent planned items |
| Finish predictability | 25.0% (3/12) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 50.0% (1/2) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 12.5% (2/16) | Outcome-only items ÷ all visible items |
| Added work closure | 0/2 | All added items marked Done |
| Reactive load (bug share) | 50.0% (2/4) | Completed bugs ÷ all completed work |
| Planning quality | 35.7% (5/14) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 0 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

The sprint did not fail; it traded predictability for responsiveness. 0/2 added items were closed, but that responsiveness came with 50.0% bug share and diluted finish predictability.

The miss pattern is concentrated: 4 partial-completion carryovers, 4 dependency-driven misses, and 2 planning-baseline items that never really started.

Most misses were not caused by poor readiness. 4 of the 10 planning-baseline carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 1 | 0 | 0 | 0 | 1 | 25.0% |
| Task | 1 | 0 | 0 | 0 | 1 | 25.0% |
| Bug | 2 | 0 | 0 | 0 | 2 | 50.0% |

# Planning baseline: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Planning-baseline items | 14 | Items present in the frozen planning snapshot |
| Planning-baseline done | 4 | Closed by sprint review |
| Planning-baseline carryover | 10 | All planned items still open, including Progress continuation |
| Finish-intent carryover | 9 | Planned-to-finish items that did not finish |
| Progress continuation | 1 | Progress-intent planned items still open as expected |
| Planning-baseline items marked Ready | 5 | Planning-quality input |
| Carryovers marked Ready | 4 | Ready did not guarantee closure |
| Carryovers not started | 2 | Execution focus gap |
| Carryovers started but unfinished | 9 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Intent | Status | Why it carried |
| --- | --- | --- | --- | --- |
| ADS-1757 — Story — [Financiar] - Plati partiale | Edgar Alexa | Finish | In Progress | Dependency delay |
| ADS-6494 — Story — Log levels & Log formats | Cojan Paul-Catalin | Finish | In Progress | Not started |
| ADS-7284 — Story — Refactorizare "Anuleaza recurenta" | Edgar Alexa | Progress | In Progress | Partial completion |
| ADS-7405 — Story — [BE] - Local Cache | Alex Murarescu | Finish | In Progress | Dependency delay |
| ADS-7423 — Task — [Stiri] - Updates after release/feedback | Alex Murarescu | Finish | In Progress | Partial completion |
| ADS-7427 — Story — [Admitere v2][Taxe] - 3. Admin Vizualizare/Validare plată | Dragoș Ivan | Finish | In Progress | Dependency delay |
| ADS-7428 — Story — [Admitere v2][Taxe] - 4. Candidate - Necesita modificări | George Murgoci | Finish | In Progress | Partial completion |
| ADS-7430 — Story — [Admitere v2][Taxe] - 5. Export platile candidatului | George Murgoci | Finish | To Do | Not started |
| ADS-7519 — Task — [BE] "Afișează noutăți Adservio" toggle is non-functional | Alex Murarescu | Finish | In Progress | Dependency delay |
| ADS-7743 — Bug — [FE/BE] - Bugs Admitere v3 | George Murgoci | Finish | In Progress | Partial completion |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 4 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 4 | Capacity protection or dependency timing created slip |
| Not started | 2 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 9 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| None |  |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did finish-intent items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show finish-intent carryovers split by dependency, partial completion, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 15 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 17 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 16 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 14 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 16 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 14 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 2 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 0 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 1 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Committed completion | 28.6% (4/14) | planned committed items marked Done ÷ all planned committed items | 4/14 | Open denominator JQL |
| Planning-baseline carryover | 71.4% (10/14) | planned baseline items not Done at review ÷ all planned baseline items | 10/14 | Open denominator JQL |
| Finish-intent carryover | 75.0% (9/12) | finish-intent planned items not Done at review ÷ all finish-intent planned items | 9/12 | Open denominator JQL |
| Finish predictability | 25.0% (3/12) | finish-intent committed items marked Done ÷ all finish-intent committed items | 3/12 | Open denominator JQL |
| Progress predictability | 50.0% (1/2) | progress-intent items that carried as intended ÷ all progress-intent committed items | 1/2 | Open denominator JQL |
| Added-during-sprint load | 12.5% (2/16) | visible items absent from planning and present in review ÷ all visible sprint items | 2/16 | Open denominator JQL |
| Added work closure | 0/2 | added visible items marked Done ÷ all added visible items | 0/2 | Open denominator JQL |
| Planning quality | 35.7% (5/14) | committed items marked Ready in planning snapshot ÷ all committed items | 5/14 | Open denominator JQL |
| Carryovers marked Ready | 40.0% (4/10) | carryovers that were marked Ready in planning snapshot ÷ all carryovers | 4/10 | Open denominator JQL |
| Reactive load | 50.0% (2/4) | completed bugs ÷ all completed work | 2/4 | Open denominator JQL |
| Workflow-truth mismatches | 0 | Done rows with non-final workflow status | 0/4 | Open denominator JQL |

Planning-baseline carryover includes both finish-intent misses and expected Progress continuations. Use Finish-intent carryover when you want only planned-to-finish items that did not finish.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.