# Engineering Pulse — Team 2 ADS Q3 W39 - 28 Sep-02 Oct

Planned sprint ADS Q3 W39 - 28 Sep-02 Oct • planning snapshot + end-of-sprint outcome snapshot

This version uses the planning snapshot as the promise set and the outcome snapshot as the result set. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 10/29 visible items. The team absorbed noise well — 3/8 added items were closed — but predictability on committed work was only 33.3% (7/21), and bugs made up 70.0% of completed items. The main drag was execution system quality, not readiness: 5/14 carryovers had been marked Ready at planning time.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 33.3% (7/21) | Planned items marked Done ÷ all planned committed items |
| Committed carryover | 66.7% (14/21) | Planned committed carryovers ÷ all planned committed items |
| Finish predictability | 38.9% (7/18) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 100.0% (2/2) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 27.6% (8/29) | Added items ÷ all visible items |
| Added work closure | 3/8 | All added items marked Done |
| Reactive load (bug share) | 70.0% (7/10) | Completed bugs ÷ all completed work |
| Planning quality | 33.3% (7/21) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 0 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

The sprint did not fail; it traded predictability for responsiveness. 3/8 added items were closed, but that responsiveness came with 70.0% bug share and diluted committed completion.

The miss pattern is concentrated: 7 partial-completion carryovers, 0 dependency-driven misses, and 6 committed items that never really started.

Most misses were not caused by poor readiness. 5 of the 14 carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 0 | 0 | 0 | 0 | 0 | 0.0% |
| Task | 2 | 1 | 0 | 0 | 3 | 30.0% |
| Bug | 5 | 2 | 0 | 0 | 7 | 70.0% |

# Committed work: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Committed items | 21 | Explicit promise set |
| Committed done | 7 | Closed as promised |
| Committed carry over | 14 | Unfinished promise |
| Committed items marked Ready | 7 | Planning-quality input |
| Carryovers marked Ready | 5 | Ready did not guarantee finish |
| Carryovers not started | 6 | Execution focus gap |
| Carryovers started but unfinished | 7 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Status | Why it carried |
| --- | --- | --- | --- |
| ADS-5654 — Story — [UPA,UPG, Asachi] Taxe școlarizare | George Murgoci | Testing | Partial completion |
| ADS-6159 — Story — Notification Center for Mobile | Dragoș Ivan | In Progress | Partial completion |
| ADS-7086 — Task — [Subscripție] - Rambursare | Dragoș Ivan | To Do | Not started |
| ADS-7354 — Story — [Abonamente] - Gestionare recurență pachete anuale | Edgar Alexa | In Progress | Partial completion |
| ADS-7657 — Bug — subscriptions-api: public package lookup crashes on missing user context (HTTP 500) | Edgar Alexa | To Do | Not started |
| ADS-8223 — Bug — [Prod][AWS][ingress] POST /api/v2/fisiere/upload maps backend 400 to HTTP 500 - 10/72h | Cojan Paul-Catalin |  | Missing from outcome snapshot |
| ADS-8259 — Story — [Abonamente][RC] - Rambursare clienti | Dragoș Ivan | To Do | Not started |
| ADS-8501 — Task — S3: Ștergere variabile OSS vechi și verificat că totul merge bine | Cojan Paul-Catalin | In Progress | Partial completion |
| ADS-8671 — Story — [AI - MCP] Teacher summaries | Alex Murarescu | In Progress | Partial completion |
| ADS-8733 — Bug — [Prod][Billing] Custom Invoice workload exposes premature PostgreSQL client release and slow pending-charge aggregation | Edgar Alexa | To Do | Not started |
| ADS-8757 — Story — [Billing] - Migrat tot codul pe Nest | George Murgoci | In Progress | Partial completion |
| ADS-8769 — Improvement — [Abonamente][Admin][Statistici] - Updates | Edgar Alexa | To Do | Not started |
| ADS-8798 — Task — [MOB][FE] - Front end optimizations for mobile app | Dragoș Ivan | To Do | Not started |
| ADS-8890 — Task — [AI] Cleanup summaries | Alex Murarescu | In Progress | Partial completion |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 7 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 0 | Capacity protection or dependency timing created slip |
| Not started | 6 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 7 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| None |  |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did committed items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show carryovers split by progress continuation, dependency, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 22 | 22 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 29 | 29 issues in the Friday review snapshot |
| Normalized sprint fact base | 29 | 29 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.