# Product Pulse — Mobile ADS Q2 W25 - 22-26 Jun

Planned sprint ADS Q2 W25 - 22-26 Jun • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 5 of 16 visible items, including 2 Stories, 2 Tasks, and 1 Bugs. Product movement was real, but the sprint was still noisy: 3 items entered after planning and 0 of them were closed. The main misses were concentrated in 11 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 16 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 5 | Items whose final outcome bucket is Done |
| Carry overs | 11 | Items not closed at sprint review |
| Delivered mix | 2 / 2 / 1 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 12 / 3 / 1 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 7 / 9 / 0 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 1/2 | Progress items were expected not to finish in this sprint |

# Stories done (2)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |
| ADS-7832 — BFF - Mobile | Planned |
| ADS-7977 — [MOB] - Deeplink email | Planned |

# Tasks done (2)

| Jira item | How entered |
| --- | --- |
| ADS-6098 — [Mobile] - nu apare "Management clasa" daca nu este materia "Dirigentie" in incadrare | Planned |
| ADS-7542 — [MOB] - Fixes and changes | Planned |

# Bugs done (1)

| Jira item | How entered |
| --- | --- |
| ADS-7811 — [Prod][mobile] Extracurricular periods endpoint returns error-level 403s when first-party app hits feature-disabled schools | Planned |

# Carry overs / not delivered (11)

| Jira item | Why it carried |
| --- | --- |
| ADS-5048 — Bug — [MOB] - Fixuri pentru release |  |
| ADS-5737 — Bug — [MOB][Photo] - Nu functioneaza filtrele de ani si de albume | Not started |
| ADS-5808 — Bug — [MOB][Wellbeing] - Parintele nu poate vizualiza testele de autocunoastere pe mob | Not started |
| ADS-6990 — Bug — [MOB] - Mesaj gresit la stergerea unei note mai vechi de 24 ore |  |
| ADS-7141 — Story — [Mob] - Redesign dashboard profesor | Bug / rework pressure |
| ADS-7807 — Story — [MOB] - Notificări modul admitere |  |
| ADS-7831 — Story — [Spike] - Mobile app cold start |  |
| ADS-7962 — Story — [MOB] Translate app in French |  |
| ADS-7976 — Story — [MOB] BFF - newsfeed | Partial completion |
| ADS-8049 — Bug — [MOB] - Primele doua ecrane de autentificare raman in limba romana dupa selectarea limbii engleze |  |
| ADS-8068 — Story — [MOB] - Încheiere situatie |  |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 1 | Carryovers blocked by partial completion |
| Dependency / competing work | 0 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 2 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

1 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

One Done row (ADS-7832 — Story — BFF - Mobile) is still flagged as Partial completion in the outcome file. The report respects the outcome as Done and treats the flag as a data-quality anomaly.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 13 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 16 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 16 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 13 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 16 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 13 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 3 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 0 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 0 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Visible sprint items | 16 | all rows in the outcome snapshot | 16/16 | Open denominator JQL |
| Delivered items | 5 | rows whose Sprint Outcome is Done | 5/16 | Open denominator JQL |
| Carry overs | 11 | rows whose Sprint Outcome is Carry Over or remained open in review | 11/16 | Open denominator JQL |
| Stories done | 2 | done items where issue type = Story | 2/5 | Open denominator JQL |
| Tasks done | 2 | done items where issue type = Task | 2/5 | Open denominator JQL |
| Bugs done | 1 | done items where issue type = Bug | 1/5 | Open denominator JQL |
| Entry kind mix | 12 / 3 / 1 | Planned / Added / Stretch counts across all visible sprint items | 16/16 | Open denominator JQL |
| Readiness mix | 7 / 9 / 0 | Ready / At risk / Not Ready counts across all visible sprint items | 16/16 | Open denominator JQL |
| Progress items behaving as intended | 1/2 | progress-intent items that carried as intended ÷ all progress-intent committed items | 1/2 | Open denominator JQL |
| Partial completion misses | 1 | carryover items whose miss reason is Partial completion | 1/11 | Open denominator JQL |
| Dependency / competing work misses | 0 | carryover items whose miss reason is Dependency delay | 0/11 | Open denominator JQL |
| Not-started misses | 2 | carryover items whose miss reason is Not started | 2/11 | Open denominator JQL |

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.