# Product Pulse — Org Adservio ADS Q1-26 W-11-12

Aggregated sprint ADS Q1-26 W-11-12 • deduplicated roll-up across included teams

This org roll-up aggregates deduplicated frozen issue facts across 1 team snapshots, then applies the same metric definitions and drill-down model. Counts in metric tables link to snapshot-exact JQL result pages.

# Executive summary

Yellow. The sprint closed 15 of 19 visible items, including 5 Stories, 4 Tasks, and 6 Bugs. Product movement was real, but the sprint was still noisy: 6 items entered after planning and all of them were closed. The main misses were concentrated in 4 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 19 | All rows in the outcome snapshot used for this retrospective |
| Delivered items | 15 | Items whose final outcome bucket is Done |
| Carry overs | 4 | Items not closed at sprint review |
| Delivered mix | 5 / 4 / 6 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 9 / 6 / 3 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 14 / 4 / 1 | Ready / At risk / Not Ready in the outcome snapshot |
| Progress items behaving as intended | 2/2 | Progress items were expected not to finish in this sprint |

# Stories done (5)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | Summary | How entered |
| --- | --- | --- |
| ADS-6834 | [Admitere v2] [US1.2] - Creare componente medie admitere | Planned |
| ADS-7001 | [UNI][MAIN][Mesagerie] - Teste automate E2E | Planned |
| ADS-7074 | [FE][Profil academic]- Modificari UI/UX -Profil academic | Stretch |
| ADS-7075 | [FE][Structura universitate] - Pagina Responsive -Structura universitate | Stretch |
| ADS-7076 | [FE] [Personal universitar] -Pagini responsive -Personal universitar | Stretch |

# Tasks done (4)

| Jira item | Summary | How entered |
| --- | --- | --- |
| ADS-7012 | [UNI][BE] Code Sanity: Deprecate and Remove Unused Endpoints, Services and DAO Methods | Planned |
| ADS-7085 | [UNMB-Muzica]- Import fisiere personal universitar | Added |
| ADS-7128 | [BE][Java] Sync Nomenclator Județe/Localtitati UNI/Preuni | Unclear |
| ADS-7129 | [BE-JAVA] - In situatie scolara disciplinele impuse apar ca neincluse la medie | Planned |

# Bugs done (6)

| Jira item | Summary | How entered |
| --- | --- | --- |
| ADS-6933 | [BE][UPA] - Calcularea numarului de credite in 'Catalog' - 'Promovare studenți' | Planned |
| ADS-7108 | [BE][Asachi] - Eroare la completarea rubricii Informatii: Studiu individual (SI) si Examinari | Added |
| ADS-7134 | [BE][UPA] - Numele Instituţiei de învăţământ superior eronat pe FD de la UPA | Added |
| ADS-7180 | [BE-PHP] - Nu se poate downloada raportul Borderou incasari | Added |
| ADS-7185 | [BE][Asachi] - Notele introduse nu mai sunt vizibile în platformă - pentru studentul Botez | Added |
| ADS-7186 | [FE] - Afisare incorecta a denumirii universitatii in download pdf | Added |

# Carry overs / not delivered (4)

| Jira item | Type | Summary | Why it carried |
| --- | --- | --- | --- |
| ADS-6661 | Story | [Catalog][Situatie scolara] - US4 Echivalari | Partial completion |
| ADS-6835 | Story | [Admitere v2] [US1.3] -Editare medie admitere single | Partial completion |
| ADS-6910 | Bug | [BE-PHP][Cazari] - Soldul de pe fisa studentului nu corespunde cu cel de pe student | Not started |
| ADS-7077 | Task | [QA][Financiar] - E2E testing UMS | Dependency delay |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 2 | Carryovers blocked by partial completion |
| Dependency / competing work | 1 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 1 | Committed item never really got underway |

# Data-quality caveats

This org roll-up is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

Included teams in this org pulse: University.

2 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

One Done row (ADS-7001 — Story — [UNI][MAIN][Mesagerie] - Teste automate E2E) is still flagged as Partial completion in the outcome file. The report respects the outcome as Done and treats the flag as a data-quality anomaly.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Full snapshot list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot full list | 13 | 13 issues used for planning baseline |
| Sprint review / outcome snapshot full list | 19 | 19 issues reviewed at sprint review |

These links are snapshot-exact JQL lists, intended for drill-down and debugging.