# Product Pulse — Org Adservio ADS Q1-26 W-14

Aggregated sprint ADS Q1-26 W-14 • deduplicated roll-up across included teams

This org roll-up aggregates deduplicated frozen issue facts across 1 team snapshots, then applies the same metric definitions and drill-down model. Counts in metric tables link to snapshot-exact JQL result pages.

# Executive summary

Yellow. The sprint closed 7 of 12 visible items, including 0 Stories, 3 Tasks, and 4 Bugs. Product movement was real, but the sprint was still noisy: 1 items entered after planning and 0 of them were closed. The main misses were concentrated in 5 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 12 | All rows in the outcome snapshot used for this retrospective |
| Delivered items | 7 | Items whose final outcome bucket is Done |
| Carry overs | 5 | Items not closed at sprint review |
| Delivered mix | 0 / 3 / 4 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 11 / 1 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 0 / 0 / 0 | Ready / At risk / Not Ready in the outcome snapshot |
| Progress items behaving as intended | 0/0 | Progress items were expected not to finish in this sprint |

# Stories done (0)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |

# Tasks done (3)

| Jira item | How entered |
| --- | --- |
| ADS-7012 — [UNI][BE] Code Sanity: Deprecate and Remove Unused Endpoints, Services and DAO Methods | Planned |
| ADS-7077 — [QA][Financiar] - E2E testing UMS | Planned |
| ADS-7193 — [BE][TUIASI] Migrarea notelor si absentelor de pe persoane cu intrări dublate in UMS, către conturile active | Planned |

# Bugs done (4)

| Jira item | How entered |
| --- | --- |
| ADS-6506 — [BUGS] -Plan de invatamant pe serii | Planned |
| ADS-6933 — [BE][UPA] - Calcularea numarului de credite in 'Catalog' - 'Promovare studenți' | Planned |
| ADS-7175 — [BE-JAva] - Media ECTS nu este calculata corect pentru anumiti studenti | Planned |
| ADS-7192 — [BE][Fisa disciplinei] - Ordinea continuturilor se modifica in UI in momentul editarii acestora | Planned |

# Carry overs / not delivered (5)

| Jira item | Why it carried |
| --- | --- |
| ADS-6662 — Story — [Catalog][Situatie scolara] -US5 Download doc | Partial completion |
| ADS-6835 — Story — [Admitere v2] [US1.3] -Editare medie admitere single | Missing from outcome snapshot |
| ADS-6910 — Bug — [BE-PHP][Cazari] - Soldul de pe fisa studentului nu corespunde cu cel de pe student | Partial completion |
| ADS-7179 — Bug — [BE][Asachi] - Verificare note introduse in sesiunea 1 | Dependency delay |
| ADS-7234 — Bug — [BE][Asachi][Catalog-Situație școlara] - Nu se calculeaza media |  |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 2 | Carryovers blocked by partial completion |
| Dependency / competing work | 1 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 0 | Committed item never really got underway |

# Data-quality caveats

This org roll-up is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

Included teams in this org pulse: University.

One Done row (ADS-7077 — Task — [QA][Financiar] - E2E testing UMS) is still flagged as Dependency delay in the outcome file. The report respects the outcome as Done and treats the flag as a data-quality anomaly.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Full snapshot list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot full list | 11 | 11 issues used for planning baseline |
| Sprint review / outcome snapshot full list | 11 | 11 issues reviewed at sprint review |

These links are snapshot-exact JQL lists, intended for drill-down and debugging.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.