# Product Pulse — Team 1 ADS Q3 W27 - 06-10 Jul

Planned sprint ADS Q3 W27 - 06-10 Jul • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 24 of 57 visible items, including 2 Stories, 2 Tasks, and 20 Bugs. Product movement was real, but the sprint was still noisy: 29 items entered after planning and 17 of them were closed. The main misses were concentrated in 33 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 57 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 24 | Items whose final outcome bucket is Done |
| Carry overs | 33 | Items not closed at sprint review |
| Delivered mix | 2 / 2 / 20 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 28 / 29 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 9 / 47 / 0 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 3/5 | Progress items were expected not to finish in this sprint |

# Stories done (2)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |
| ADS-5784 — [FE/BE] Refactor pagina de permisiuni | Planned |
| ADS-6638 — [Preferinte][Notificari] Refactor pagina de gestionare notificări | Planned |

# Tasks done (2)

| Jira item | How entered |
| --- | --- |
| ADS-8146 — cerere ISJ Iasi Inspector Enea - autentificare parinte ID 2636934 an scolar 2025-2026 | Added |
| ADS-8208 — [BE]: Erori pe api/v2/portofoliu | Added |

# Bugs done (20)

| Jira item | How entered |
| --- | --- |
| ADS-1241 — [FE][Students] - Changes required for when ads_native is active | Added |
| ADS-1506 — [Account] -The e-mail address ovidiu grosu@yahoo.com must be deleted | Added |
| ADS-1695 — [BE][Message]- The ppsx attachment is not loading | Added |
| ADS-1736 — [BE][BUG] Deleting unified accounts may lead to a blocked account | Added |
| ADS-1892 — [FE][Files] - Sort dropdown does not work in the responsive view | Added |
| ADS-2684 — [BE][National days] - Search is case and diacritics sensitive | Added |
| ADS-3409 — [Baza de date] -Stergere adresa de mail din baza de date | Added |
| ADS-3503 — [Annuar] - Imposibilitatea încărcării unei poze în anuar | Added |
| ADS-3751 — [BE] POST ./groups cod 500 | Added |
| ADS-3837 — [Students] - Lipsa preluării implicite a naționalității la importul automat al elevilor | Added |
| ADS-3895 — [Massage ] - Selectarea/Deselectarea Școlilor din Listă se Replică pe Toate Paginile | Added |
| ADS-3903 — [Homework] - Ordinea incorectă a elevilor în secțiunea Teme din contul profesorului | Added |
| ADS-5722 — [BE/FE] Modal adauga note | Planned |
| ADS-7571 — Utilizatori.php: candidate profile_get() dereferences missing candidate row in GET /api/v2/utilizatori/profile - 48 warnings/24h | Planned |
| ADS-8130 — [MOB] - Videoconferinta se creeaza fara selectarea participantilor | Planned |
| ADS-8148 — [BE]: [Grupuri] eroare 500 la stergere mark pe eveniment | Planned |
| ADS-8154 — [Prod][AWS][legacy-web] Teacher portfolio funding list renders undefined labels - 35 errors/72h | Planned |
| ADS-8163 — [FE] - Eroare 400 setare tip nota corigenta ID 165 | Added |
| ADS-8173 — docgen2-api: Gradebook 2022 view returns HTTP 500 after downstream class lookup is forbidden | Added |
| ADS-8189 — [Prod][AWS][legacy-web] End-of-year subject average save reads missing intermediate status - 2,730 errors/72h | Added |

# Carry overs / not delivered (33)

| Jira item | Why it carried |
| --- | --- |
| ADS-1806 — Bug — [LCY][registration codes] - Nu se activează trimiterea codului de înregistrare |  |
| ADS-2001 — Bug — [BE][Setari ] - Desi profesoara a fost stearsa de la cadre didactice ea apare in continuare la roluri si permisiuni si nu se poate sterge de acolo- la stergere apare eroar 400 |  |
| ADS-2590 — Bug — [Students] - Trebuie inlocuit articolul de la model import automat-date de completare si sa se deschida articolul din manualul de utilizare daca de da click pe linkul respectiv |  |
| ADS-3858 — Bug — [Account][Preferences] - Imposibilitatea de a dezasocia contul Zoom pentru profesorii cu conturi secundare |  |
| ADS-3862 — Bug — [Data base] - Parintele Țoptea Petronela nu își poate accesa contul - Colegiul "Costache Negruzzi" Iași |  |
| ADS-3896 — Bug — [Classes][Homework] -Problema la Trimiterea Temelor Corectate din aplicatia de mobil |  |
| ADS-3915 — Bug — [Files] - La distribuirea fișierelor către părinți se poate distribui doar catre primul parinte |  |
| ADS-393 — Bug — [FE/PHP][Behavior] Leftovers from ADS-193 |  |
| ADS-4037 — Bug — [Preferences][Conturi ]- Nu se actualizeaza dezunificarea conturilor in contul utlizatorilor |  |
| ADS-4341 — Bug — [Condica de prezenta] - Nu apare butonul ,, semneaza condica pentru toata ziua | Not started |
| ADS-4439 — Bug — [Teste si chestionare] - Numarul de destinatari care se afiseaza nu corespunde cu numarul real de destinatari | Not started |
| ADS-5931 — Story — Seedere de date - cod in proiect | Not started |
| ADS-6545 — Story — [SDK] Implementare v1 layer comunicare native-web *post message bridge | Not started |
| ADS-6698 — Bug — [FE/BE] Restrictie vizualizare fise scolare | Not started |
| ADS-7305 — Task — [REQ] - Remote Session Termination for Users | Not started |
| ADS-7389 — Bug — AdservioAPI.php: svcAuth self-call failures turn web API endpoints into HTTP 500 - 20 hits/Friday | Not started |
| ADS-7390 — Bug — rooms-api: room search endpoint returns HTTP 500 - 3 hits/Friday | Not started |
| ADS-7484 — Bug — Session.php: session_start() fails reading session data during teacher class-book requests - 26 errors/24h | Not started |
| ADS-7653 — Bug — Clase_profesori.php / M_cmc.php: teacher-class assignment insert fails FK constraint in cat_cadre2materii2clase - 2 errors/24h | Not started |
| ADS-7721 — Bug — Repartizari.php / M_elevi.php: grade-system visibility toggle inserts partial student config row and fails when no override exists - 3 errors/24h |  |
| ADS-7852 — Task — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata | Partial completion |
| ADS-7907 — Task — [BE] Refactoring SQL_CALC_FOUND_ROWS | Partial completion |
| ADS-7908 — Bug — [Prod][AWS][legacy-web] Auth recaptcha helper dereferences null verification response | Not started |
| ADS-8004 — Improvement — [FE] - Elevii transferati apar in statistici ca "medii neconfirmate" |  |
| ADS-8061 — Bug — [Prod][AWS][legacy-web] School-transfer edit recalculates status for NULL student ID - 64 errors/72h | Not started |
| ADS-8062 — Bug — [Prod][AWS][legacy-web] Certificate template fetch returns 500 when forms schema lookup gets 403 - 26 errors/72h | Dependency delay |
| ADS-8067 — Improvement — [Incadrare] Refactoring React & API | Late start / sequencing |
| ADS-8105 — Story — Impartirea pe module |  |
| ADS-8108 — Bug — [Prod][AWS][legacy-web] Teacher exam-prep save writes unsupported peeTipPregatire value - 2 errors/72h | Not started |
| ADS-8151 — Bug — [Prod][AWS][legacy-web] POST /ro/secretary/export/elevi returns HTTP 500 from M_export num_rows on bool - 4 errors/72h |  |
| ADS-8205 — Task — [FE]: Modificari rute pentru Mobile |  |
| ADS-8209 — Bug — [Prod][AWS][legacy-web] GET /api/v2/fisiere/view returns HTTP 500 when M_fisiere.php calls query() on null |  |
| ADS-8212 — Task — Blocare acces in Adservio pentru trimiterea mesajelor a tuturor fostilor elevi, fosti profesori, cat si absolventi |  |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 2 | Carryovers blocked by partial completion |
| Dependency / competing work | 1 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 12 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

3 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

One Done row (ADS-1892 — Bug — [FE][Files] - Sort dropdown does not work in the responsive view) is still flagged as Not started in the outcome file. The report respects the outcome as Done and treats the flag as a data-quality anomaly.

One Done row (ADS-5784 — Story — [FE/BE] Refactor pagina de permisiuni) is still flagged as Late start / sequencing in the outcome file. The report respects the outcome as Done and treats the flag as a data-quality anomaly.

One Done row (ADS-8130 — Bug — [MOB] - Videoconferinta se creeaza fara selectarea participantilor) is still flagged as Not started in the outcome file. The report respects the outcome as Done and treats the flag as a data-quality anomaly.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 30 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 79 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 57 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 28 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 57 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 28 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 29 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 0 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 22 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Visible sprint items | 57 | all rows in the outcome snapshot | 57/57 | Open denominator JQL |
| Delivered items | 24 | rows whose Sprint Outcome is Done | 24/57 | Open denominator JQL |
| Carry overs | 33 | rows whose Sprint Outcome is Carry Over or remained open in review | 33/57 | Open denominator JQL |
| Stories done | 2 | done items where issue type = Story | 2/24 | Open denominator JQL |
| Tasks done | 2 | done items where issue type = Task | 2/24 | Open denominator JQL |
| Bugs done | 20 | done items where issue type = Bug | 20/24 | Open denominator JQL |
| Entry kind mix | 28 / 29 / 0 | Planned / Added / Stretch counts across all visible sprint items | 57/57 | Open denominator JQL |
| Readiness mix | 9 / 47 / 0 | Ready / At risk / Not Ready counts across all visible sprint items | 57/57 | Open denominator JQL |
| Progress items behaving as intended | 3/5 | progress-intent items that carried as intended ÷ all progress-intent committed items | 3/5 | Open denominator JQL |
| Partial completion misses | 2 | carryover items whose miss reason is Partial completion | 2/33 | Open denominator JQL |
| Dependency / competing work misses | 1 | carryover items whose miss reason is Dependency delay | 1/33 | Open denominator JQL |
| Not-started misses | 12 | carryover items whose miss reason is Not started | 12/33 | Open denominator JQL |

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.