# Product Pulse — Team 1 ADS Q3 W29 - 20-24 Jul

Planned sprint ADS Q3 W29 - 20-24 Jul • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 10 of 22 visible items, including 2 Stories, 1 Tasks, and 5 Bugs. Product movement was real, but the sprint was still noisy: 5 items entered after planning and 1 of them were closed. The main misses were concentrated in 12 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 22 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 10 | Items whose final outcome bucket is Done |
| Carry overs | 12 | Items not closed at sprint review |
| Delivered mix | 2 / 1 / 5 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 17 / 5 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 6 / 16 / 0 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 3/3 | Progress items were expected not to finish in this sprint |

# Stories done (2)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |
| ADS-6545 — [SDK] Implementare v1 layer comunicare native-web *post message bridge | Planned |
| ADS-8262 — [FE] Responsive conduită / listă elevi | Planned |

# Tasks done (1)

| Jira item | How entered |
| --- | --- |
| ADS-8205 — [FE]: Modificari rute pentru Mobile | Planned |

# Bugs done (5)

| Jira item | How entered |
| --- | --- |
| ADS-8224 — [FE] La editarea elevului, campul "rol" nu afiseaza optiuni in dropdown si impiedica salvarea modificarilor | Planned |
| ADS-8245 — [FE] Preferințe generale alignment | Planned |
| ADS-8257 — [BE] - Eroare 400 la debifare afisare in catalog a unui transfer intre clase | Planned |
| ADS-8269 — [Documente - Catalog] - De modificat fontul primei pagini | Planned |
| ADS-8282 — [Prod][AWS][legacy-web] Student profile save overflows adrCodPostal because postal length is not validated - 2 errors/72h | Planned |

# Carry overs / not delivered (12)

| Jira item | Why it carried |
| --- | --- |
| ADS-2590 — Bug — [Students] - Trebuie inlocuit articolul de la model import automat-date de completare si sa se deschida articolul din manualul de utilizare daca de da click pe linkul respectiv | Partial completion |
| ADS-3896 — Bug — [Classes][Homework] -Problema la Trimiterea Temelor Corectate din aplicatia de mobil | Not started |
| ADS-5784 — Story — [FE/BE] Refactor pagina de permisiuni |  |
| ADS-7816 — Story — [SIIIR] - Import clase | Partial completion |
| ADS-7907 — Task — [BE] Refactoring SQL_CALC_FOUND_ROWS | Partial completion |
| ADS-8067 — Story — [Incadrare] Refactoring React & API | Late start / sequencing |
| ADS-8105 — Story — Impartirea pe module | Partial completion |
| ADS-8129 — Improvement — Sincronizare istoric elevi |  |
| ADS-8209 — Bug — [Prod][AWS][legacy-web] GET /api/v2/fisiere/view returns HTTP 500 when M_fisiere.php calls query() on null | Not started |
| ADS-8285 — Bug — [Medii] - Recalculare medii greșite |  |
| ADS-8306 — Bug — [FE] - Nefunctionalitate filtru "Elevi" |  |
| ADS-8310 — Bug — [Prod][AWS][legacy-web] Admin home reads missing school session context and renders warnings - 35 errors/72h |  |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 4 | Carryovers blocked by partial completion |
| Dependency / competing work | 0 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 2 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

3 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

One Done row (ADS-8262 — Story — [FE] Responsive conduită / listă elevi) is still flagged as Partial completion in the outcome file. The report respects the outcome as Done and treats the flag as a data-quality anomaly.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 17 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 22 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 22 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 17 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 22 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 17 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 5 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 0 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 0 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Visible sprint items | 22 | all rows in the outcome snapshot | 22/22 | Open denominator JQL |
| Delivered items | 10 | rows whose Sprint Outcome is Done | 10/22 | Open denominator JQL |
| Carry overs | 12 | rows whose Sprint Outcome is Carry Over or remained open in review | 12/22 | Open denominator JQL |
| Stories done | 2 | done items where issue type = Story | 2/10 | Open denominator JQL |
| Tasks done | 1 | done items where issue type = Task | 1/10 | Open denominator JQL |
| Bugs done | 5 | done items where issue type = Bug | 5/10 | Open denominator JQL |
| Entry kind mix | 17 / 5 / 0 | Planned / Added / Stretch counts across all visible sprint items | 22/22 | Open denominator JQL |
| Readiness mix | 6 / 16 / 0 | Ready / At risk / Not Ready counts across all visible sprint items | 22/22 | Open denominator JQL |
| Progress items behaving as intended | 3/3 | progress-intent items that carried as intended ÷ all progress-intent committed items | 3/3 | Open denominator JQL |
| Partial completion misses | 4 | carryover items whose miss reason is Partial completion | 4/12 | Open denominator JQL |
| Dependency / competing work misses | 0 | carryover items whose miss reason is Dependency delay | 0/12 | Open denominator JQL |
| Not-started misses | 2 | carryover items whose miss reason is Not started | 2/12 | Open denominator JQL |

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.