# Product Pulse — Team 1 ADS Q3 W37 - 14-18 Sep

Planned sprint ADS Q3 W37 - 14-18 Sep • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 15 of 34 visible items, including 1 Stories, 5 Tasks, and 8 Bugs. Product movement was real, but the sprint was still noisy: 18 items entered after planning and 11 of them were closed. The main misses were concentrated in 19 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 34 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 15 | Items whose final outcome bucket is Done |
| Carry overs | 19 | Items not closed at sprint review |
| Delivered mix | 1 / 5 / 8 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 16 / 18 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 13 / 20 / 1 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 1/2 | Progress items were expected not to finish in this sprint |

# Stories done (1)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |
| ADS-7818 — [SIIIR] - Import elevi | Planned |

# Tasks done (5)

| Jira item | How entered |
| --- | --- |
| ADS-8486 — [Catalog] - Import note din VIVA (verificare format și date necesare) | Added |
| ADS-8695 — [BE]: Adaugare nota tip corigenta pe Maarif | Planned |
| ADS-8755 — Stergerea bazei de date cu elevii incarcati | Planned |
| ADS-8791 — [BE] stergere module | Added |
| ADS-8795 — nu se primesc codurile de inregistrare/ mail de confirmare pe adresa de e-mail domeniu | Added |

# Bugs done (8)

| Jira item | How entered |
| --- | --- |
| ADS-8724 — [FE/BE] Modal detalii elev ani trecuți | Added |
| ADS-8742 — [FE] catalogul descarcat din arhiva nu contine numele/prenumele/nr telefon al parintilor la date personale | Added |
| ADS-8750 — [Prod] service-fetgenerator crashes on unhandled TypeError when fet-cl reports a data validation error | Added |
| ADS-8754 — [FE] intarziere la selectarea coordonatorului clasei si pierderea datelor completate la refresh | Planned |
| ADS-8784 — [FE] pentru un elev transferat, nu se gaseste transferul in modulul "transferuri" | Added |
| ADS-8789 — [FE] eroare 400 la completare formular contact | Added |
| ADS-8797 — [FE] - Image Cropper | Added |
| ADS-8799 — [FE] selectarea altui elev din catalog nu actualizeaza pagina | Added |

# Carry overs / not delivered (19)

| Jira item | Why it carried |
| --- | --- |
| ADS-2590 — Bug — [Students] - Trebuie inlocuit articolul de la model import automat-date de completare si sa se deschida articolul din manualul de utilizare daca de da click pe linkul respectiv | Not started |
| ADS-3757 — Story — [Site] - Actualizare website Adservio | Partial completion |
| ADS-7803 — Task — [FE/BE/MOB/UNI] - Titulatura | Partial completion |
| ADS-7817 — Story — [SIIIR] - Import cadre didactice | Partial completion |
| ADS-7852 — Task — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata | Partial completion |
| ADS-8569 — Task — [BE] transfer date comasare scoli | Partial completion |
| ADS-8570 — Task — [FE] inactivare conturi in urma comasarii | Partial completion |
| ADS-8580 — Task — Recuperare date sterse elev ID 775987 | Partial completion |
| ADS-8598 — Task — [BE] aflare cine l-a sters pe elev ID 2372338 | Partial completion |
| ADS-8713 — Bug — [FE] cod de inregistrare invalid la accesarea linkului din email | Not started |
| ADS-8721 — Bug — [FE] Butonul de semnare a condicii de prezenta nu e afisat pentru rolul de contabil | Not started |
| ADS-8723 — Improvement — Posibilitate generare orar atunci cand exista 2 profesori principali | Partial completion |
| ADS-8758 — Task — de mutat elevii de clasa aVIII de pe scoala ID 6179 pe ID 6254 | Partial completion |
| ADS-8760 — Task — [FE]: Schimbari pe Suprascrieri si transferuri | Not started |
| ADS-8766 — Bug — [Prod][AWS][legacy-web] Bulk class creation returns 500 when generated class name exceeds storage limit - 35 failures/72h | Not started |
| ADS-8785 — Bug — [Prod][AWS][Auth] Password recovery silently skips missing parent profile - 28 requests/72h | Not started |
| ADS-8792 — Task — Stergere elevi dublati la sincronizarea cu SIIR | Not started |
| ADS-8802 — Bug — [FE] ordine absente gresita pentru elevii de gradinita- 2024-2025 | Not started |
| ADS-8806 — Improvement — [SIIIR] Improvments & bugs | Partial completion |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 9 | Carryovers blocked by partial completion |
| Dependency / competing work | 0 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 5 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

1 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 26 | 26 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 39 | 39 issues in the Friday review snapshot |
| Normalized sprint fact base | 34 | 34 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.