# Product Pulse — Team 1 ADS Q3 W38 - 21-25 Sep

Planned sprint ADS Q3 W38 - 21-25 Sep • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 17 of 33 visible items, including 0 Stories, 10 Tasks, and 5 Bugs. Product movement was real, but the sprint was still noisy: 20 items entered after planning and 11 of them were closed. The main misses were concentrated in 16 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 33 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 17 | Items whose final outcome bucket is Done |
| Carry overs | 16 | Items not closed at sprint review |
| Delivered mix | 0 / 10 / 5 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 13 / 20 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 16 / 16 / 1 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 3/4 | Progress items were expected not to finish in this sprint |

# Stories done (0)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |

# Tasks done (10)

| Jira item | How entered |
| --- | --- |
| ADS-7852 — [BE]: Dezactivare actiuni noteaza (si bulk) daca media anuala si/sau media semestriala este incheiata | Planned |
| ADS-8356 — [Elev][Parinte] - Banner - Web | Added |
| ADS-8569 — [BE] transfer date comasare scoli | Planned |
| ADS-8570 — [FE] inactivare conturi in urma comasarii | Planned |
| ADS-8583 — [Clasa][Materie] - Sortare Medie anuala | Added |
| ADS-8758 — de mutat elevii de clasa aVIII de pe scoala ID 6179 pe ID 6254 | Planned |
| ADS-8792 — Stergere elevi dublati la sincronizarea cu SIIR | Added |
| ADS-8877 — Stergere parinti dublati la sincronizarea cu SIIR | Added |
| ADS-8904 — fixare sistem de notare | Added |
| ADS-8943 — [FE]: UI Improvements | Added |

# Bugs done (5)

| Jira item | How entered |
| --- | --- |
| ADS-8713 — [FE] cod de inregistrare invalid la accesarea linkului din email | Planned |
| ADS-8721 — [FE] Butonul de semnare a condicii de prezenta nu e afisat pentru rolul de contabil | Added |
| ADS-8802 — [FE] ordine absente gresita pentru elevii de gradinita- 2024-2025 | Added |
| ADS-8861 — [Prod][AWS][Web] Allocation deletion returns HTTP 500 while timetable activities reference the CMC | Added |
| ADS-8937 — [Prod][BE][GetResponse] events worker crashloops on null liceuID, queue blocked at 75k messages | Added |

# Carry overs / not delivered (16)

| Jira item | Why it carried |
| --- | --- |
| ADS-3757 — Story — [Site] - Actualizare website Adservio | Partial completion |
| ADS-7803 — Task — [FE/BE/MOB/UNI] - Titulatura | Partial completion |
| ADS-7817 — Story — [SIIIR] - Import cadre didactice | Partial completion |
| ADS-8567 — Story — NOMENCLATOR - Refactor structura clasa | Partial completion |
| ADS-8580 — Task — Recuperare date sterse elev ID 775987 | Partial completion |
| ADS-8598 — Task — [BE] aflare cine l-a sters pe elev ID 2372338 | Partial completion |
| ADS-8723 — Improvement — Posibilitate generare orar atunci cand exista 2 profesori principali | Partial completion |
| ADS-8760 — Task — [FE]: Schimbari pe Suprascrieri si transferuri | Partial completion |
| ADS-8785 — Bug — [Prod][AWS][Auth] Password recovery silently skips missing parent profile - 28 requests/72h | Partial completion |
| ADS-8841 — Bug — [FE] Clase lipsa din statisticile de promovabilitate pentru anul scolar 2025-2026 | Not started |
| ADS-8880 — Task — Adaugare rol "parinte" | Partial completion |
| ADS-8889 — Bug — Ora afisata incorect in istoricul notei | Partial completion |
| ADS-8895 — Bug — [Prod][AWS][Auth] Apple SSO fails when JWKS endpoint transiently returns 404 - 126 requests/72h | Partial completion |
| ADS-8919 — Bug — [MOB] la stergerea unui cont, utilizatorul ramane logat in aplicatie | Partial completion |
| ADS-8933 — Bug — [FE] Numele si prenumele parintelui nu se salveaza la unificarea contului cu cod de inregistrare | Partial completion |
| ADS-8964 — Bug — [Prod][AWS][Web] Absence save returns 500 when annual-average upsert deadlocks | Partial completion |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 9 | Carryovers blocked by partial completion |
| Dependency / competing work | 0 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 1 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

3 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 26 | 26 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 39 | 39 issues in the Friday review snapshot |
| Normalized sprint fact base | 33 | 33 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.