# Product Pulse — Team 2 ADS Q2 W23 - 08-12 June

Planned sprint ADS Q2 W23 - 08-12 June • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 6 of 15 visible items, including 3 Stories, 1 Tasks, and 2 Bugs. Product movement was real, but the sprint was still noisy: 4 items entered after planning and 0 of them were closed. The main misses were concentrated in 9 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 15 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 6 | Items whose final outcome bucket is Done |
| Carry overs | 9 | Items not closed at sprint review |
| Delivered mix | 3 / 1 / 2 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 11 / 4 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 6 / 9 / 0 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 1/2 | Progress items were expected not to finish in this sprint |

# Stories done (3)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |
| ADS-7284 — Refactorizare "Anuleaza recurenta" | Planned |
| ADS-7427 — [Admitere v2][Taxe] - 3. Admin Vizualizare/Validare plată | Planned |
| ADS-7428 — [Admitere v2][Taxe] - 4. Candidate - Necesita modificări | Planned |

# Tasks done (1)

| Jira item | How entered |
| --- | --- |
| ADS-7423 — [Stiri] - Updates after release/feedback | Planned |

# Bugs done (2)

| Jira item | How entered |
| --- | --- |
| ADS-7743 — [FE/BE] - Bugs Admitere v3 | Planned |
| ADS-7773 — [BE][UPA-Admitere] - Bugs | Planned |

# Carry overs / not delivered (9)

| Jira item | Why it carried |
| --- | --- |
| ADS-1757 — Story — [Financiar] - Plati partiale | Dependency delay |
| ADS-6494 — Story — Log levels & Log formats | Dependency delay |
| ADS-7239 — Story — [Admitere v2] - Label/eticheta cazuri speciale | Partial completion |
| ADS-7405 — Story — [BE] - Local Cache | Dependency delay |
| ADS-7430 — Story — [Admitere v2][Taxe] - 5. Export platile candidatului&extinderea cu alte informatii ale candidatilor | Not started |
| ADS-7487 — Story — [Admitere v2] - Adaugare candidat in billing&eliberare chitanta | Partial completion |
| ADS-7519 — Task — [BE] "Afișează noutăți Adservio" toggle is non-functional | Dependency delay |
| ADS-7849 — Story — Stergere date S3 | Partial completion |
| ADS-7874 — Task — [Node/React] Cache images for news created by admins via CDN | Partial completion |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 1 | Carryovers blocked by partial completion |
| Dependency / competing work | 3 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 1 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

1 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 11 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 15 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 15 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 11 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 15 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 11 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 4 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 0 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 0 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Visible sprint items | 15 | all rows in the outcome snapshot | 15/15 | Open denominator JQL |
| Delivered items | 6 | rows whose Sprint Outcome is Done | 6/15 | Open denominator JQL |
| Carry overs | 9 | rows whose Sprint Outcome is Carry Over or remained open in review | 9/15 | Open denominator JQL |
| Stories done | 3 | done items where issue type = Story | 3/6 | Open denominator JQL |
| Tasks done | 1 | done items where issue type = Task | 1/6 | Open denominator JQL |
| Bugs done | 2 | done items where issue type = Bug | 2/6 | Open denominator JQL |
| Entry kind mix | 11 / 4 / 0 | Planned / Added / Stretch counts across all visible sprint items | 15/15 | Open denominator JQL |
| Readiness mix | 6 / 9 / 0 | Ready / At risk / Not Ready counts across all visible sprint items | 15/15 | Open denominator JQL |
| Progress items behaving as intended | 1/2 | progress-intent items that carried as intended ÷ all progress-intent committed items | 1/2 | Open denominator JQL |
| Partial completion misses | 1 | carryover items whose miss reason is Partial completion | 1/9 | Open denominator JQL |
| Dependency / competing work misses | 3 | carryover items whose miss reason is Dependency delay | 3/9 | Open denominator JQL |
| Not-started misses | 1 | carryover items whose miss reason is Not started | 1/9 | Open denominator JQL |

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.