# Product Pulse — Team 2 ADS Q3 W29 - 20-24 Jul

Planned sprint ADS Q3 W29 - 20-24 Jul • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 5 of 14 visible items, including 0 Stories, 3 Tasks, and 1 Bugs. Product movement was real, but the sprint was still noisy: 4 items entered after planning and all of them were closed. The main misses were concentrated in 9 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 14 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 5 | Items whose final outcome bucket is Done |
| Carry overs | 9 | Items not closed at sprint review |
| Delivered mix | 0 / 3 / 1 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 8 / 4 / 2 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 6 / 8 / 0 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 4/5 | Progress items were expected not to finish in this sprint |

# Stories done (0)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |

# Tasks done (3)

| Jira item | How entered |
| --- | --- |
| ADS-6064 — [Internal] Export Clienti Adservio din Billing pentru import in Nexus | Added |
| ADS-7343 — [Stiri] - Distribuie Updates | Planned |
| ADS-8319 — [Abonamente] - Rambursare 2969809 | Added |

# Bugs done (1)

| Jira item | How entered |
| --- | --- |
| ADS-8316 — [Prod][Billing/Frontend] Groups Marks hides eligible services beyond first 100 results | Added |

# Carry overs / not delivered (9)

| Jira item | Why it carried |
| --- | --- |
| ADS-4007 — Bug — [BE][Subscriptions] - Comportament ciudat featureflags in cazul in care sunt dezactivate subscriptiile | Not started |
| ADS-4328 — Story — Headers in Mobile App | Not started |
| ADS-6159 — Story — Notification Center for Mobile | Partial completion |
| ADS-6201 — Story — Log formatting - node.js, subscriptions | Not started |
| ADS-6675 — Story — [Financiar] - Managementul penalitatilor | Partial completion |
| ADS-7474 — Task — [FE] - Optimizare viteză de încărcare pagini | Partial completion |
| ADS-7849 — Story — Stergere date S3 | Bug / rework pressure |
| ADS-8071 — Story — Teste automate flow Subscripții | Partial completion |
| ADS-8223 — Bug — [Prod][AWS][ingress] POST /api/v2/fisiere/upload maps backend 400 to HTTP 500 - 10/72h | Not started |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 4 | Carryovers blocked by partial completion |
| Dependency / competing work | 0 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 4 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

4 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 10 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 14 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 14 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 10 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 14 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 10 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 4 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 0 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 0 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Visible sprint items | 14 | all rows in the outcome snapshot | 14/14 | Open denominator JQL |
| Delivered items | 5 | rows whose Sprint Outcome is Done | 5/14 | Open denominator JQL |
| Carry overs | 9 | rows whose Sprint Outcome is Carry Over or remained open in review | 9/14 | Open denominator JQL |
| Stories done | 0 | done items where issue type = Story | 0/5 | Open denominator JQL |
| Tasks done | 3 | done items where issue type = Task | 3/5 | Open denominator JQL |
| Bugs done | 1 | done items where issue type = Bug | 1/5 | Open denominator JQL |
| Entry kind mix | 8 / 4 / 2 | Planned / Added / Stretch counts across all visible sprint items | 14/14 | Open denominator JQL |
| Readiness mix | 6 / 8 / 0 | Ready / At risk / Not Ready counts across all visible sprint items | 14/14 | Open denominator JQL |
| Progress items behaving as intended | 4/5 | progress-intent items that carried as intended ÷ all progress-intent committed items | 4/5 | Open denominator JQL |
| Partial completion misses | 4 | carryover items whose miss reason is Partial completion | 4/9 | Open denominator JQL |
| Dependency / competing work misses | 0 | carryover items whose miss reason is Dependency delay | 0/9 | Open denominator JQL |
| Not-started misses | 4 | carryover items whose miss reason is Not started | 4/9 | Open denominator JQL |

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.