# Product Pulse — Team 2 ADS Q3 W34 - 24-28 Aug

Planned sprint ADS Q3 W34 - 24-28 Aug • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 5 of 18 visible items, including 1 Stories, 3 Tasks, and 1 Bugs. Product movement was real, but the sprint was still noisy: 4 items entered after planning and 1 of them were closed. The main misses were concentrated in 13 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 18 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 5 | Items whose final outcome bucket is Done |
| Carry overs | 13 | Items not closed at sprint review |
| Delivered mix | 1 / 3 / 1 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 14 / 4 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 8 / 8 / 2 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 2/3 | Progress items were expected not to finish in this sprint |

# Stories done (1)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |
| ADS-7659 — [Abonamente] - Nu pot selecta România din secțiunea de publicare, și nu mai apar pachetele pe site-ul public | Planned |

# Tasks done (3)

| Jira item | How entered |
| --- | --- |
| ADS-8499 — Sync coduri Siruta | Planned |
| ADS-8500 — [AI] - Shared folder, logging, tracing | Planned |
| ADS-8572 — [AI] Validare feature flags pe endpointuri | Added |

# Bugs done (1)

| Jira item | How entered |
| --- | --- |
| ADS-8544 — Billing invoice export can timeout/OOM and silently truncate large result sets | Planned |

# Carry overs / not delivered (13)

| Jira item | Why it carried |
| --- | --- |
| ADS-5654 — Story — [UPA,UPG, Asachi] Taxe școlarizare | Partial completion |
| ADS-7250 — Story — [Abonamente][Checkout] - Data urmatoarei debitari | Dependency delay |
| ADS-7251 — Story — Mutarea subscriptii de pe recurenta An scolar pe recurenta an calendaristic | Dependency delay |
| ADS-7279 — Task — [Billing] - Implementare Stripe + Apple pay + Google pay | Late start / sequencing |
| ADS-7354 — Story — [Abonamente] - Gestionare recurență pachete anuale | Not started |
| ADS-7849 — Story — Stergere date S3 | Priority Change |
| ADS-8223 — Bug — [Prod][AWS][ingress] POST /api/v2/fisiere/upload maps backend 400 to HTTP 500 - 10/72h | Not started |
| ADS-8339 — Story — Tools | Partial completion |
| ADS-8343 — Story — Integration | Partial completion |
| ADS-8383 — Story — [BE] - Local Cache Billing | Dependency delay |
| ADS-8404 — Improvement — [Elev][Parinte] - Redesign - Rapoarte | Not started |
| ADS-8501 — Task — S3: Ștergere variabile OSS vechi și verificat că totul merge bine | Priority Change |
| ADS-8601 — Bug — [FE] eroare 403 la accesarea contului de test- director | Not started |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 2 | Carryovers blocked by partial completion |
| Dependency / competing work | 2 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 3 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

2 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 15 | 15 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 18 | 18 issues in the Friday review snapshot |
| Normalized sprint fact base | 18 | 18 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.