# Product Pulse — Team 2 ADS Q3 W36 - 07-11 Sep

Planned sprint ADS Q3 W36 - 07-11 Sep • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 7 of 20 visible items, including 1 Stories, 1 Tasks, and 5 Bugs. Product movement was real, but the sprint was still noisy: 6 items entered after planning and 4 of them were closed. The main misses were concentrated in 13 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 20 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 7 | Items whose final outcome bucket is Done |
| Carry overs | 13 | Items not closed at sprint review |
| Delivered mix | 1 / 1 / 5 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 14 / 6 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 9 / 10 / 1 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 3/3 | Progress items were expected not to finish in this sprint |

# Stories done (1)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |
| ADS-8383 — [BE] - Local Cache Billing | Planned |

# Tasks done (1)

| Jira item | How entered |
| --- | --- |
| ADS-8694 — [Subscriptions] - Marketing fields | Planned |

# Bugs done (5)

| Jira item | How entered |
| --- | --- |
| ADS-8480 — [Prod][Groups][FE/BE] Invalid OAuth request prevents realtime chat auth - 23 production 401s/5d | Added |
| ADS-8602 — [Prod][AWS][legacy-web] Roles user validation dereferences missing account from social events - 12 warnings/72h | Planned |
| ADS-8690 — [Prod][AWS][Web] Route bootstrap reads missing AI summaries translation key - 37 warnings | Added |
| ADS-8725 — [Prod][Billing] Nightly penalty generation fails, leaving expected penalties unrecorded | Added |
| ADS-8737 — [Prod][Social] Article detail queries lack news_visibility(news_id) index during notification bursts | Added |

# Carry overs / not delivered (13)

| Jira item | Why it carried |
| --- | --- |
| ADS-4026 — Improvement — [Abonamente][Admin] - Option to disable packages | Partial completion |
| ADS-5654 — Story — [UPA,UPG, Asachi] Taxe școlarizare | Partial completion |
| ADS-6159 — Story — Notification Center for Mobile | Partial completion |
| ADS-7272 — Bug — M_user_api.php / M_user.php: subscriptions features lookup fails hard when subscriptions-api-svc is slow or down - 20 errors/48h | Not started |
| ADS-7279 — Task — [Billing] - Implementare Stripe + Apple pay + Google pay | Dependency delay |
| ADS-7354 — Story — [Abonamente] - Gestionare recurență pachete anuale | Not started |
| ADS-7421 — Task — [BE] Cleanup Noutati | Not started |
| ADS-7988 — Bug — [Prod][AWS][legacy-web] School update/logo storage uses invalid S3 endpoint or wrong region - 32,341 errors/72h | Partial completion |
| ADS-8259 — Story — [Abonamente][RC] - Rambursare clienti | Not started |
| ADS-8343 — Story — Integration | Partial completion |
| ADS-8404 — Improvement — [Elev][Parinte] - Redesign - Rapoarte | Partial completion |
| ADS-8671 — Story — [AI - MCP] Teacher summaries | Partial completion |
| ADS-8733 — Bug — [Prod][Billing] Custom Invoice workload exposes premature PostgreSQL client release and slow pending-charge aggregation | Not started |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 6 | Carryovers blocked by partial completion |
| Dependency / competing work | 1 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 4 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

3 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 14 | 14 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 20 | 20 issues in the Friday review snapshot |
| Normalized sprint fact base | 20 | 20 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.