# Product Pulse — University ADS Q2 W24 - 15-19 Jun

Planned sprint ADS Q2 W24 - 15-19 Jun • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 9 of 19 visible items, including 2 Stories, 1 Tasks, and 6 Bugs. Product movement was real, but the sprint was still noisy: 5 items entered after planning and all of them were closed. The main misses were concentrated in 10 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 19 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 9 | Items whose final outcome bucket is Done |
| Carry overs | 10 | Items not closed at sprint review |
| Delivered mix | 2 / 1 / 6 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 14 / 5 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 2 / 17 / 0 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 4/5 | Progress items were expected not to finish in this sprint |

# Stories done (2)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |
| ADS-7375 — [BE/FE] - Disciplinele in EN pentru programele de studiu din EN | Planned |
| ADS-7838 — [BE-JAVA/FE] - Modificari serii -adaugare dropdown Tip Invatamant | Planned |

# Tasks done (1)

| Jira item | How entered |
| --- | --- |
| ADS-7923 — Pentru numerele intregi nu trebuie sa apara separator de zecimale | Added |

# Bugs done (6)

| Jira item | How entered |
| --- | --- |
| ADS-7708 — [BE] - Personal universitar: Numele nu se actualizeaza corect dupa editare | Planned |
| ADS-7720 — [BE-JAVA][Asachi] - Nu mai apare optiune de 'Grupe asociate' pe studenti | Planned |
| ADS-7910 — [Prod][TUIASI][uni-api] DB pool exhaustion breaks academic-years, faculty, and grade-save flows | Added |
| ADS-7926 — [Prod][AWS][uni-api] Student-study disciplines fail when prod DB lacks disciplina.denumireDisciplinaKey | Added |
| ADS-7933 — [FE] - Pe UMS apare catalogul UPA la download | Added |
| ADS-7957 — [FE] - Disciplinele din situatiile scolare apar in engleza | Added |

# Carry overs / not delivered (10)

| Jira item | Why it carried |
| --- | --- |
| ADS-7495 — Story — [FE/BE][Adeverinte absolvire] - Creare Probe evaluare | Partial completion |
| ADS-7496 — Story — [FE/BE][Adeverinte absolvire] - Probe&medie pe situatie scolara | Partial completion |
| ADS-7534 — Story — [FE/BE][Adeverinte absolvire] - Flow generare adeverinte | Partial completion |
| ADS-7574 — Story — [UPG] - Calculul mediilor la nivel de grupa/serie | Partial completion |
| ADS-7666 — Bug — accommodations-api: shared HTTP 500 burst on POST /api/v2/accommodations/dorms/list and related endpoints - 16 hits/20m | Bug / rework pressure |
| ADS-7688 — Bug — [BE] [Studenti] [Muzica]- Studentul nu este unificat pe baza CNP-ului la import | Priority Change |
| ADS-7876 — Bug — [Prod][AWS+TUIASI][uni-api] Auth bootstrap fails when profile lookup lacks uaID or resolves an invalid tenant | Not started |
| ADS-7877 — Bug — [Prod][TUIASI][uni-api] Profile dependency returns 502 Bad Gateway during auth bootstrap | Not started |
| ADS-7880 — Bug — TUIASI uni-api: catalog import and adjacent grades endpoints return HTTP 500 - 23 hits/72h | Not started |
| ADS-7890 — Story — [BE PHP][Cazari] - Stingerea obligatiilor din E-taxe | Partial completion |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 5 | Carryovers blocked by partial completion |
| Dependency / competing work | 0 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 3 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

4 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot / movement | Issue count | Calculation | Link |
| --- | --- | --- | --- |
| Planning snapshot raw list | 14 | Frozen planning export before metric exclusions | Open JQL |
| Sprint review / outcome snapshot raw list | 19 | Frozen review export before metric exclusions | Open JQL |
| Normalized sprint fact base | 19 | Deduplicated union used by metrics after canceled/cancelled exclusions | Open JQL |
| Metric planning baseline | 14 | Non-canceled issue keys present in the frozen planning snapshot | Open JQL |
| Metric outcome snapshot | 19 | Non-canceled issue keys present in the frozen sprint-review snapshot | Open JQL |
| Planned and still present at review | 14 | planning_snapshot_present = true and outcome_snapshot_present = true | Open JQL |
| Added after planning | 5 | planning_snapshot_present = false and outcome_snapshot_present = true | Open JQL |
| Planned but missing from review | 0 | planning_snapshot_present = true and outcome_snapshot_present = false | Open JQL |
| Metric-excluded canceled/cancelled rows | 0 | Rows preserved in audit but excluded from every numerator and denominator | Open JQL |

Planning and outcome are separate frozen moments. Raw snapshot counts can be larger than metric counts because canceled/cancelled rows stay in audit but leave all metric denominators.

Added after planning is snapshot-based: present in the outcome snapshot and absent from the planning snapshot. Planned but missing from review shows items that left the sprint snapshot before review.

# Metric register addendum

| Metric | Value | Formula | Numerator / denominator | Denominator evidence |
| --- | --- | --- | --- | --- |
| Visible sprint items | 19 | all rows in the outcome snapshot | 19/19 | Open denominator JQL |
| Delivered items | 9 | rows whose Sprint Outcome is Done | 9/19 | Open denominator JQL |
| Carry overs | 10 | rows whose Sprint Outcome is Carry Over or remained open in review | 10/19 | Open denominator JQL |
| Stories done | 2 | done items where issue type = Story | 2/9 | Open denominator JQL |
| Tasks done | 1 | done items where issue type = Task | 1/9 | Open denominator JQL |
| Bugs done | 6 | done items where issue type = Bug | 6/9 | Open denominator JQL |
| Entry kind mix | 14 / 5 / 0 | Planned / Added / Stretch counts across all visible sprint items | 19/19 | Open denominator JQL |
| Readiness mix | 2 / 17 / 0 | Ready / At risk / Not Ready counts across all visible sprint items | 19/19 | Open denominator JQL |
| Progress items behaving as intended | 4/5 | progress-intent items that carried as intended ÷ all progress-intent committed items | 4/5 | Open denominator JQL |
| Partial completion misses | 5 | carryover items whose miss reason is Partial completion | 5/10 | Open denominator JQL |
| Dependency / competing work misses | 0 | carryover items whose miss reason is Dependency delay | 0/10 | Open denominator JQL |
| Not-started misses | 3 | carryover items whose miss reason is Not started | 3/10 | Open denominator JQL |

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.