Product Pulse — University ADS Q3 W27 - 06-10 Jul
Planned sprint ADS Q3 W27 - 06-10 Jul • planning snapshot + end-of-sprint outcome snapshot
This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.
Executive summary
Yellow. The sprint closed 6 of 24 visible items, including 0 Stories, 3 Tasks, and 3 Bugs. Product movement was real, but the sprint was still noisy: 18 items entered after planning and 6 of them were closed. The main misses were concentrated in 18 carryovers.
Top-line metrics
	Metric
	Value
	How to read it

	Visible sprint items
	24
	Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses

	Delivered items
	6
	Items whose final outcome bucket is Done

	Carry overs
	18
	Items not closed at sprint review

	Delivered mix
	0 / 3 / 3
	Stories / Tasks / Bugs delivered

	Entry kind mix
	6 / 18 / 0
	Planned / Added during sprint / Stretch visible

	Readiness mix
	4 / 20 / 0
	Ready / At risk / Not Ready across the normalized sprint fact base

	Progress items behaving as intended
	5/5
	Progress items were expected not to finish in this sprint


Stories done (0)
Below are the items marked Done in the sprint review snapshot, grouped by work-item type.
	Jira item
	How entered


Tasks done (3)
	Jira item
	How entered

	ADS-8000 — [UNI][Denumire disciplina] Refactor atribut Denumire disciplina - loc
	Added

	ADS-8010 — [BE] -Pe disciplina s-au modificat procentele
	Added

	ADS-8056 — [BE] -Inchiderea cataloagelor istorice pentru facultatea CMMI
	Added


Bugs done (3)
	Jira item
	How entered

	ADS-8135 — [BE-PHP][Cazari] - Neconcordanta de solduri pentru un student
	Added

	ADS-8150 — [Prod][AWS][uni-api] POST /api/v2/uni/structure/SECTIE returns 500 when saving section group - 12 errors/72h
	Added

	ADS-8190 — [Prod][TUIASI][uni-api] Student profile section lookup joins missing sec.idGrup - 7 errors/72h
	Added


Carry overs / not delivered (18)
	Jira item
	Why it carried

	ADS-6438 — Task — [BE][UNI] - Sincronizare ID-uri Ani universitari/scolari - UNI/preuni - master
	

	ADS-7495 — Story — [FE/BE][Adeverinte absolvire] - Creare Probe evaluare
	Dependency delay

	ADS-7496 — Story — [FE/BE][Adeverinte absolvire] - Probe&medie pe situatie scolara
	Dependency delay

	ADS-7534 — Story — [FE/BE][Adeverinte absolvire] - Flow generare adeverinte
	Partial completion

	ADS-7535 — Story — [FE] - Download Adeverinta de absolvire
	Dependency delay

	ADS-7666 — Bug — accommodations-api: shared HTTP 500 burst on POST /api/v2/accommodations/dorms/list and related endpoints - 16 hits/20m
	Bug / rework pressure

	ADS-7890 — Story — [BE PHP][Cazari] - Stingerea obligatiilor din E-taxe
	Dependency delay

	ADS-7952 — Story — [Burse] - US1 - Implementare mecanism Atribute
	Partial completion

	ADS-7958 — Story — [FE/BE] -  Reconstituire scolaritate - transfer, an repetare
	Partial completion

	ADS-8073 — Task — [FE/BE] - Aducerea titularilor din planul curent in tab-ul restantieri pe disciplina
	Partial completion

	ADS-8104 — Story — [BE-PHP] - Gestiunea cazarilor de vara
	

	ADS-8111 — Bug — [FE/BE] - In centralizator note nu apare numele unei discipline
	Not started

	ADS-8118 — Bug — [BE] - Lipsa nota si catalog deschis pe restantieri
	Not started

	ADS-8141 — Task — [FE][Situatie scolara] - Lipsa mesaj de eroare la  modificarea mediei de absolvire
	Not started

	ADS-8147 — Bug — [BE] - Nu apar studentii pe sesiunea 2
	Not started

	ADS-8153 — Bug — [Prod][TUIASI][accommodations-api] Student balance export returns HTTP 500 when mPDF hits pcre.backtrack_limit
	Not started

	ADS-8186 — Bug — [Prod][AWS][accommodations-api] External person create returns 500 after partial create when fallback faculty is hidden by scope
	Bug / rework pressure

	ADS-8188 — Task — Extindere import studenti cu coloana sectie
	


Blocker / miss pattern
	Metric
	Value
	How to read it

	Partial completion
	4
	Carryovers blocked by partial completion

	Dependency / competing work
	4
	Delivery slipped because attention or dependency landed elsewhere

	Not started
	5
	Committed item never really got underway


Data-quality caveats
This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.
5 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.
Traceability / drill-down
	Report element
	How to drill down
	Traceability mechanism

	Delivered Stories / Tasks / Bugs
	Click the section count rows
	Snapshot-exact JQL by issuekey list

	Carry overs / not delivered
	Click the Carry overs count
	Snapshot-exact JQL by issuekey list

	Miss pattern summary
	Click each miss-pattern count
	Snapshot-exact JQL by issuekey list


Snapshot and fact-base list links
	Snapshot
	Issue count
	Link

	Planning snapshot raw list
	21
	21 issues in the planning snapshot

	Sprint review / outcome snapshot raw list
	24
	24 issues in the Friday review snapshot

	Normalized sprint fact base
	24
	24 issues used for metrics and drill-down


Planning and outcome are separate frozen moments.
Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.
Evidence artifacts
	Artifact
	Link

	Issue audit register
	Open issue-level audit CSV

	Metric lineage
	Open metric lineage CSV

	JQL traceability register
	Open JQL traceability CSV

	Sprint metrics JSON
	Open sprint metrics JSON


Use these files when you need to validate the exact rows and formulas behind a pulse claim.




