# Product Pulse — University ADS Q3 W27 - 06-10 Jul

Planned sprint ADS Q3 W27 - 06-10 Jul • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 6 of 24 visible items, including 0 Stories, 3 Tasks, and 3 Bugs. Product movement was real, but the sprint was still noisy: 18 items entered after planning and 6 of them were closed. The main misses were concentrated in 18 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 24 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 6 | Items whose final outcome bucket is Done |
| Carry overs | 18 | Items not closed at sprint review |
| Delivered mix | 0 / 3 / 3 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 6 / 18 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 4 / 20 / 0 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 5/5 | Progress items were expected not to finish in this sprint |

# Stories done (0)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |

# Tasks done (3)

| Jira item | How entered |
| --- | --- |
| ADS-8000 — [UNI][Denumire disciplina] Refactor atribut Denumire disciplina - loc | Added |
| ADS-8010 — [BE] -Pe disciplina s-au modificat procentele | Added |
| ADS-8056 — [BE] -Inchiderea cataloagelor istorice pentru facultatea CMMI | Added |

# Bugs done (3)

| Jira item | How entered |
| --- | --- |
| ADS-8135 — [BE-PHP][Cazari] - Neconcordanta de solduri pentru un student | Added |
| ADS-8150 — [Prod][AWS][uni-api] POST /api/v2/uni/structure/SECTIE returns 500 when saving section group - 12 errors/72h | Added |
| ADS-8190 — [Prod][TUIASI][uni-api] Student profile section lookup joins missing sec.idGrup - 7 errors/72h | Added |

# Carry overs / not delivered (18)

| Jira item | Why it carried |
| --- | --- |
| ADS-6438 — Task — [BE][UNI] - Sincronizare ID-uri Ani universitari/scolari - UNI/preuni - master |  |
| ADS-7495 — Story — [FE/BE][Adeverinte absolvire] - Creare Probe evaluare | Dependency delay |
| ADS-7496 — Story — [FE/BE][Adeverinte absolvire] - Probe&medie pe situatie scolara | Dependency delay |
| ADS-7534 — Story — [FE/BE][Adeverinte absolvire] - Flow generare adeverinte | Partial completion |
| ADS-7535 — Story — [FE] - Download Adeverinta de absolvire | Dependency delay |
| ADS-7666 — Bug — accommodations-api: shared HTTP 500 burst on POST /api/v2/accommodations/dorms/list and related endpoints - 16 hits/20m | Bug / rework pressure |
| ADS-7890 — Story — [BE PHP][Cazari] - Stingerea obligatiilor din E-taxe | Dependency delay |
| ADS-7952 — Story — [Burse] - US1 - Implementare mecanism Atribute | Partial completion |
| ADS-7958 — Story — [FE/BE] - Reconstituire scolaritate - transfer, an repetare | Partial completion |
| ADS-8073 — Task — [FE/BE] - Aducerea titularilor din planul curent in tab-ul restantieri pe disciplina | Partial completion |
| ADS-8104 — Story — [BE-PHP] - Gestiunea cazarilor de vara |  |
| ADS-8111 — Bug — [FE/BE] - In centralizator note nu apare numele unei discipline | Not started |
| ADS-8118 — Bug — [BE] - Lipsa nota si catalog deschis pe restantieri | Not started |
| ADS-8141 — Task — [FE][Situatie scolara] - Lipsa mesaj de eroare la modificarea mediei de absolvire | Not started |
| ADS-8147 — Bug — [BE] - Nu apar studentii pe sesiunea 2 | Not started |
| ADS-8153 — Bug — [Prod][TUIASI][accommodations-api] Student balance export returns HTTP 500 when mPDF hits pcre.backtrack_limit | Not started |
| ADS-8186 — Bug — [Prod][AWS][accommodations-api] External person create returns 500 after partial create when fallback faculty is hidden by scope | Bug / rework pressure |
| ADS-8188 — Task — Extindere import studenti cu coloana sectie |  |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 4 | Carryovers blocked by partial completion |
| Dependency / competing work | 4 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 5 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

5 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 21 | 21 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 24 | 24 issues in the Friday review snapshot |
| Normalized sprint fact base | 24 | 24 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.