# Product Pulse — University ADS Q3 W36 - 07-11 Sep

Planned sprint ADS Q3 W36 - 07-11 Sep • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 14 of 24 visible items, including 1 Stories, 3 Tasks, and 9 Bugs. Product movement was real, but the sprint was still noisy: 6 items entered after planning and 5 of them were closed. The main misses were concentrated in 10 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 24 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 14 | Items whose final outcome bucket is Done |
| Carry overs | 10 | Items not closed at sprint review |
| Delivered mix | 1 / 3 / 9 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 18 / 6 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 6 / 15 / 2 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 6/6 | Progress items were expected not to finish in this sprint |

# Stories done (1)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |
| ADS-8722 — [BE/FE] [State de functii] Configurare nr semigrupe, filtru departament in planul de invatamant | Added |

# Tasks done (3)

| Jira item | How entered |
| --- | --- |
| ADS-8448 — [BE] [State de Functii] Permisiuni dedicate modul | Added |
| ADS-8579 — [UNI][FE][BE] Permisune Acces secțiunea Documente | Planned |
| ADS-8665 — [BE/FE][State de functii]Refactor reduceri aplicate pentru functia de conducere | Added |

# Bugs done (9)

| Jira item | How entered |
| --- | --- |
| ADS-8509 — Universitatea Petre Andrei- nu se afiseaza informatiile din modulul Statistici si rapoarte | Planned |
| ADS-8534 — Asachi - Nu afiseaza an de studiu pentru studentii din anul 1 (2025-2026)din situatie scolara | Planned |
| ADS-8597 — [Asachi] - nu se salveaza echivalarea disciplinei Educatie fizica si sport | Added |
| ADS-8632 — [Prod][TUIASI][uni-api] Missing disciplina.idDepartament causes catalog status HTTP 500 - 1,042 errors | Planned |
| ADS-8652 — [Asachi] - Modificare numar credite si inchidere catalog | Planned |
| ADS-8681 — [Prod][TUIASI][Web] Certificate list uses unsupported MariaDB JSON operator and returns HTTP 500 | Planned |
| ADS-8683 — [Prod][AWS][Uni] Missing workload_percentage tenant migration breaks position creation | Planned |
| ADS-8685 — [Prod][AWS][uni-api] Missing mentiune migration breaks student discipline list | Planned |
| ADS-8696 — [Asachi] - modificare student in platforma | Added |

# Carry overs / not delivered (10)

| Jira item | Why it carried |
| --- | --- |
| ADS-7559 — Story — [UPG] - Adeverinte de student | Partial completion |
| ADS-8160 — Story — [Burse] - US3 - Configurare burse | Partial completion |
| ADS-8161 — Story — [Burse] - US4 - Alocare burse | Partial completion |
| ADS-8164 — Story — [Burse] - US6 - Rapoarte | Not started |
| ADS-8179 — Story — [Registre Matricole] - US2 Incarcare atribute studenti pentru popularea registrelor matricole | Partial completion |
| ADS-8326 — Bug — [BE-PHP][Cazari] - La decazare soldurie apar incorect fata de fisa studentilor | Breakdown issue |
| ADS-8593 — Bug — [Prod][TUIASI][legacy-web] Admin edit reads missing suppressAdminEvent flag - 2 warnings/72h | Not started |
| ADS-8667 — Story — [FE/BE] Lista imbunatatiri dupa demo 3.09.26 | Missing from outcome snapshot |
| ADS-8682 — Bug — [Prod][TUIASI][Accommodations] Dependency failures cause report and list HTTP 500 burst | Not started |
| ADS-8706 — Story — [BE/FE]Cazari - Contract nou perioada didactica | Partial completion |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 4 | Carryovers blocked by partial completion |
| Dependency / competing work | 0 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 3 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

6 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 20 | 20 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 23 | 23 issues in the Friday review snapshot |
| Normalized sprint fact base | 24 | 24 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.