# Product Pulse — University ADS Q3 W38 - 21-25 Sep

Planned sprint ADS Q3 W38 - 21-25 Sep • planning snapshot + end-of-sprint outcome snapshot

This retrospective uses the planning snapshot as the baseline promise set for sprint intent and entry kind, and the outcome snapshot as the actual end-of-sprint result.

# Executive summary

Yellow. The sprint closed 8 of 23 visible items, including 3 Stories, 1 Tasks, and 4 Bugs. Product movement was real, but the sprint was still noisy: 9 items entered after planning and 3 of them were closed. The main misses were concentrated in 15 carryovers.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Visible sprint items | 23 | Normalized sprint fact base: planning baseline plus outcome additions and planning-only misses |
| Delivered items | 8 | Items whose final outcome bucket is Done |
| Carry overs | 15 | Items not closed at sprint review |
| Delivered mix | 3 / 1 / 4 | Stories / Tasks / Bugs delivered |
| Entry kind mix | 14 / 9 / 0 | Planned / Added during sprint / Stretch visible |
| Readiness mix | 13 / 9 / 1 | Ready / At risk / Not Ready across the normalized sprint fact base |
| Progress items behaving as intended | 5/7 | Progress items were expected not to finish in this sprint |

# Stories done (3)

Below are the items marked Done in the sprint review snapshot, grouped by work-item type.

| Jira item | How entered |
| --- | --- |
| ADS-7559 — [UPG] - Adeverinte de student | Planned |
| ADS-8177 — [State de functii] - Rapoarte 20 sept | Planned |
| ADS-8179 — [Registre Matricole] - US2 Incarcare atribute studenti pentru popularea registrelor matricole | Planned |

# Tasks done (1)

| Jira item | How entered |
| --- | --- |
| ADS-8871 — [Cazari] - Import studenti Erasmus an universitar 2026-2027 | Added |

# Bugs done (4)

| Jira item | How entered |
| --- | --- |
| ADS-8751 — [FE] Import note bulk are success dar nu importa notele | Planned |
| ADS-8786 — [Asachi] - Schimbare numar credite la o disciplina | Planned |
| ADS-8860 — [Prod][AWS][uni-api] Staff sync returns 500 when duplicate person mappings violate single-result contract - 2 requests/72h | Added |
| ADS-8896 — [Prod][AWS][uni-api] Invalid identity date poisons bulk-import Hibernate session - 12 traces/72h | Added |

# Carry overs / not delivered (15)

| Jira item | Why it carried |
| --- | --- |
| ADS-8161 — Story — [Burse] - US4 - Alocare burse | Partial completion |
| ADS-8162 — Story — [Burse] - US5 - Plati | Partial completion |
| ADS-8166 — Story — [Burse] - US7 - View Student/actiuni student | Partial completion |
| ADS-8599 — Story — [Asachi][BE/FE] Ajustari echivalari note | Partial completion |
| ADS-8682 — Bug — [Prod][TUIASI][Accommodations] Dependency failures cause report and list HTTP 500 burst | Partial completion |
| ADS-8763 — Task — [Asachi][BE] Import studenti pentru anul universitar 2026-2027 | Dependency delay |
| ADS-8804 — Bug — [Asachi] - Student duplicat in catalog de restantieri la descarcare | Not started |
| ADS-8810 — Bug — [Asachi] - Eroare alocare restantieri | Not started |
| ADS-8812 — Story — Download RM | Partial completion |
| ADS-8879 — Bug — [Asachi] - Eroare acces student in UMS | Not started |
| ADS-8888 — Bug — [Cazari] - Eroare la export fisier | Partial completion |
| ADS-8893 — Bug — [Cazari] - Corectii sold | Partial completion |
| ADS-8897 — Bug — [Prod][TUIASI][Accommodations] Missing studentId makes accommodation create return HTTP 500 | Partial completion |
| ADS-8938 — Bug — [Asachi] - Problema echivalari | Not started |
| ADS-8972 — Bug — [Asachi] - Problema incheiere media anuala master | Not started |

# Blocker / miss pattern

| Metric | Value | How to read it |
| --- | --- | --- |
| Partial completion | 5 | Carryovers blocked by partial completion |
| Dependency / competing work | 1 | Delivery slipped because attention or dependency landed elsewhere |
| Not started | 3 | Committed item never really got underway |

# Data-quality caveats

This product pulse is retrospective only and uses the planning snapshot for baseline fields and the outcome snapshot for actuals.

5 rows have Sprint Intent = Progress and remained open; they are treated as healthy continuation rather than finish misses.

# Traceability / drill-down

| Report element | How to drill down | Traceability mechanism |
| --- | --- | --- |
| Delivered Stories / Tasks / Bugs | Click the section count rows | Snapshot-exact JQL by issuekey list |
| Carry overs / not delivered | Click the Carry overs count | Snapshot-exact JQL by issuekey list |
| Miss pattern summary | Click each miss-pattern count | Snapshot-exact JQL by issuekey list |

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 14 | 14 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 24 | 24 issues in the Friday review snapshot |
| Normalized sprint fact base | 23 | 23 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

Use these files when you need to validate the exact rows and formulas behind a pulse claim.